## Dawaiyat Service Tool
Link Code | Work Order | Percentage of Completion | Region | Project | Subclass | Stage | WO Cost | Cost | Created | Assigned at | In Progress at | Year | Targeted Completion | Updated Target Date | Updated | Updates | Trench Progress | Trench Scope | MH/HH Progress | MH/HH Scope | Number of Buildings | Number of Households | Parcels | Fiber Progress | Fiber Scope | ODBs Progress | ODBs Scope | ODFs Progress | ODFs Scope | JCL Progress | JCL Scope | FAT Progress | FAT Scope | PFAT Progress | PFAT Scope | SFAT Progress | SFAT Scope | Work Order Status | Cancel Reason | Type | Class | Closed at | Permit Review | Permit Completion Status | Permits Progress | Permits Scope | PIP rejection count | PAT rejection count | Approval rejection count | As-Built Rejection Count | Handover Rejection Count | Parent | Number | Request | SOR Reference Number | Target Area | Notes | Scope of Work
JED-HRR2-SALH-04 | 2502OSPFI0002425 | 116.34 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 212790.6 | 212790.6 | 2025-08-12 13:27 | 2025-08-12 13:27 | 2025-08-12 22:54 | 2025 | 2025-12-25 |  | 2026-03-01 12:48 | 22 | 0 | 0 | 0 | 0 | 151 | 300 |  | 22800 | 19590 | 156 | 151 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002480 | OSPWO0021620 | RITM0070553 |  | 2376401 | 17/02/2026 13:58:43 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-63 | 2502OSPCI0002401 | 100.42 | MAKKAH | FTTH | Civil | 6 - PAT Approval | 656375.1 | 655335 | 2025-08-15 13:47 | 2025-08-15 13:47 | 2025-08-15 13:48 | 2025 | 2025-09-30 | 2025-09-30 | 2026-03-26 14:59 | 41 | 4072 | 4055 | 14 | 14 | 291 | 117 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001497 | OSPWO0021676 | RITM0070690 |  | 2383801 | 13/11/2025 11:13:49 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-60 | 2502OSPFI0002428 | 100.12 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 253854.55 | 255575 | 2025-08-12 22:56 | 2025-08-12 22:56 | 2025-08-12 22:56 | 2025 | 2025-10-31 | 2025-11-30 | 2026-01-21 16:57 | 42 | 0 | 0 | 0 | 0 | 200 | 237 |  | 26028 | 26028 | 225 | 200 | 0 | 0 | 0 | 0 | 6 | 12 | 0 | 0 | 12 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001532 | OSPWO0021636 | RITM0070557 |  | 2383801 | 21/01/2026 16:57:19 - Mohammad Nasser AlHayaya (Notes) Approved by DWT PM 01 ODB not Implemented (D9175475001)as customer refused the service. 19/01/2026 23:13:50 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 03/12/2025 19:18:27 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs not yet implemented 30/09/2025 09:24:07 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-71 | 2502OSPFI0002431 | 100.09 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 155991.15 | 157081 | 2025-08-12 23:08 | 2025-08-12 23:08 | 2025-08-12 23:08 | 2025 | 2025-10-19 |  | 2026-01-12 22:09 | 22 | 0 | 0 | 0 | 0 | 109 | 117 |  | 14680 | 14680 | 110 | 109 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 12 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001534 | OSPWO0021648 | RITM0070563 |  | 2383801 | 12/01/2026 22:09:18 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-64 | 2502OSPFI0002429 | 100.06 | MAKKAH | FTTH | Fiber | 6 - PAT Approval | 116028.5 | 116689 | 2025-08-12 22:59 | 2025-08-12 22:59 | 2025-08-12 23:00 | 2025 | 2025-10-18 | 2025-11-27 | 2026-03-26 15:05 | 53 | 0 | 0 | 0 | 0 | 66 | 107 |  | 10780 | 10780 | 78 | 72 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 10 | 10 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 2402OSPFD0001536 | OSPWO0021640 | RITM0070559 |  | 2383801 | 12/01/2026 22:12:12 - Mohammad Nasser AlHayaya (Notes) Approved 06/01/2026 12:35:18 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs not yet implemented 24/12/2025 14:16:18 - Mohammad Nasser AlHayaya (Notes) Reject 1 ODB not yet implemented 25/11/2025 15:45:39 - Muhammad Nabeel Shahid (Notes) Reject, 1 ODB not implemented
JED-HRR2-RIYA-63 | 2502OSPFI0002437 | 100.04 | MAKKAH | FTTH | Fiber | 6 - PAT Approval | 153548.6 | 154589 | 2025-08-15 13:48 | 2025-08-15 13:48 | 2025-08-15 13:49 | 2025 | 2025-10-22 | 2025-11-30 | 2026-03-26 15:02 | 50 | 0 | 0 | 0 | 0 | 104 | 117 |  | 14108 | 14108 | 110 | 104 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 12 | 12 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001535 | OSPWO0021678 | RITM0070691 |  | 2383801 | 12/01/2026 22:10:06 - Mohammad Nasser AlHayaya (Notes) Approved 24/12/2025 14:14:49 - Mohammad Nasser AlHayaya (Notes) Reject 12 ODBs not yet implemented 25/11/2025 15:41:48 - Muhammad Nabeel Shahid (Notes) Reject, 12 ODBs not implemented 30/09/2025 09:24:55 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-69 | 2502OSPFI0002440 | 100.01 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 160210.05 | 161020 | 2025-08-15 14:00 | 2025-08-15 14:00 | 2025-08-15 14:01 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:49 | 29 | 0 | 0 | 0 | 0 | 81 | 242 |  | 13654 | 13654 | 81 | 81 | 0 | 0 | 0 | 0 | 13 | 12 | 0 | 0 | 16 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2402OSPFD0001541 | OSPWO0021690 | RITM0070696 |  | 2383801 | 29/01/2026 10:43:38 - Mohammad Nasser AlHayaya (Notes) Approved 21/01/2026 16:51:08 - Mohammad Nasser AlHayaya (Notes) Reject, 4 ODBs still not implemented
JED-HRR2-RIYA-67 | 2502OSPFI0002441 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 189267 | 190367 | 2025-08-15 14:03 | 2025-08-15 14:03 | 2025-08-15 14:04 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:46 | 24 | 0 | 0 | 0 | 0 | 110 | 314 |  | 17905 | 17905 | 110 | 110 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001539 | OSPWO0021694 | RITM0070698 |  | 2383801 | 06/01/2026 12:33:34 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-49 | 2602OSPCI0000001 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 726851 | 726851 | 2026-01-01 11:52 | 2026-01-01 11:52 | 2026-01-01 11:53 | 2026 | 2026-02-28 |  | 2026-02-25 01:00 | 15 | 6446 | 6446 | 15 | 15 | 63 | 282 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000732 | OSPWO0026525 | RITM0083098 |  | 2387401
SHU-AZRQ-JORI-01 | 2510OSPCI0002892 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 282978.6 | 282978.6 | 2025-10-27 08:48 | 2025-10-27 08:48 | 2025-10-27 08:51 | 2025 | 2026-09-30 |  | 2026-02-18 11:36 | 24 | 2153 | 2153 | 9 | 9 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 5 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023906 | RITM0076018 |  | 8485201 | 27/01/2026 14:22:48 - Husam Jari (Notes) Proposed Target is Rejected. Revise the Date with PM
JED-HRR2-SALH-11 | 2502OSPCI0002952 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 813766.1 | 813766 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025 | 2026-01-30 |  | 2026-03-09 16:06 | 30 | 7854 | 7854 | 15 | 15 | 170 | 139 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2502OSPCD0000018 | OSPWO0024249 | RITM0076721 |  | 2376401 | 29/01/2026 10:41:06 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still in Progress
SHU-AZRQ-JORI-01 | 2510OSPFI0002901 | 100 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 45367.1 | 45367.1 | 2025-10-27 08:49 | 2025-10-27 08:49 | 2025-10-27 08:51 | 2025 | 2026-09-30 |  | 2026-02-18 11:37 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2304 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023908 | RITM0076019 |  | 8485201
JED-HRR2-SALH-03 | 2502OSPCI0002389 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 803540.7 | 803540.7 | 2025-08-12 13:24 | 2025-08-12 13:24 | 2025-08-12 15:20 | 2025 | 2025-11-30 | 2025-12-10 | 2026-03-01 12:48 | 46 | 5626 | 5626 | 12 | 12 | 155 | 342 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 2402OSPCD0002455 | OSPWO0021614 | RITM0070520 |  | 2376401 | 29/01/2026 10:42:02 - Mohammad Nasser AlHayaya (Notes) Approved 25/01/2026 13:35:36 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress 30/09/2025 09:31:44 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RAHA-18 | 2502OSPCI0003104 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 1364392.9 | 1362703 | 2025-11-16 22:38 | 2025-11-16 22:38 | 2025-11-16 22:39 | 2025 | 2026-01-11 |  | 2026-03-09 17:22 | 30 | 10280 | 10280 | 18 | 18 | 170 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000008 | OSPWO0024972 | RITM0077705 |  | 2376401
JED-HRR2-RIYA-38 | 2502OSPCI0002861 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 932366 | 932366 | 2025-10-11 22:38 | 2025-10-11 22:38 | 2025-10-11 22:39 | 2025 | 2026-03-28 |  | 2026-03-10 22:49 | 18 | 7550 | 7550 | 16 | 16 |  |  | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000693 | OSPWO0023694 | RITM0075247 |  | 2387401
JED-HRR2-SALH-05 | 2502OSPCI0002391 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 913312.1 | 913312.1 | 2025-08-12 13:28 | 2025-08-12 13:28 | 2025-08-12 15:21 | 2025 | 2025-12-04 | 2026-01-12 | 2026-03-01 13:21 | 32 | 6628 | 6628 | 14 | 14 | 169 | 368 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002457 | OSPWO0021622 | RITM0070522 |  | 2376401 | 24/02/2026 15:33:07 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:32:28 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-F6 | 2502OSPFI0002488 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 304001.2 | 304001 | 2025-08-23 21:28 | 2025-08-23 21:28 | 2025-09-04 11:20 | 2025 | 2025-10-25 | 2025-11-30 | 2026-03-03 13:46 | 47 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26520 | 26520 | 0 | 0 | 4 | 4 | 3 | 3 | 4 | 4 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001542 | OSPWO0021887 | RITM0072341 |  | 2383801 | 03/03/2026 13:45:46 - Mohammad Nasser AlHayaya (Notes) Approved 21/01/2026 16:50:06 - Mohammad Nasser AlHayaya (Notes) Reject, work not yet started 12/01/2026 21:48:28 - Mohammad Nasser AlHayaya (Notes) Reject, No inspector assignment requested 30/09/2025 09:30:50 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-60 | 2502OSPCI0002392 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 900061.6 | 821262 | 2025-08-12 22:55 | 2025-08-12 22:55 | 2025-08-12 22:56 | 2025 | 2025-10-05 | 2025-10-18 | 2026-01-21 16:58 | 44 | 6547 | 6547 | 12 | 12 | 297 | 236 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 2402OSPCD0001494 | OSPWO0021634 | RITM0070556 |  | 2383801 | 21/01/2026 16:58:05 - Mohammad Nasser AlHayaya (Notes) Approved by DWT PM, 01 ODB not Implemented (D9175475001) as customer refused the service. 19/01/2026 23:14:44 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 12/01/2026 21:59:29 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs Not Yet Implemented
JED-HRR2-SALH-02 | 2502OSPFI0002415 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 242464.65 | 242464.65 | 2025-08-10 11:33 | 2025-08-10 11:33 | 2025-08-12 22:53 | 2025 | 2025-12-17 |  | 2026-03-01 12:48 | 22 | 0 | 0 | 0 | 0 | 171 | 424 |  | 22520 | 22520 | 177 | 177 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 12 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002478 | OSPWO0021579 | RITM0070551 |  | 2376401 | 17/02/2026 13:47:16 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-02 | 2502OSPCI0002388 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 932260.7 | 932260.7 | 2025-08-12 13:20 | 2025-08-12 13:20 | 2025-08-12 15:20 | 2025 | 2025-11-27 | 2025-12-14 | 2026-03-01 12:48 | 42 | 6557 | 6557 | 14 | 14 | 171 | 424 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002454 | OSPWO0021612 | RITM0070519 |  | 2376401 | 25/01/2026 13:38:44 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:31:21 - Mufleh Alsulami (Notes) Revise the target with project manger
MOY-MOYH-KHAL-01 | 2502OSPFI0002445 | 100 | MAKKAH | FEP-Phase1 | Fiber | 5 - Conducting PAT | 186673.2 | 171378 | 2025-08-16 18:30 | 2025-08-16 18:30 | 2025-08-16 18:30 | 2025 | 2025-09-05 |  | 2026-01-01 14:09 | 32 | 0 | 0 | 0 | 0 | 2 | 2 |  | 288 | 288 | 2 | 2 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | OSPWO0021711 | RITM0070780 |  | 2759401 | 01/01/2026 14:08:36 - Mohammad Nasser AlHayaya (Notes) Reject, PAT Documents missing DCR Pending with no report submitted 13/11/2025 11:14:19 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-66 | 2502OSPFI0002438 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 166999.9 | 168000 | 2025-08-15 13:54 | 2025-08-15 13:54 | 2025-08-15 13:55 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:46 | 23 | 0 | 0 | 0 | 0 | 100 | 309 |  | 13986 | 13986 | 100 | 100 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001538 | OSPWO0021682 | RITM0070692 |  | 2383801 | 12/01/2026 22:05:02 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-64 | 2502OSPCI0002393 | 100 | MAKKAH | FTTH | Civil | 6 - PAT Approval | 613447 | 612787 | 2025-08-12 22:59 | 2025-08-12 22:59 | 2025-08-12 23:00 | 2025 | 2025-09-29 | 2025-09-29 | 2026-03-26 15:03 | 40 | 3918 | 3918 | 11 | 11 | 281 | 107 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001498 | OSPWO0021638 | RITM0070558 |  | 2383801 | 13/11/2025 11:15:25 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-67 | 2502OSPCI0002405 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 847493.4 | 846393 | 2025-08-15 14:03 | 2025-08-15 14:03 | 2025-08-15 14:04 | 2025 | 2025-10-31 |  | 2026-03-02 14:46 | 36 | 6642 | 6642 | 12 | 12 | 110 | 314 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 2402OSPCD0001501 | OSPWO0021692 | RITM0070699 |  | 2383801 | 12/01/2026 22:06:08 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 21:10:37 - Mufleh Alsulami (Notes) Revise the target with project manager 30/09/2025 09:29:56 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-10 | 2502OSPCI0002823 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 904296.7 | 904297 | 2025-10-06 09:57 | 2025-10-06 09:57 | 2025-10-06 09:58 | 2025 | 2026-01-28 |  | 2026-03-09 16:06 | 23 | 6633 | 6633 | 14 | 14 | 179 | 137 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000017 | OSPWO0023535 | RITM0074722 |  | 2376401 | 25/01/2026 13:39:10 - Mohammad Nasser AlHayaya (Notes) Approved
SHU-AZRQ-SHUQ-01 | 2510OSPCI0002893 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 1574004 | 1574004 | 2025-10-27 08:50 | 2025-10-27 08:50 | 2025-10-27 08:51 | 2025 | 2026-09-30 |  | 2026-02-18 11:38 | 19 | 11603 | 11603 | 56 | 56 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 5 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023910 | RITM0076020 |  | 8485401
JED-HRR2-RIYA-68 | 2502OSPCI0002403 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 774818.4 | 773798 | 2025-08-15 13:56 | 2025-08-15 13:56 | 2025-08-15 13:58 | 2025 | 2025-10-31 | 2025-11-30 | 2026-03-02 14:48 | 37 | 6041 | 6041 | 13 | 13 | 102 | 304 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 2402OSPCD0001502 | OSPWO0021684 | RITM0070694 |  | 2383801 | 18/01/2026 14:26:20 - Mohammad Nasser AlHayaya (Notes) Approved 01/12/2025 20:19:27 - Mohammad Nasser AlHayaya (Notes) Reject, The remaining 5 HH to be installed, with 100 m to be excavated 30/09/2025 09:30:10 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-35 | 2502OSPCI0002983 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 666148 | 666148 | 2025-11-05 10:37 |  | 2025-11-05 10:37 | 2025 | 2026-02-25 |  | 2026-03-10 22:47 | 17 | 5300 | 5300 | 14 | 14 | 48 | 302 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000799 | OSPWO0024384 | RITM0076809 |  | 2387401
JED-HRR2-RIYA-47 | 2502OSPCI0002994 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 753767 | 753767 | 2025-11-05 10:45 |  | 2025-11-05 10:45 | 2025 | 2026-01-25 |  | 2026-03-01 14:13 | 23 | 5105 | 5105 | 14 | 14 | 79 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000650 | OSPWO0024428 | RITM0076831 |  | 2387401 | 21/01/2026 16:59:07 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-26 | 2502OSPCI0002979 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 726486 | 726486 | 2025-11-05 10:34 |  | 2025-11-05 10:34 | 2025 | 2026-01-25 |  | 2026-03-10 22:44 | 16 | 6300 | 6300 | 14 | 14 | 56 | 276 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000748 | OSPWO0024368 | RITM0076801 |  | 2387401
JED-HRR2-SALH-09 | 2502OSPFI0002954 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 217615.85 | 217616 | 2025-11-03 19:06 | 2025-11-03 19:06 | 2025-11-03 19:06 | 2025 | 2026-03-25 |  | 2026-03-11 14:54 | 22 | 0 | 0 | 0 | 0 | 146 | 139 |  | 22960 | 22960 | 169 | 169 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 20 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000016 | OSPWO0024204 | RITM0076643 |  | 2376401 | 11/03/2026 14:53:35 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-12 | 2502OSPFI0002839 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 278039.9 | 278040 | 2025-10-06 11:52 | 2025-10-06 11:52 | 2025-10-06 11:53 | 2025 | 2026-03-25 |  | 2026-03-11 14:54 | 18 | 0 | 0 | 0 | 0 | 204 | 135 |  | 28803 | 28803 | 230 | 230 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 15 | 15 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000019 | OSPWO0023600 | RITM0074761 |  | 2376401 | 11/03/2026 14:54:00 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-08 | 2502OSPFI0002822 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 195167.95 | 195168 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025 | 2026-02-27 |  | 2026-03-11 14:54 | 22 | 0 | 0 | 0 | 0 | 131 | 134 |  | 22650 | 22650 | 138 | 138 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000015 | OSPWO0023529 | RITM0074719 |  | 2376401 | 11/03/2026 14:54:29 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-66 | 2502OSPCI0002402 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 808777.9 | 807778 | 2025-08-15 13:53 | 2025-08-15 13:53 | 2025-08-15 13:55 | 2025 | 2025-10-31 |  | 2026-03-02 14:46 | 33 | 6162 | 6162 | 15 | 15 | 100 | 309 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0001500 | OSPWO0021680 | RITM0070693 |  | 2383801 | 12/01/2026 22:06:51 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:29:29 - Mufleh Alsulami (Notes) Revise the target with project manger
SAM-SMTH-KHAD-01 | 2510OSPCI0003073 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 670187 | 670187 | 2025-11-16 10:38 |  | 2025-11-16 10:38 | 2025 | 2026-09-30 |  | 2026-02-05 09:06 | 16 | 5015 | 5015 | 24 | 24 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 10 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024843 | RITM0077589 |  | 8673901
JED-HRR2-SALH-08 | 2502OSPCI0002821 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 875273.2 | 875273 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025 | 2026-01-26 |  | 2026-03-02 12:13 | 24 | 6263 | 6263 | 13 | 13 | 171 | 131 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000015 | OSPWO0023527 | RITM0074718 |  | 2376401 | 25/01/2026 13:39:35 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-25 | 2502OSPCI0002978 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 714254 | 714254 | 2025-11-05 10:34 |  | 2025-11-05 10:34 | 2025 | 2026-01-26 |  | 2026-03-01 14:13 | 24 | 5121 | 5121 | 11 | 11 | 84 | 257 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2302OSPCD0000739 | OSPWO0024364 | RITM0076799 |  | 2387401 | 12/02/2026 14:54:03 - Mohammad Nasser AlHayaya (Notes) Approved 25/01/2026 13:36:16 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress
SHU-AZRQ-SHUQ-01 | 2510OSPFI0002902 | 100 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 281335.4 | 281335.4 | 2025-10-27 08:51 | 2025-10-27 08:51 | 2025-10-27 08:51 | 2025 | 2026-09-30 |  | 2026-02-18 11:39 | 21 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12443 | 12443 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023912 | RITM0076021 |  | 8485401
JED-HRR2-RIYA-24 | 2502OSPCI0002977 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 760211 | 760211 | 2025-11-05 10:33 |  | 2025-11-05 10:33 | 2025 | 2026-01-24 |  | 2026-03-01 14:13 | 33 | 5455 | 5455 | 11 | 11 | 79 | 264 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 2302OSPCD0000763 | OSPWO0024360 | RITM0076797 |  | 2387401 | 17/02/2026 13:58:16 - Mohammad Nasser AlHayaya (Notes) Approved 12/02/2026 14:54:46 - Mohammad Nasser AlHayaya (Notes) Reject, 3 Span Not Yet IMPL 25/01/2026 13:37:08 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress
TAI-AYKB-QAMA-01 | 2502OSPFI0002770 | 100 | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 345947.4 | 288628 | 2025-09-28 08:36 | 2025-09-28 08:36 | 2025-09-28 08:36 | 2025 | 2026-04-30 |  | 2026-02-24 15:36 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16159 | 16159 | 0 | 0 | 1 | 1 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | OSPWO0023235 | RITM0073986 |  | 2634901 | 24/02/2026 15:36:12 - Mohammad Nasser AlHayaya (Notes) Not Yet Started
JED-HRR2-RIYA-23 | 2502OSPCI0003303 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 870181 | 870181 | 2025-12-22 22:51 | 2025-12-22 22:51 | 2025-12-22 22:52 | 2025 | 2026-02-07 |  | 2026-02-25 00:57 | 17 | 8470 | 8470 | 18 | 18 | 65 | 286 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000762 | OSPWO0026339 | RITM0080199 |  | 2387401
JED-HRR2-RIYA-69 | 2502OSPCI0002404 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 816783 | 815973 | 2025-08-15 13:59 | 2025-08-15 13:59 | 2025-08-15 14:01 | 2025 | 2025-10-31 | 2025-11-30 | 2026-03-02 14:48 | 35 | 6380 | 6380 | 14 | 14 | 81 | 242 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0001503 | OSPWO0021688 | RITM0070697 |  | 2383801 | 25/01/2026 13:41:11 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:30:25 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-09 | 2502OSPCI0002941 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 931223.5 | 931224 | 2025-11-03 19:06 | 2025-11-03 19:06 | 2025-11-03 19:07 | 2025 | 2026-02-28 |  | 2026-03-09 15:57 | 27 | 6685 | 6685 | 13 | 13 | 146 | 139 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000016 | OSPWO0024202 | RITM0076644 |  | 2376401 | 25/01/2026 13:41:46 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-37 | 2502OSPCI0002985 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 1003675 | 1003675 | 2025-11-05 10:39 |  | 2025-11-05 10:39 | 2025 | 2026-03-31 |  | 2026-03-10 22:53 | 17 | 8250 | 8250 | 18 | 18 | 45 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000640 | OSPWO0024392 | RITM0076813 |  | 2387401
JED-HRR2-SALH-04 | 2502OSPCI0002390 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 838015.3 | 838015.3 | 2025-08-12 13:26 | 2025-08-12 13:26 | 2025-08-12 15:20 | 2025 | 2025-12-05 |  | 2026-03-01 12:48 | 40 | 5703 | 5703 | 15 | 15 | 151 | 300 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002456 | OSPWO0021618 | RITM0070521 |  | 2376401 | 25/01/2026 13:42:25 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:32:13 - Mufleh Alsulami (Notes) Revise the target with project manger
MOY-MOYH-KHAL-01 | 2502OSPCI0002409 | 100 | MAKKAH | FEP-Phase1 | Civil | 5 - Conducting PAT | 936270.4 | 936270.4 | 2025-08-16 18:29 | 2025-08-16 18:29 | 2025-08-16 18:31 | 2025 | 2025-09-05 |  | 2026-01-01 11:46 | 31 | 6740 | 6740 | 26 | 26 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 9 | 9 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0021709 | RITM0070781 |  | 2759401 | 13/11/2025 11:16:29 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-68 | 2502OSPFI0002439 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 170711.45 | 171731 | 2025-08-15 13:57 | 2025-08-15 13:57 | 2025-08-15 13:58 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:48 | 25 | 0 | 0 | 0 | 0 | 102 | 304 |  | 14133 | 14133 | 102 | 102 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001540 | OSPWO0021686 | RITM0070695 |  | 2383801 | 18/01/2026 14:26:51 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-65 | 2502OSPCI0002695 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 1216284.2 | 1165710.2 | 2025-09-16 11:47 |  | 2025-09-16 11:47 | 2025 | 2025-10-09 | 2025-10-25 | 2026-03-02 14:45 | 35 | 7560 | 7560 | 20 | 20 | 309 | 283 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022886 | RITM0073181 |  | 2383801 | 12/01/2026 22:11:29 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-12 | 2502OSPCI0002838 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 1048065.3 | 1048065 | 2025-10-06 11:51 | 2025-10-06 11:51 | 2025-10-06 11:52 | 2025 | 2026-02-26 |  | 2026-03-02 12:14 | 21 | 7576 | 7576 | 13 | 13 | 204 | 135 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000019 | OSPWO0023598 | RITM0074760 |  | 2376401 | 25/01/2026 13:42:55 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-70 | 2502OSPCI0002394 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 771781.3 | 706747 | 2025-08-12 23:05 | 2025-08-12 23:05 | 2025-08-12 23:06 | 2025 | 2025-09-28 | 2025-10-18 | 2026-01-21 17:02 | 43 | 5525 | 5525 | 12 | 12 | 243 | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2402OSPCD0001495 | OSPWO0021642 | RITM0070560 |  | 2383801 | 21/01/2026 17:02:04 - Mohammad Nasser AlHayaya (Notes) Approved 19/01/2026 23:16:12 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented
JED-HRR2-RIYA-71 | 2502OSPCI0002395 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 649016.5 | 636503 | 2025-08-12 23:07 | 2025-08-12 23:07 | 2025-08-12 23:08 | 2025 | 2025-09-27 | 2025-09-30 | 2026-01-18 14:28 | 31 | 4614 | 4614 | 11 | 11 | 258 | 117 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001496 | OSPWO0021646 | RITM0070562 |  | 2383801 | 18/01/2026 14:27:41 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-65 | 2502OSPFI0002703 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 169864.45 | 170334.45 | 2025-09-16 11:47 |  | 2025-09-16 11:47 | 2025 | 2025-10-31 | 2025-12-31 | 2026-03-02 14:45 | 35 | 0 | 0 | 0 | 0 | 75 | 284 |  | 13593 | 13593 | 105 | 105 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0022888 | RITM0073182 |  | 2383801 | 06/01/2026 12:34:34 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:26:56 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-70 | 2502OSPFI0002430 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 271582.95 | 273553 | 2025-08-12 23:05 | 2025-08-12 23:05 | 2025-08-12 23:06 | 2025 | 2025-10-31 | 2025-11-25 | 2026-01-25 13:44 | 44 | 0 | 0 | 0 | 0 | 225 | 234 |  | 27813 | 27813 | 225 | 225 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 21 | 21 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001533 | OSPWO0021644 | RITM0070561 |  | 2383801 | 25/01/2026 13:43:58 - Mohammad Nasser AlHayaya (Notes) Approved 19/01/2026 23:16:56 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 25/11/2025 15:47:11 - Muhammad Nabeel Shahid (Notes) Reject, 3 ODB not implemented 30/09/2025 09:25:59 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-10 | 2502OSPFI0002824 | 99.93 | MAKKAH | FTTH | Fiber | 3 - Implementation | 225566.85 | 225567 | 2025-10-06 09:58 | 2025-10-06 09:58 | 2025-10-06 09:58 | 2025 | 2026-02-28 |  | 2026-03-09 16:06 | 17 | 0 | 0 | 0 | 0 | 171 | 137 |  | 21657 | 21657 | 177 | 171 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 2 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000017 | OSPWO0023537 | RITM0074723 |  | 2376401
JED-HRR2-SALH-05 | 2502OSPFI0002426 | 99.32 | MAKKAH | FTTH | Fiber | 3 - Implementation | 227271.35 | 227271.35 | 2025-08-12 13:29 | 2025-08-12 13:29 | 2025-08-12 22:54 | 2025 | 2025-12-23 |  | 2026-03-03 22:08 | 15 | 0 | 0 | 0 | 0 | 169 | 368 |  | 22530 | 22503 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002481 | OSPWO0021624 | RITM0070554 |  | 2376401
TAB-TBK5-MASY-02 | 2607OSPFI0000135 | 98.91 | TABUK | FTTH | Fiber | 3 - Implementation | 310878 | 310878 | 2026-01-07 12:24 |  | 2026-01-07 12:24 | 2026 | 2026-03-15 |  | 2026-03-03 22:05 | 11 | 0 | 0 | 0 | 0 | 200 | 200 |  | 20962 | 20962 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002384 | OSPWO0027073 | RITM0086548 |  | 4732401
TAB-TBK5-MASY-04 | 2607OSPFI0000137 | 98.75 | TABUK | FTTH | Fiber | 3 - Implementation | 273659 | 273659 | 2026-01-07 12:24 |  | 2026-01-07 12:24 | 2026 | 2026-03-17 |  | 2026-03-03 22:06 | 11 | 0 | 0 | 0 | 0 | 171 | 171 |  | 15881 | 15881 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002386 | OSPWO0027077 | RITM0086552 |  | 4732401
TAB-TBK5-MASY-03 | 2607OSPFI0000136 | 91.35 | TABUK | FTTH | Fiber | 3 - Implementation | 313953 | 313953 | 2026-01-07 12:24 |  | 2026-01-07 12:24 | 2026 | 2026-03-28 |  | 2026-03-25 11:27 | 13 | 0 | 0 | 0 | 0 | 205 | 205 |  | 18000 | 19466 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 22 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002385 | OSPWO0027075 | RITM0086550 |  | 4732401 |  | 2,026
JED-HRR2-SALH-03 | 2502OSPFI0002424 | 89.28 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 212835 | 212835 | 2025-08-12 13:25 | 2025-08-12 13:25 | 2025-08-12 22:54 | 2025 | 2025-12-21 |  | 2026-03-01 12:48 | 17 | 0 | 0 | 0 | 0 | 155 | 342 |  | 20832 | 23200 | 156 | 155 | 0 | 155 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002479 | OSPWO0021616 | RITM0070552 |  | 2376401 | 17/02/2026 13:59:11 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-16 | 2502OSPCI0002834 | 83.57 | MAKKAH | FTTH | Civil | 3 - Implementation | 937327.4 | 937327 | 2025-10-06 10:30 | 2025-10-06 10:30 | 2025-10-06 10:30 | 2025 | 2026-02-26 |  | 2026-03-25 11:24 | 17 | 5800 | 6938 | 10 | 14 | 137 | 159 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002460 | OSPWO0023579 | RITM0074746 |  | 2376401
JED-HRR2-SALH-17 | 2502OSPCI0002832 | 79.34 | MAKKAH | FTTH | Civil | 3 - Implementation | 904261.8 | 904262 | 2025-10-06 10:24 | 2025-10-06 10:24 | 2025-10-06 10:25 | 2025 | 2026-02-27 |  | 2026-03-25 11:25 | 18 | 5200 | 6552 | 10 | 15 | 161 | 142 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002461 | OSPWO0023571 | RITM0074742 |  | 2376401
JED-HRR2-SALH-14 | 2502OSPCI0003326 | 73.63 | MAKKAH | FTTH | Civil | 3 - Implementation | 938610 | 938610 | 2025-12-31 16:10 | 2025-12-31 16:10 | 2025-12-31 16:11 | 2025 | 2026-06-30 |  | 2026-03-25 11:25 | 14 | 4950 | 6724 | 12 | 15 | 164 | 357 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002458 | OSPWO0026485 | RITM0082468 |  | 2376401
JED-HRR2-SALH-11 | 2502OSPFI0002965 | 66.95 | MAKKAH | FTTH | Fiber | 3 - Implementation | 230941.2 | 230941 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025 | 2026-02-28 |  | 2026-03-25 11:26 | 16 | 0 | 0 | 0 | 0 | 170 | 139 |  | 14000 | 20909 | 120 | 170 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000018 | OSPWO0024251 | RITM0076722 |  | 2376401
JED-HRR2-SALH-F2 | 2502OSPFI0002427 | 57.09 | MAKKAH | FTTH | Fiber | 3 - Implementation | 1185423 | 1185423 | 2025-08-12 13:31 | 2025-08-12 13:31 | 2025-08-12 22:54 | 2025 | 2025-12-15 |  | 2026-03-09 17:16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20500 | 35906 | 0 | 0 | 2 | 4 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000021 | OSPWO0021626 | RITM0070555 |  | 2376401
EDA-AYBN-EDAB-01 | 2510OSPCI0002891 | 8.93 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 4861289.9 | 4985409.8 | 2025-10-27 08:38 | 2025-10-27 08:38 | 2025-10-27 08:39 | 2025 | 2026-10-31 |  | 2026-03-03 23:40 | 30 | 3350 | 37467 | 10 | 170 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 40 | 4 | 10 | 2 | 0 | 0 | 0 | 0 |  | OSPWO0023902 | RITM0076015 |  | 8574601 | 27/01/2026 14:22:25 - Husam Jari (Notes) Proposed Target is Rejected. Revise the Date with PM 01/12/2025 10:04:35 - Husam Jari (Notes) completion Target Date is rejected
DAI-ADAR-DAIR-01 | 2510OSPCI0003072 | 5.29 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 6679307 | 6679307 | 2025-11-16 10:38 |  | 2025-11-16 10:38 | 2025 | 2026-09-30 |  | 2026-03-03 23:41 | 19 | 2640 | 49908 | 9 | 202 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 60 | 3 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024839 | RITM0077587 |  | 8386301
DAI-ADAR-DAIR-01 | 2510OSPFI0003092 | 4.13 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 1126800 | 1126800 | 2025-11-16 10:38 |  | 2025-11-16 10:38 | 2025 | 2026-09-30 |  | 2026-03-03 23:42 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2200 | 53278 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 161 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024841 | RITM0077588 |  | 8386301
JED-HRR2-RIYA-53 | 2502OSPCA0002838 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:47 |  |  | 2025 |  |  | 2025-11-05 10:49 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002997 | OSPWO0024441
TAI-MELI-FIYS-02 | 2602OSPCA0000105 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:43 |  |  | 2026 |  |  | 2026-01-06 14:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000105 | OSPWO0026976
SAM-SMTH-MASO-01 | 2510OSPCA0002916 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:40 |  |  | 2025 |  |  | 2025-11-16 10:41 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003075 | OSPWO0024852
JED-HRR2-WAFA-05 | 2602OSPFI0000682 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:00 | 2026-03-26 11:00 | 2026-03-26 11:01 | 2026 |  |  | 2026-03-26 11:01 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000678 | OSPWO0034791 | RITM0095072 |  | 2378601
JED-HRR2-RIYA-35 | 2502OSPFA0002975 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:38 |  |  | 2025 |  |  | 2025-11-05 10:39 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002997 | OSPWO0024387
JED-HRR2-RIYA-24 | 2502OSPCA0002818 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:33 |  |  | 2025 |  |  | 2025-11-05 10:34 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002977 | OSPWO0024361
TAI-QRAU-SABA-05 | 2602OSPFI0000626 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 193465 | 193465 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026 |  |  | 2026-03-16 01:35 | 1 | 0 | 0 | 0 | 0 | 119 | 551 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002391 | OSPWO0034519 | RITM0094609 |  | 2651701
TAI-MELI-FIYS-01 | 2602OSPFI0000446 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026-01-28 15:08 | 2026 |  |  | 2026-01-28 15:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028764 | RITM0088963 |  | 2652602 |  | To close the pending held orders in the mentioned cluster
TAI-QRAU-MUAS-01 | 2602OSPCA0000112 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:52 |  |  | 2026 |  |  | 2026-01-06 14:53 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000112 | OSPWO0027018
JED-FRDS-MANA-17 | 2602OSPCA0000117 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:56 |  |  | 2026 |  |  | 2026-01-06 14:57 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000117 | OSPWO0027038
SAM-SMTH-AMUD-01 | 2510OSPFA0003074 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:41 |  |  | 2025 |  |  | 2025-11-16 10:42 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003096 | OSPWO0024858
JED-HRR2-WAFA-87 | 2602OSPCA0000466 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:12 |  |  | 2026 |  |  | 2026-02-16 12:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000466 | OSPWO0032377
BAH-BCPS-RADW-01 | 2612OSPCA0000220 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:26 |  |  | 2026 |  |  | 2026-01-14 14:27 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000220 | OSPWO0027726
SAM-SMTH-AMUD-01 | 2510OSPCA0002917 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:40 |  |  | 2025 |  |  | 2025-11-16 10:42 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003076 | OSPWO0024856
JED-HRR2-RIYA-23 | 2602OSPCI0000399 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:21 |  | 2026-01-28 14:21 | 2026 |  |  | 2026-01-28 14:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028526 | RITM0088840 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-11 | 2602OSPFA0000441 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:06 |  |  | 2026 |  |  | 2026-03-07 23:38 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000441 | OSPWO0028755
TAI-QRAU-MUAS-01 | 2602OSPCI0000112 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:52 |  | 2026-01-06 14:52 | 2026 |  |  | 2026-01-06 14:52 | 1 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027017 | RITM0086064 |  | 2652202
SAM-SMTH-TURS-01 | 2510OSPCA0002915 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:39 |  |  | 2025 |  |  | 2025-11-16 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003074 | OSPWO0024848
BAH-BCPS-ADEL-01 | 2612OSPFI0000245 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 202846 | 202846 | 2026-01-14 14:24 |  | 2026-01-14 14:24 | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027715 | RITM0087560 |  | 6558501
JED-HRR2-RIYA-29 | 2502OSPCA0002822 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:36 |  |  | 2025 |  |  | 2025-11-05 10:37 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002981 | OSPWO0024377
JED-HRR2-RIYA-55 | 2502OSPCA0002840 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:48 |  |  | 2025 |  |  | 2025-11-05 10:50 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002999 | OSPWO0024449
JED-HRR2-WAFA-06 | 2602OSPFI0000652 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:30 | 2026-03-17 11:30 | 2026-03-17 11:31 | 2026 |  |  | 2026-03-17 11:31 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000679 | OSPWO0034626 | RITM0094721 |  | 2378601
JED-FRDS-BUHA-26 | 2502OSPCA0003077 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:11 |  |  | 2025 |  |  | 2025-12-16 13:12 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003236 | OSPWO0025998
JED-HRR2-WAFA-14 | 2602OSPFI0000653 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:33 | 2026-03-17 11:33 | 2026-03-17 11:34 | 2026 |  |  | 2026-03-17 11:34 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000687 | OSPWO0034630 | RITM0094722 |  | 2378601
JED-HRR2-RIYA-44 | 2502OSPFA0002983 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:43 |  |  | 2025 |  |  | 2025-11-05 10:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003005 | OSPWO0024419
TAI-QRAU-SABA-02 | 2602OSPFI0000623 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 262287 | 262287 | 2026-03-16 01:29 | 2026-03-16 01:29 | 2026-03-16 01:29 | 2026 |  |  | 2026-03-16 01:29 | 1 | 0 | 0 | 0 | 0 | 171 | 614 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002388 | OSPWO0034507 | RITM0094603 |  | 2651701
JED-HRR2-WAFA-85 | 2602OSPFI0000513 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:10 |  | 2026-02-16 12:10 | 2026 |  |  | 2026-03-01 15:39 | 2 | 0 | 0 | 0 | 0 | 32 | 59 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000619 | OSPWO0032370 | RITM0091401 |  | 2378501
JED-HRR2-WAFA-19 | 2602OSPCI0000639 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:27 | 2026-03-26 11:27 | 2026-03-26 11:28 | 2026 |  |  | 2026-03-26 11:28 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000667 | OSPWO0034825 | RITM0095089 |  | 2378601
JED-HRR2-WAFA-27 | 2602OSPCI0000644 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026 |  |  | 2026-03-26 11:44 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000675 | OSPWO0034845 | RITM0095100 |  | 2378601
BAH-BCPS-NAIM-01 | 2612OSPFA0000250 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:29 |  |  | 2026 |  |  | 2026-01-14 14:30 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000250 | OSPWO0027738
JED-HRR2-WAFA-07 | 2602OSPFI0000683 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:04 | 2026-03-26 11:04 | 2026-03-26 11:04 | 2026 |  |  | 2026-03-26 11:04 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000680 | OSPWO0034795 | RITM0095074 |  | 2378601
JED-FRDS-BUHA-25 | 2502OSPCA0003076 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:10 |  |  | 2025 |  |  | 2025-12-16 13:11 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003235 | OSPWO0025994
JED-FRDS-MANA-09 | 2502OSPCA0002809 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:14 |  |  | 2025 |  |  | 2025-11-05 10:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002968 | OSPWO0024325
JED-FRDS-MANA-09 | 2502OSPFA0002960 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:14 |  |  | 2025 |  |  | 2025-11-05 10:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002982 | OSPWO0024327
JED-HRR2-RIYA-24 | 2502OSPFA0002969 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:33 |  |  | 2025 |  |  | 2025-11-05 10:35 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002991 | OSPWO0024363
JED-HRR2-WAFA-98 | 2602OSPCI0000472 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:20 |  | 2026-02-16 12:20 | 2026 |  |  | 2026-02-16 12:20 | 1 | 0 | 0 | 0 | 0 |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000608 | OSPWO0032400 | RITM0091416 |  | 2378501
JED-HRR2-WAFA-24 | 2602OSPCI0000642 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:35 | 2026-03-26 11:35 | 2026-03-26 11:36 | 2026 |  |  | 2026-03-26 11:36 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000672 | OSPWO0034837 | RITM0095095 |  | 2378601
SAM-SMTH-MAJA-01 | 2510OSPFA0003075 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:41 |  |  | 2025 |  |  | 2025-11-16 10:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003097 | OSPWO0024862
JED-HRR2-RIYA-55 | 2502OSPFA0002991 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:49 |  |  | 2025 |  |  | 2025-11-05 10:50 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003013 | OSPWO0024451
JED-HRR2-WAFA-28 | 2602OSPCI0000645 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:49 | 2026-03-26 11:49 | 2026-03-26 11:50 | 2026 |  |  | 2026-03-26 11:50 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000676 | OSPWO0034849 | RITM0095102 |  | 2378601
JED-HRR2-WAFA-101 | 2602OSPFI0000508 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:14 | 2026-02-15 22:14 | 2026-02-15 22:14 | 2026 |  |  | 2026-03-01 15:44 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000635 | OSPWO0032350 | RITM0091370 |  | 2378501
TAI-QAIM-HASH-F4 | 2602OSPCA0000108 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:46 |  |  | 2026 |  |  | 2026-01-06 14:46 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000108 | OSPWO0026988
TAI-MELI-JUBR-10 | 2602OSPCI0000352 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:03 |  | 2026-01-28 14:03 | 2026 |  |  | 2026-01-28 14:03 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028432 | RITM0088789 |  | 2652504 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-99 | 2602OSPFA0000522 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:22 |  |  | 2026 |  |  | 2026-02-16 12:22 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000522 | OSPWO0032407
JED-HRR2-WAFA-57 | 2602OSPCI0000650 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026 |  |  | 2026-03-26 12:33 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000705 | OSPWO0034869 | RITM0095113 |  | 2378601
JED-HRR2-WAFA-89 | 2602OSPFI0000517 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:16 |  | 2026-02-16 12:16 | 2026 |  |  | 2026-02-16 12:16 | 1 | 0 | 0 | 0 | 0 | 23 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000623 | OSPWO0032386 | RITM0091409 |  | 2378501
JED-HRR2-WAFA-91 | 2602OSPFI0000519 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:18 |  | 2026-02-16 12:18 | 2026 |  |  | 2026-02-16 12:18 | 1 | 0 | 0 | 0 | 0 | 21 | 65 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000625 | OSPWO0032394 | RITM0091413 |  | 2378501
JED-HRR2-RIYA-47 | 2502OSPFA0002986 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:45 |  |  | 2025 |  |  | 2025-11-05 10:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003008 | OSPWO0024431
JED-HRR2-WAFA-79 | 2602OSPFI0000510 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:18 | 2026-02-15 22:18 | 2026-02-15 22:18 | 2026 |  |  | 2026-03-01 15:42 | 2 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000613 | OSPWO0032358 | RITM0091374 |  | 2378501
JED-HRR2-RIYA-64 | 2602OSPCA0000332 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 13:54 |  |  | 2026 |  |  | 2026-01-28 13:55 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000332 | OSPWO0028393
BAH-BCPS-SARA-01 | 2612OSPFI0000244 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 470440 | 470440 | 2026-01-14 14:24 |  | 2026-01-14 14:24 | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027713 | RITM0087559 |  | 6558101
BAH-BCPS-ADEL-01 | 2612OSPCA0000218 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:24 |  |  | 2026 |  |  | 2026-01-14 14:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000218 | OSPWO0027718
| 2602OSPOF0000021 | 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-03-08 10:30 | 2026-03-08 10:30 | 2026-03-08 10:30 | 2026 |  |  | 2026-03-08 10:30 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034192 | RITM0094080 |  | 2241601
JED-HRR2-RIYA-37 | 2502OSPFA0002977 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:39 |  |  | 2025 |  |  | 2025-11-05 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002999 | OSPWO0024395
JED-HRR2-RIYA-64 | 2602OSPFA0000382 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:43 |  |  | 2026 |  |  | 2026-01-28 14:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000382 | OSPWO0028637
JED-HRR2-RIYA-70 | 2602OSPCI0000390 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:17 |  | 2026-01-28 14:17 | 2026 |  |  | 2026-01-28 14:17 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028508 | RITM0088831 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-GHAD-01 | 2612OSPFA0000247 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:26 |  |  | 2026 |  |  | 2026-01-14 14:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000247 | OSPWO0027724
BAH-BCPS-AREE-01 | 2612OSPCI0000221 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 531632 | 531632 | 2026-01-14 14:27 |  | 2026-01-14 14:27 | 2026 |  |  | 2026-01-14 14:27 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027727 | RITM0087567 |  | 6574301
BAH-BCPS-BADR-01 | 2612OSPCI0000224 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1295656 | 1295656 | 2026-01-14 14:30 |  | 2026-01-14 14:30 | 2026 |  |  | 2026-01-14 14:30 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027741 | RITM0087574 |  | 6574901
JED-HRR2-RIYA-70 | 2602OSPCA0000390 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:17 |  |  | 2026 |  |  | 2026-01-28 14:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000390 | OSPWO0028509
JED-HRR2-WAFA-90 | 2602OSPCI0000469 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:16 |  | 2026-02-16 12:16 | 2026 |  |  | 2026-02-16 12:16 | 1 | 0 | 0 | 0 | 0 |  |  | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000600 | OSPWO0032388 | RITM0091410 |  | 2378501
TAI-QRAU-SABA-02 | 2602OSPCI0000570 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1280045 | 1280045 | 2026-03-16 01:28 | 2026-03-16 01:28 | 2026-03-16 01:29 | 2026 |  |  | 2026-03-16 01:29 | 1 | 0 | 0 | 0 | 0 |  |  | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002374 | OSPWO0034505 | RITM0094604 |  | 2651701
JED-HRR2-WAFA-84 | 2602OSPCI0000463 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:08 |  | 2026-02-16 12:08 | 2026 |  |  | 2026-03-01 15:40 | 2 | 0 | 0 | 0 | 0 |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000594 | OSPWO0032364 | RITM0091398 |  | 2378501
JED-HRR2-RIYA-23 | 2602OSPFI0000449 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:10 |  | 2026-01-28 15:10 | 2026 |  |  | 2026-01-28 15:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028770 | RITM0088966 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
| 2602OSPOF0000022 | 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-03-08 10:35 | 2026-03-08 10:35 | 2026-03-08 10:36 | 2026 |  |  | 2026-03-08 10:36 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034193 | RITM0094081 |  | 2374501
JED-HRR2-WAFA-10 | 2602OSPFI0000685 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:09 | 2026-03-26 11:09 | 2026-03-26 11:09 | 2026 |  |  | 2026-03-26 11:09 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000683 | OSPWO0034803 | RITM0095077 |  | 2378601
TAI-MELI-JUBR-10 | 2602OSPFI0000402 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:51 |  | 2026-01-28 14:51 | 2026 |  |  | 2026-01-28 14:51 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028676 | RITM0088916 |  | 2652504 |  | To close the pending held orders in the mentioned cluster
TAB-TBK5-MASY-F1 | 2607OSPFA0000138 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  |  | 2026 |  |  | 2026-01-07 12:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000138 | OSPWO0027080
JED-HRR2-WAFA-85 | 2602OSPCI0000464 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:10 |  | 2026-02-16 12:10 | 2026 |  |  | 2026-03-01 15:39 | 2 | 0 | 0 | 0 | 0 |  |  | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000595 | OSPWO0032368 | RITM0091400 |  | 2378501
JED-HRR2-WAFA-85 | 2602OSPCA0000464 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:10 |  |  | 2026 |  |  | 2026-02-16 12:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000464 | OSPWO0032369
JED-HRR2-RIYA-38 | 2502OSPCI0002986 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 932366 | 932366 | 2025-11-05 10:39 |  | 2025-11-05 10:39 | 2025 |  |  | 2025-11-10 17:50 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000693 | OSPWO0024396 | RITM0076815 |  | 2387401
JED-HRR2-WAFA-16 | 2602OSPCI0000636 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:19 | 2026-03-26 11:19 | 2026-03-26 11:20 | 2026 |  |  | 2026-03-26 11:20 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000664 | OSPWO0034813 | RITM0095083 |  | 2378601
JED-HRR2-WAFA-173 | 2602OSPFI0000648 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:11 | 2026-03-17 11:11 | 2026-03-17 11:12 | 2026 |  |  | 2026-03-17 11:12 | 1 | 0 | 0 | 0 | 0 | 125 | 125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0001013 | OSPWO0034608 | RITM0094713 |  | 2378501
JED-HRR2-RIYA-64 | 2602OSPFI0000382 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:43 |  | 2026-01-28 14:43 | 2026 |  |  | 2026-01-28 14:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028636 | RITM0088896 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-145 | 2602OSPFI0000647 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:09 | 2026-03-17 11:09 | 2026-03-17 11:09 | 2026 |  |  | 2026-03-17 11:09 | 1 | 0 | 0 | 0 | 0 | 4 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000985 | OSPWO0034604 | RITM0094711 |  | 2378501
JED-HRR2-WAFA-160 | 2602OSPFI0000645 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:04 | 2026-03-17 11:04 | 2026-03-17 11:04 | 2026 |  |  | 2026-03-17 11:04 | 1 | 0 | 0 | 0 | 0 | 9 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034596 | RITM0094707 |  | 2378501
JED-HRR2-WAFA-22 | 2602OSPCI0000602 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:35 | 2026-03-17 11:35 | 2026-03-17 11:36 | 2026 |  |  | 2026-03-17 11:36 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000670 | OSPWO0034632 | RITM0094725 |  | 2378601
JED-FRDS-BUHA-24 | 2502OSPCA0003075 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:09 |  |  | 2025 |  |  | 2025-12-16 13:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003234 | OSPWO0025990
JED-HRR2-WAFA-57 | 2602OSPFI0000701 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026 |  |  | 2026-03-26 12:33 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000730 | OSPWO0034871 | RITM0095114 |  | 2378601
JED-HRR2-WAFA-15 | 2602OSPCI0000635 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:16 | 2026-03-26 11:16 | 2026-03-26 11:17 | 2026 |  |  | 2026-03-26 11:17 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000663 | OSPWO0034809 | RITM0095081 |  | 2378601
BAH-BCPS-RADW-01 | 2612OSPFA0000246 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:25 |  |  | 2026 |  |  | 2026-01-14 14:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000246 | OSPWO0027720
JED-HRR2-RIYA-56 | 2602OSPCA0000395 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  |  | 2026 |  |  | 2026-01-28 14:20 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000395 | OSPWO0028519
JED-FRDS-MANA-07 | 2502OSPFA0002958 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:13 |  |  | 2025 |  |  | 2025-11-05 10:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002980 | OSPWO0024319
JED-HRR2-WAFA-16 | 2602OSPOI0000001 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:19 | 2026-03-26 11:19 | 2026-03-26 11:20 | 2026 |  |  | 2026-03-26 11:20 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000689 | OSPWO0034815 | RITM0095084 |  | 2378601
JED-HRR2-WAFA-84 | 2602OSPFI0000512 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:09 |  | 2026-02-16 12:09 | 2026 |  |  | 2026-03-01 15:40 | 2 | 0 | 0 | 0 | 0 | 14 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000618 | OSPWO0032366 | RITM0091399 |  | 2378501
TAB-TBK5-MASY-03 | 2607OSPFA0000136 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  |  | 2026 |  |  | 2026-01-07 12:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000136 | OSPWO0027076
JED-HRR2-RIYA-57 | 2602OSPCA0000118 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:57 |  |  | 2026 |  |  | 2026-01-06 14:58 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000118 | OSPWO0027042
JUB-DHAH-AZIZ-16 | 2605OSPFI0000020 | 0 | EASTERN REGION | FTTH | Fiber | 1 - PIP Submission | 66919 | 66919 | 2026-01-04 09:15 | 2026-01-04 09:15 | 2026-01-04 09:16 | 2026 |  |  | 2026-01-04 09:16 | 2 | 0 | 0 | 0 | 0 | 18 | 57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-04 09:16 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026613 | RITM0084725 |  | 3541601
JED-FRDS-MANA-21 | 2502OSPCA0002815 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:18 |  |  | 2025 |  |  | 2025-11-05 10:20 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002974 | OSPWO0024349
BAH-BCPS-MASA-01 | 2612OSPCI0000216 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2295598 | 2295598 | 2026-01-14 14:22 |  | 2026-01-14 14:22 | 2026 |  |  | 2026-01-14 14:22 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027707 | RITM0087556 |  | 6557601
JED-HRR2-RIYA-47 | 2502OSPCA0002835 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:45 |  |  | 2025 |  |  | 2025-11-05 10:46 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002994 | OSPWO0024429
| 2502OSPOF0000415 | 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2025-12-16 19:31 | 2025-12-16 19:31 | 2025-12-16 19:31 | 2025 |  |  | 2025-12-16 19:31 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026041 | RITM0079749 |  | 2241301
TAI-MELI-FIYS-01 | 2602OSPFA0000106 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:42 |  |  | 2026 |  |  | 2026-01-06 14:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000106 | OSPWO0026974
JED-HRR2-RIYA-42 | 2502OSPFA0002981 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:42 |  |  | 2025 |  |  | 2025-11-05 10:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003003 | OSPWO0024411
JED-HRR2-RIYA-23 | 2602OSPCI0000234 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 870180 | 870180 | 2026-01-15 16:24 |  | 2026-01-15 16:24 | 2026 |  |  | 2026-01-26 08:53 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-26 08:53 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000762 | OSPWO0027799 | RITM0087655 |  | 2387401
TAI-QAIM-HASH-08 | 2602OSPFA0000108 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:44 |  |  | 2026 |  |  | 2026-01-06 14:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000108 | OSPWO0026982
BAH-BCPS-BADR-01 | 2612OSPCA0000224 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:30 |  |  | 2026 |  |  | 2026-01-14 14:30 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000224 | OSPWO0027742
JED-HRR2-WAFA-17 | 2602OSPCI0000637 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:21 | 2026-03-26 11:21 | 2026-03-26 11:22 | 2026 |  |  | 2026-03-26 11:22 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000665 | OSPWO0034817 | RITM0095085 |  | 2378601
BAH-BCPS-NAIM-01 | 2612OSPCA0000223 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:28 |  |  | 2026 |  |  | 2026-01-14 14:29 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000223 | OSPWO0027736
JED-HRR2-FURO-29 | 2602OSPCI0000458 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:10 | 2026-02-15 22:10 | 2026-02-15 22:11 | 2026 |  |  | 2026-03-01 15:46 | 2 | 0 | 0 | 0 | 0 |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000585 | OSPWO0032344 | RITM0091368 |  | 2378501
TAI-QAIM-QIAA-08 | 2602OSPFI0000442 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:07 |  | 2026-01-28 15:07 | 2026 |  |  | 2026-01-28 15:07 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028756 | RITM0088959 |  | 2656301 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-RADW-01 | 2612OSPCI0000220 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1483547 | 1483547 | 2026-01-14 14:26 |  | 2026-01-14 14:26 | 2026 |  |  | 2026-01-14 14:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027725 | RITM0087566 |  | 6574301
JED-FRDS-BUHA-23 | 2502OSPFA0003242 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:09 |  |  | 2025 |  |  | 2025-12-16 13:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003264 | OSPWO0025988
JED-HRR2-WAFA-51 | 2602OSPCI0000648 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:28 | 2026-03-26 12:28 | 2026-03-26 12:28 | 2026 |  |  | 2026-03-26 12:28 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000699 | OSPWO0034861 | RITM0095109 |  | 2378601
JED-HRR2-WAFA-19 | 2602OSPFI0000690 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:28 | 2026-03-26 11:28 | 2026-03-26 11:28 | 2026 |  |  | 2026-03-26 11:28 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000692 | OSPWO0034827 | RITM0095090 |  | 2378601
JED-HRR2-SALH-08 | 2602OSPFI0000447 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:09 |  | 2026-01-28 15:09 | 2026 |  |  | 2026-01-28 15:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028766 | RITM0088964 |  | 2376401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-80 | 2602OSPCI0000462 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:07 |  | 2026-02-16 12:07 | 2026 |  |  | 2026-02-16 12:07 | 1 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000614 | OSPWO0032360 | RITM0091396 |  | 2378501
JED-HRR2-WAFA-80 | 2602OSPCA0000462 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:07 |  |  | 2026 |  |  | 2026-02-16 12:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000462 | OSPWO0032361
JED-FRDS-MANA-08 | 2502OSPCA0002808 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:13 |  |  | 2025 |  |  | 2025-11-05 10:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002967 | OSPWO0024321
JED-FRDS-MANA-16 | 2502OSPFA0002962 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:16 |  |  | 2025 |  |  | 2025-11-05 10:17 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002984 | OSPWO0024335
JED-HRR2-RIYA-41 | 2602OSPCI0000398 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:21 |  | 2026-01-28 14:21 | 2026 |  |  | 2026-01-28 14:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028524 | RITM0088839 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-42 | 2602OSPCI0000647 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:25 | 2026-03-26 12:25 | 2026-03-26 12:26 | 2026 |  |  | 2026-03-26 12:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000690 | OSPWO0034857 | RITM0095107 |  | 2378601
JED-HRR2-WAFA-18 | 2602OSPFI0000689 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:25 | 2026-03-26 11:25 | 2026-03-26 11:25 | 2026 |  |  | 2026-03-26 11:25 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000691 | OSPWO0034823 | RITM0095087 |  | 2378601
JED-FRDS-MANA-18 | 2502OSPFA0002963 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:17 |  |  | 2025 |  |  | 2025-11-05 10:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002985 | OSPWO0024339
BAH-BCPS-AREE-01 | 2612OSPFA0000249 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:28 |  |  | 2026 |  |  | 2026-01-14 14:28 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000249 | OSPWO0027732
JED-FRDS-AMWA-11 | 2602OSPFI0000704 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 79735 | 79735 | 2026-03-28 21:53 | 2026-03-28 21:53 | 2026-03-28 21:54 | 2026 |  |  | 2026-03-28 21:54 | 1 | 0 | 0 | 0 | 0 | 33 | 104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001046 | OSPWO0034884 | RITM0095199 |  | 2381401
TAI-QAIM-QIAA-F2 | 2602OSPFA0000113 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:49 |  |  | 2026 |  |  | 2026-01-06 14:49 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000113 | OSPWO0027002
TAI-MELI-JALL-01 | 2602OSPCI0000606 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:44 | 2026-03-17 11:44 | 2026-03-17 11:45 | 2026 |  |  | 2026-03-17 11:45 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034648 | RITM0094733 |  | 2652306
JED-HRR2-WAFA-87 | 2602OSPCI0000466 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:12 |  | 2026-02-16 12:12 | 2026 |  |  | 2026-03-01 15:47 | 2 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000597 | OSPWO0032376 | RITM0091404 |  | 2378501
TAB-TBK5-MASY-04 | 2607OSPFA0000137 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  |  | 2026 |  |  | 2026-01-07 12:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000137 | OSPWO0027078
JED-FRDS-MANA-21 | 2502OSPFA0002966 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:19 |  |  | 2025 |  |  | 2025-11-05 10:20 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002988 | OSPWO0024351
JED-FRDS-MANA-22 | 2502OSPCA0002816 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:19 |  |  | 2025 |  |  | 2025-11-05 10:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002975 | OSPWO0024353
JED-FRDS-BUHA-23 | 2502OSPFI0003264 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 98385 | 98385 | 2025-12-16 13:09 |  | 2025-12-16 13:09 | 2025 |  |  | 2025-12-16 13:09 | 1 | 0 | 0 | 0 | 0 | 48 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002800 | OSPWO0025987 | RITM0079691 |  | 2382301
JED-HRR2-WAFA-170 | 2602OSPFI0000651 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:27 | 2026-03-17 11:27 | 2026-03-17 11:27 | 2026 |  |  | 2026-03-17 11:27 | 1 | 0 | 0 | 0 | 0 | 21 | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0001010 | OSPWO0034622 | RITM0094719 |  | 2378501
SAM-SMTH-TURS-01 | 2510OSPFA0003072 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:39 |  |  | 2025 |  |  | 2025-11-16 10:41 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003094 | OSPWO0024850
JED-HRR2-RIYA-27 | 2502OSPCA0002821 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:35 |  |  | 2025 |  |  | 2025-11-05 10:37 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002980 | OSPWO0024373
JED-HRR2-RIYA-43 | 2502OSPFA0002982 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:42 |  |  | 2025 |  |  | 2025-11-05 10:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003004 | OSPWO0024415
JED-HRR2-WAFA-11 | 2602OSPCI0000604 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:39 | 2026-03-17 11:39 | 2026-03-17 11:40 | 2026 |  |  | 2026-03-17 11:40 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000659 | OSPWO0034640 | RITM0094729 |  | 2378601
JED-HRR2-WAFA-137 | 2602OSPFI0000509 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:16 | 2026-02-15 22:16 | 2026-02-15 22:16 | 2026 |  |  | 2026-03-01 15:43 | 2 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000647 | OSPWO0032354 | RITM0091372 |  | 2378501
JED-HRR2-WAFA-05 | 2602OSPCI0000630 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:00 | 2026-03-26 11:00 | 2026-03-26 11:00 | 2026 |  |  | 2026-03-26 11:00 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000653 | OSPWO0034789 | RITM0095071 |  | 2378601
JED-HRR2-RIYA-36 | 2502OSPCA0002825 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:38 |  |  | 2025 |  |  | 2025-11-05 10:39 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002984 | OSPWO0024389
JED-HRR2-RIYA-56 | 2602OSPFI0000445 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026-01-28 15:08 | 2026 |  |  | 2026-01-28 15:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028762 | RITM0088962 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-78 | 2602OSPFI0000702 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026 |  |  | 2026-03-26 12:35 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000751 | OSPWO0034875 | RITM0095116 |  | 2378601
JED-FRDS-BUHA-29 | 2502OSPFA0003248 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:14 |  |  | 2025 |  |  | 2025-12-16 13:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003270 | OSPWO0026012
TAI-QAIM-QIAA-08 | 2602OSPCA0000392 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:18 |  |  | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000392 | OSPWO0028513
JED-HRR2-WAFA-86 | 2602OSPCA0000465 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:11 |  |  | 2026 |  |  | 2026-02-16 12:12 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000465 | OSPWO0032373
JED-FRDS-BUHA-23 | 2502OSPCA0003074 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:08 |  |  | 2025 |  |  | 2025-12-16 13:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003233 | OSPWO0025986
TAI-QRAU-MUAS-01 | 2602OSPFI0000121 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:52 |  | 2026-01-06 14:52 | 2026 |  |  | 2026-01-06 14:52 | 1 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027019 | RITM0086065 |  | 2652202
JED-FRDS-BUHA-30 | 2502OSPCA0003081 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:14 |  |  | 2025 |  |  | 2025-12-16 13:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003240 | OSPWO0026014
JED-HRR2-WAFA-92 | 2602OSPFI0000520 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:19 |  | 2026-02-16 12:19 | 2026 |  |  | 2026-02-16 12:19 | 1 | 0 | 0 | 0 | 0 | 11 | 82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000626 | OSPWO0032398 | RITM0091415 |  | 2378501
JED-HRR2-WAFA-91 | 2602OSPCA0000470 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:17 |  |  | 2026 |  |  | 2026-02-16 12:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000470 | OSPWO0032393
JED-HRR2-WAFA-07 | 2602OSPCI0000631 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:03 | 2026-03-26 11:03 | 2026-03-26 11:04 | 2026 |  |  | 2026-03-26 11:04 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000655 | OSPWO0034793 | RITM0095073 |  | 2378601
JED-HRR2-WAFA-137 | 2602OSPCI0000460 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:15 | 2026-02-15 22:15 | 2026-02-15 22:16 | 2026 |  |  | 2026-03-01 15:43 | 2 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000671 | OSPWO0032352 | RITM0091373 |  | 2378501
JED-HRR2-WAFA-92 | 2602OSPCI0000471 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:19 |  | 2026-02-16 12:19 | 2026 |  |  | 2026-02-16 12:19 | 1 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000602 | OSPWO0032396 | RITM0091414 |  | 2378501
TAI-QAIM-QIAA-10 | 2602OSPCI0000393 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026-01-28 14:19 | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028514 | RITM0088834 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-78 | 2602OSPCI0000651 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026 |  |  | 2026-03-26 12:35 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000726 | OSPWO0034873 | RITM0095117 |  | 2378601
TAI-MELI-FIYS-01 | 2602OSPFA0000446 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  |  | 2026 |  |  | 2026-01-28 15:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000446 | OSPWO0028765
SAM-SMTH-KHAD-01 | 2510OSPFA0003071 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:39 |  |  | 2025 |  |  | 2025-11-16 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003093 | OSPWO0024846
JED-FRDS-BUHA-29 | 2502OSPFI0003270 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 102929 | 102929 | 2025-12-16 13:14 |  | 2025-12-16 13:14 | 2025 |  |  | 2025-12-16 13:14 | 1 | 0 | 0 | 0 | 0 | 49 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002806 | OSPWO0026011 | RITM0079703 |  | 2382301
JED-HRR2-RIYA-70 | 2602OSPFA0000440 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:06 |  |  | 2026 |  |  | 2026-01-28 15:07 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000440 | OSPWO0028753
BAH-BCPS-BADR-01 | 2612OSPFA0000251 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:29 |  |  | 2026 |  |  | 2026-01-14 14:30 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000251 | OSPWO0027740
TAI-QRAU-MUAS-01 | 2602OSPFA0000121 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:52 |  |  | 2026 |  |  | 2026-01-06 14:53 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000121 | OSPWO0027020
JED-HRR2-WAFA-89 | 2602OSPCA0000468 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:15 |  |  | 2026 |  |  | 2026-02-16 12:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000468 | OSPWO0032385
BAH-BCPS-NAIM-01 | 2612OSPFI0000250 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 450271 | 450271 | 2026-01-14 14:29 |  | 2026-01-14 14:29 | 2026 |  |  | 2026-01-14 14:29 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027737 | RITM0087572 |  | 6574501
JED-FRDS-BUHA-27 | 2502OSPCA0003078 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:12 |  |  | 2025 |  |  | 2025-12-16 13:12 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003237 | OSPWO0026002
JED-HRR2-WAFA-90 | 2602OSPFI0000518 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:17 |  | 2026-02-16 12:17 | 2026 |  |  | 2026-02-16 12:17 | 1 | 0 | 0 | 0 | 0 | 23 | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000624 | OSPWO0032390 | RITM0091411 |  | 2378501
JED-FRDS-MANA-22 | 2502OSPFA0002967 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:19 |  |  | 2025 |  |  | 2025-11-05 10:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002989 | OSPWO0024355
TAI-QAIM-QIAA-F2 | 2602OSPCA0000111 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:48 |  |  | 2026 |  |  | 2026-01-06 14:49 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000111 | OSPWO0027000
JED-HRR2-RIYA-50 | 2502OSPFA0002987 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:46 |  |  | 2025 |  |  | 2025-11-05 10:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003009 | OSPWO0024435
JED-HRR2-RIYA-F3 | 2502OSPFA0002993 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:50 |  |  | 2025 |  |  | 2025-11-05 10:52 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003015 | OSPWO0024459
JED-HRR2-WAFA-15 | 2602OSPFI0000687 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:17 | 2026-03-26 11:17 | 2026-03-26 11:17 | 2026 |  |  | 2026-03-26 11:17 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000688 | OSPWO0034811 | RITM0095082 |  | 2378601
JED-HRR2-WAFA-99 | 2602OSPCA0000473 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:21 |  |  | 2026 |  |  | 2026-02-16 12:22 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000473 | OSPWO0032405
JED-HRR2-WAFA-54 | 2602OSPFI0000663 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 14:04 | 2026-03-17 14:04 | 2026-03-17 14:05 | 2026 |  |  | 2026-03-17 14:05 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000727 | OSPWO0034670 | RITM0094747 |  | 2378601
JED-HRR2-WAFA-23 | 2602OSPCI0000641 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026 |  |  | 2026-03-26 11:32 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000671 | OSPWO0034833 | RITM0095093 |  | 2378601
JED-HRR2-RIYA-65 | 2502OSPCA0002547 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-09-16 11:47 |  |  | 2025 |  |  | 2025-09-16 11:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002695 | OSPWO0022887
JED-FRDS-MANA-20 | 2502OSPCA0002814 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:18 |  |  | 2025 |  |  | 2025-11-05 10:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002973 | OSPWO0024345
JED-HRR2-WAFA-88 | 2602OSPFI0000516 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:14 |  | 2026-02-16 12:14 | 2026 |  |  | 2026-02-16 12:14 | 1 | 0 | 0 | 0 | 0 | 27 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000622 | OSPWO0032382 | RITM0091407 |  | 2378501
JED-HRR2-WAFA-88 | 2602OSPFA0000516 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:14 |  |  | 2026 |  |  | 2026-02-16 12:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000516 | OSPWO0032383
JED-FRDS-MANA-10 | 2502OSPFA0002961 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:15 |  |  | 2025 |  |  | 2025-11-05 10:17 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002983 | OSPWO0024331
JED-HRR2-WAFA-84 | 2602OSPCA0000463 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:08 |  |  | 2026 |  |  | 2026-02-16 12:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000463 | OSPWO0032365
BAH-BCPS-ADEL-01 | 2612OSPCI0000218 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1241863 | 1241863 | 2026-01-14 14:24 |  | 2026-01-14 14:24 | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027717 | RITM0087562 |  | 6558501
JED-FRDS-MANA-F1 | 2502OSPCA0002817 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:20 |  |  | 2025 |  |  | 2025-11-05 10:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002976 | OSPWO0024357
JED-HRR2-WAFA-141 | 2602OSPFI0000646 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:07 | 2026-03-17 11:07 | 2026-03-17 11:07 | 2026 |  |  | 2026-03-17 11:07 | 1 | 0 | 0 | 0 | 0 | 16 | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000981 | OSPWO0034600 | RITM0094709 |  | 2378501
JED-FRDS-MANA-20 | 2502OSPFA0002965 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:18 |  |  | 2025 |  |  | 2025-11-05 10:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002987 | OSPWO0024347
BAH-BCPS-GHAD-01 | 2612OSPFI0000247 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 62008 | 62008 | 2026-01-14 14:26 |  | 2026-01-14 14:26 | 2026 |  |  | 2026-01-14 14:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027723 | RITM0087565 |  | 6574301
JED-HRR2-RIYA-50 | 2502OSPCA0002836 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:46 |  |  | 2025 |  |  | 2025-11-05 10:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002995 | OSPWO0024433
JED-HRR2-RIYA-F6 | 2502OSPCI0002485 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 0 | 0 | 2025-08-23 21:28 | 2025-08-23 21:28 | 2025-09-04 11:20 | 2025 |  |  | 2026-03-01 12:39 | 3 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001504 | OSPWO0021885 | RITM0072340 |  | 2383801
JED-HRR2-WAFA-80 | 2602OSPFA0000511 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:08 |  |  | 2026 |  |  | 2026-02-16 12:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000511 | OSPWO0032363
JED-FRDS-BUHA-25 | 2502OSPFA0003244 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:10 |  |  | 2025 |  |  | 2025-12-16 13:11 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003266 | OSPWO0025996
JED-HRR2-WAFA-141 | 2602OSPCI0000593 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:06 | 2026-03-17 11:06 | 2026-03-17 11:07 | 2026 |  |  | 2026-03-17 11:07 | 1 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000948 | OSPWO0034598 | RITM0094708 |  | 2378501
TAI-QAIM-QIAA-08 | 2602OSPCA0000109 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:46 |  |  | 2026 |  |  | 2026-01-06 14:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000109 | OSPWO0026992
JED-HRR2-RIYA-65 | 2502OSPFA0002680 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-09-16 11:47 |  |  | 2025 |  |  | 2025-09-16 11:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002703 | OSPWO0022889
JED-FRDS-MANA-05 | 2502OSPCA0002805 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:11 |  |  | 2025 |  |  | 2025-11-05 10:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002964 | OSPWO0024309
JED-HRR2-WAFA-84 | 2602OSPFA0000512 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:09 |  |  | 2026 |  |  | 2026-02-16 12:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000512 | OSPWO0032367
JED-HRR2-RIYA-35 | 2502OSPCA0002824 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:37 |  |  | 2025 |  |  | 2025-11-05 10:39 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002983 | OSPWO0024385
TAI-MELI-JALL-01 | 2602OSPFI0000658 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:45 | 2026-03-17 11:45 | 2026-03-17 11:45 | 2026 |  |  | 2026-03-17 11:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034650 | RITM0094734 |  | 2652306
JED-HRR2-RIYA-26 | 2502OSPCA0002820 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:34 |  |  | 2025 |  |  | 2025-11-05 10:36 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002979 | OSPWO0024369
JED-HRR2-SALH-18 | 2602OSPFA0000143 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-07 15:45 |  |  | 2026 |  |  | 2026-01-07 15:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000143 | OSPWO0027100
JED-HRR2-WAFA-145 | 2602OSPCI0000594 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:08 | 2026-03-17 11:08 | 2026-03-17 11:09 | 2026 |  |  | 2026-03-17 11:09 | 1 | 0 | 0 | 0 | 0 |  |  | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000952 | OSPWO0034602 | RITM0094710 |  | 2378501
TAI-MELI-FIYS-02 | 2602OSPFI0000107 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:43 |  | 2026-01-06 14:43 | 2026 |  |  | 2026-01-06 14:43 | 1 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026977 | RITM0086037 |  | 2652602
JED-FRDS-BUHA-25 | 2502OSPFI0003266 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 138009 | 138009 | 2025-12-16 13:10 |  | 2025-12-16 13:10 | 2025 |  |  | 2025-12-16 13:10 | 1 | 0 | 0 | 0 | 0 | 71 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002802 | OSPWO0025995 | RITM0079695 |  | 2382301
TAB-TBHH-MASY-01 | 2607OSPFA0000134 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  |  | 2026 |  |  | 2026-02-10 15:33 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000134 | OSPWO0027072
JED-HRR2-WAFA-53 | 2602OSPFI0000650 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:22 | 2026-03-17 11:22 | 2026-03-26 10:56 | 2026 |  |  | 2026-03-26 10:56 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000726 | OSPWO0034616 | RITM0095070 |  | 2378601
JED-HRR2-RIYA-41 | 2602OSPFI0000448 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:09 |  | 2026-01-28 15:09 | 2026 |  |  | 2026-01-28 15:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028768 | RITM0088965 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-SARA-01 | 2612OSPCA0000217 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:23 |  |  | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000217 | OSPWO0027712
| 2602OSPOF0000015 | 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-02-11 08:54 | 2026-02-11 08:54 | 2026-02-11 08:54 | 2026 |  |  | 2026-02-11 08:54 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0030093 | RITM0090257 |  | 2427301
JED-HRR2-WAFA-98 | 2602OSPFI0000521 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:20 |  | 2026-02-16 12:20 | 2026 |  |  | 2026-02-16 12:21 | 1 | 0 | 0 | 0 | 0 | 11 | 87 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000632 | OSPWO0032402 | RITM0091417 |  | 2378501
JED-HRR2-WAFA-18 | 2602OSPCI0000638 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:25 | 2026-03-26 11:25 | 2026-03-26 11:26 | 2026 |  |  | 2026-03-26 11:26 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000666 | OSPWO0034821 | RITM0095088 |  | 2378601
JED-HRR2-RIYA-52 | 2502OSPCA0002837 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:46 |  |  | 2025 |  |  | 2025-11-05 10:48 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002996 | OSPWO0024437
BAH-BCPS-RADW-01 | 2612OSPFI0000246 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 227778 | 227778 | 2026-01-14 14:25 |  | 2026-01-14 14:25 | 2026 |  |  | 2026-01-14 14:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027719 | RITM0087563 |  | 6574301
JED-HRR2-RIYA-52 | 2502OSPFA0002988 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:47 |  |  | 2025 |  |  | 2025-11-05 10:48 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003010 | OSPWO0024439
JED-HRR2-RIYA-26 | 2502OSPFA0002971 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:35 |  |  | 2025 |  |  | 2025-11-05 10:36 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002993 | OSPWO0024371
JED-HRR2-WAFA-88 | 2602OSPCA0000467 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:14 |  |  | 2026 |  |  | 2026-02-16 12:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000467 | OSPWO0032381
JED-HRR2-WAFA-53 | 2602OSPCI0000597 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:21 | 2026-03-17 11:21 | 2026-03-17 11:23 | 2026 |  |  | 2026-03-26 10:57 | 2 | 0 | 0 | 0 | 0 |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-26 10:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000726 | OSPWO0034614 | RITM0094716 |  | 2378601
JED-HRR2-WAFA-170 | 2602OSPCI0000599 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:26 | 2026-03-17 11:26 | 2026-03-17 11:27 | 2026 |  |  | 2026-03-17 11:27 | 1 | 0 | 0 | 0 | 0 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000977 | OSPWO0034620 | RITM0094718 |  | 2378501
JED-HRR2-RIYA-42 | 2502OSPCA0002830 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:41 |  |  | 2025 |  |  | 2025-11-05 10:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002989 | OSPWO0024409
TAI-MELI-FIYS-02 | 2602OSPFA0000107 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:43 |  |  | 2026 |  |  | 2026-01-06 14:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000107 | OSPWO0026978
JED-HRR2-SALH-08 | 2602OSPCI0000397 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:20 |  | 2026-01-28 14:20 | 2026 |  |  | 2026-01-28 14:20 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028522 | RITM0088838 |  | 2376401 |  | To close the pending held orders in the mentioned cluster
TAI-MELI-FIYS-02 | 2602OSPCI0000105 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:43 |  | 2026-01-06 14:43 | 2026 |  |  | 2026-01-06 14:43 | 1 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026975 | RITM0086036 |  | 2652602
JED-HRR2-RIYA-53 | 2502OSPFA0002989 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:47 |  |  | 2025 |  |  | 2025-11-05 10:49 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003011 | OSPWO0024443
JED-HRR2-WAFA-160 | 2602OSPCI0000592 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:03 | 2026-03-17 11:03 | 2026-03-17 11:04 | 2026 |  |  | 2026-03-17 11:04 | 1 | 0 | 0 | 0 | 0 |  |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034594 | RITM0094706 |  | 2378501
TAI-QAIM-QIAA-08 | 2602OSPFA0000442 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:07 |  |  | 2026 |  |  | 2026-01-28 15:07 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000442 | OSPWO0028757
JED-FRDS-BUHA-22 | 2502OSPCA0003073 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:07 |  |  | 2025 |  |  | 2025-12-16 13:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003232 | OSPWO0025982
JED-HRR2-SALH-08 | 2602OSPFA0000447 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:09 |  |  | 2026 |  |  | 2026-01-28 15:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000447 | OSPWO0028767
BAH-BCPS-ARIF-01 | 2612OSPFA0000248 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:27 |  |  | 2026 |  |  | 2026-01-14 14:28 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000248 | OSPWO0027730
JED-HRR2-WAFA-79 | 2602OSPCI0000461 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:18 | 2026-02-15 22:18 | 2026-02-15 22:19 | 2026 |  |  | 2026-03-01 15:42 | 2 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000589 | OSPWO0032356 | RITM0091375 |  | 2378501
JED-HRR2-WAFA-14 | 2602OSPCI0000601 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:33 | 2026-03-17 11:33 | 2026-03-17 11:34 | 2026 |  |  | 2026-03-17 11:34 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000662 | OSPWO0034628 | RITM0094723 |  | 2378601
JED-HRR2-RIYA-41 | 2602OSPCA0000398 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:21 |  |  | 2026 |  |  | 2026-01-28 14:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000398 | OSPWO0028525
JED-HRR2-WAFA-20 | 2602OSPCI0000640 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:29 | 2026-03-26 11:29 | 2026-03-26 11:30 | 2026 |  |  | 2026-03-26 11:30 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000668 | OSPWO0034829 | RITM0095091 |  | 2378601
SAM-SMTH-MASO-01 | 2510OSPFA0003073 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:40 |  |  | 2025 |  |  | 2025-11-16 10:41 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003095 | OSPWO0024854
JED-FRDS-MANA-18 | 2502OSPCA0002812 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:16 |  |  | 2025 |  |  | 2025-11-05 10:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002971 | OSPWO0024337
JED-HRR2-WAFA-53 | 2602OSPCI0000598 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:24 | 2026-03-17 11:24 | 2026-03-17 11:24 | 2026 |  |  | 2026-03-17 11:24 | 1 | 0 | 0 | 0 | 0 |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000701 | OSPWO0034618 | RITM0094717 |  | 2378601
TAI-QAIM-QIAA-08 | 2602OSPFA0000111 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:47 |  |  | 2026 |  |  | 2026-01-06 14:48 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000111 | OSPWO0026994
BAH-BCPS-MASA-01 | 2612OSPFA0000243 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:23 |  |  | 2026 |  |  | 2026-01-14 14:23 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000243 | OSPWO0027710
BAH-BCPS-NAIM-01 | 2612OSPCI0000223 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2899644 | 2899644 | 2026-01-14 14:28 |  | 2026-01-14 14:28 | 2026 |  |  | 2026-01-14 14:28 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027735 | RITM0087571 |  | 6574501
JED-HRR2-WAFA-02 | 2602OSPFI0000655 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:38 | 2026-03-17 11:38 | 2026-03-17 11:38 | 2026 |  |  | 2026-03-17 11:38 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000675 | OSPWO0034638 | RITM0094727 |  | 2378601
JED-HRR2-RIYA-57 | 2602OSPFA0000127 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:58 |  |  | 2026 |  |  | 2026-01-06 14:58 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000127 | OSPWO0027044
TAI-QAIM-QIAA-09 | 2602OSPCA0000394 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  |  | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000394 | OSPWO0028517
JED-HRR2-RIYA-54 | 2502OSPCA0002839 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:48 |  |  | 2025 |  |  | 2025-11-05 10:49 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002998 | OSPWO0024445
BAH-BCPS-AREE-01 | 2612OSPFI0000249 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 79479 | 79479 | 2026-01-14 14:28 |  | 2026-01-14 14:28 | 2026 |  |  | 2026-01-14 14:28 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027731 | RITM0087569 |  | 6574301
JED-HRR2-RIYA-56 | 2602OSPFA0000445 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  |  | 2026 |  |  | 2026-01-28 15:09 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000445 | OSPWO0028763
JED-HRR2-WAFA-54 | 2602OSPCI0000611 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 14:03 | 2026-03-17 14:03 | 2026-03-17 14:05 | 2026 |  |  | 2026-03-17 14:05 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000702 | OSPWO0034668 | RITM0094746 |  | 2378601
SHA-ADAR-DAIR-01 | 2510OSPFA0003070 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:38 |  |  | 2025 |  |  | 2025-11-16 10:39 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003092 | OSPWO0024842
JED-FRDS-MANA-17 | 2602OSPFA0000126 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:57 |  |  | 2026 |  |  | 2026-01-06 14:57 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000126 | OSPWO0027040
MAK-WHD2-QASA-15 | 2602OSPCA0000131 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-07 15:46 |  |  | 2026 |  |  | 2026-01-07 17:57 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000131 | OSPWO0027106
TAI-QAIM-HASH-09 | 2602OSPCA0000107 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:45 |  |  | 2026 |  |  | 2026-01-06 14:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000107 | OSPWO0026984
JED-FRDS-MANA-06 | 2502OSPCA0002806 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:12 |  |  | 2025 |  |  | 2025-11-05 10:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002965 | OSPWO0024313
JED-FRDS-MANA-19 | 2502OSPCA0002813 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:17 |  |  | 2025 |  |  | 2025-11-05 10:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002972 | OSPWO0024341
BAH-BCPS-BADR-01 | 2612OSPFI0000251 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 198041 | 198041 | 2026-01-14 14:29 |  | 2026-01-14 14:29 | 2026 |  |  | 2026-01-14 14:29 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027739 | RITM0087573 |  | 6574901
TAI-QRAU-SABA-03 | 2602OSPCI0000571 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 805902 | 805902 | 2026-03-16 01:30 | 2026-03-16 01:30 | 2026-03-16 01:31 | 2026 |  |  | 2026-03-16 01:31 | 1 | 0 | 0 | 0 | 0 |  |  | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002375 | OSPWO0034509 | RITM0094605 |  | 2651701
JED-HRR2-WAFA-98 | 2602OSPCA0000472 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:20 |  |  | 2026 |  |  | 2026-02-16 12:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000472 | OSPWO0032401
SAM-SMTH-MAJA-01 | 2510OSPCA0002918 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:41 |  |  | 2025 |  |  | 2025-11-16 10:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003077 | OSPWO0024860
SAM-SMTH-KHAD-01 | 2510OSPCA0002914 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:38 |  |  | 2025 |  |  | 2025-11-16 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003073 | OSPWO0024844
JED-FRDS-MANA-10 | 2502OSPCA0002810 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:15 |  |  | 2025 |  |  | 2025-11-05 10:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002969 | OSPWO0024329
JED-HRR2-WAFA-22 | 2602OSPFI0000654 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:36 | 2026-03-17 11:36 | 2026-03-17 11:36 | 2026 |  |  | 2026-03-17 11:36 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000695 | OSPWO0034634 | RITM0094726 |  | 2378601
BAH-BCPS-GHAD-01 | 2612OSPCA0000219 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:25 |  |  | 2026 |  |  | 2026-01-14 14:26 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000219 | OSPWO0027722
JED-HRR2-RIYA-27 | 2502OSPFA0002972 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:35 |  |  | 2025 |  |  | 2025-11-05 10:37 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002994 | OSPWO0024375
TAI-QAIM-QIAA-10 | 2602OSPCA0000393 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  |  | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000393 | OSPWO0028515
JED-HRR2-WAFA-89 | 2602OSPFA0000517 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:16 |  |  | 2026 |  |  | 2026-02-16 12:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000517 | OSPWO0032387
| 2502OSPOF0000407 | 0 | MAKKAH | FTTH | Others | 2 - PIP Approval |  |  | 2025-11-16 22:33 | 2025-11-16 22:33 | 2025-11-16 22:33 | 2025 |  | 2026-01-01 | 2026-03-16 13:24 | 5 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0024971 | RITM0077704 |  | 2254201
JED-HRR2-WAFA-87 | 2602OSPFI0000515 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:13 |  | 2026-02-16 12:13 | 2026 |  |  | 2026-02-16 12:13 | 1 | 0 | 0 | 0 | 0 | 37 | 58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000621 | OSPWO0032378 | RITM0091405 |  | 2378501
MAK-WHD2-QASA-15 | 2602OSPCI0000131 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 490966 | 490966 | 2026-01-07 15:46 |  | 2026-01-07 15:46 | 2026 |  |  | 2026-01-07 17:57 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-07 17:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001763 | OSPWO0027105 | RITM0086640 |  | 2457701
TAI-MELI-JUBR-10 | 2602OSPCA0000352 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:03 |  |  | 2026 |  |  | 2026-01-28 14:03 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000352 | OSPWO0028433
JED-HRR2-WAFA-99 | 2602OSPFI0000522 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:22 |  | 2026-02-16 12:22 | 2026 |  |  | 2026-02-16 12:22 | 1 | 0 | 0 | 0 | 0 | 9 | 90 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000633 | OSPWO0032406 | RITM0091419 |  | 2378501
JED-FRDS-BUHA-24 | 2502OSPFI0003265 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 139770 | 139770 | 2025-12-16 13:10 |  | 2025-12-16 13:10 | 2025 |  |  | 2025-12-16 13:10 | 1 | 0 | 0 | 0 | 0 | 71 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002801 | OSPWO0025991 | RITM0079693 |  | 2382301
TAI-QAIM-QIAA-11 | 2602OSPCA0000391 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:18 |  |  | 2026 |  |  | 2026-03-07 23:37 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000391 | OSPWO0028511
TAI-MELI-JUFE-04 | 2602OSPFI0000450 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:10 |  | 2026-01-28 15:10 | 2026 |  |  | 2026-01-28 15:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028772 | RITM0088967 |  | 2652502 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-08 | 2602OSPCI0000392 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:18 |  | 2026-01-28 14:18 | 2026 |  |  | 2026-01-28 14:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028512 | RITM0088833 |  | 2656301 |  | To close the pending held orders in the mentioned cluster
SHA-ADAR-DAIR-01 | 2510OSPCA0002913 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:38 |  |  | 2025 |  |  | 2025-11-16 10:39 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003072 | OSPWO0024840
TAI-MELI-FIYS-01 | 2602OSPCI0000104 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:42 |  | 2026-01-06 14:42 | 2026 |  |  | 2026-01-06 14:42 | 1 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026971 | RITM0086034 |  | 2652602
JED-HRR2-WAFA-10 | 2602OSPCI0000633 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:08 | 2026-03-26 11:08 | 2026-03-26 11:09 | 2026 |  |  | 2026-03-26 11:09 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000658 | OSPWO0034801 | RITM0095078 |  | 2378601
JED-HRR2-RIYA-23 | 2602OSPFA0000271 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-15 16:24 |  |  | 2026 |  |  | 2026-01-26 08:53 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000271 | OSPWO0027802
JED-HRR2-RIYA-34 | 2502OSPCA0002823 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:36 |  |  | 2025 |  |  | 2025-11-05 10:38 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002982 | OSPWO0024381
JED-HRR2-TEEB-11 | 2602OSPFI0000405 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:52 |  | 2026-01-28 14:52 | 2026 |  |  | 2026-01-28 14:52 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028682 | RITM0088919 |  | 2383501 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-52 | 2602OSPFI0000700 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:30 | 2026-03-26 12:30 | 2026-03-26 12:30 | 2026 |  |  | 2026-03-26 12:31 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000725 | OSPWO0034867 | RITM0095111 |  | 2378601
JED-FRDS-BUHA-30 | 2502OSPFI0003271 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 115971 | 115971 | 2025-12-16 13:15 |  | 2025-12-16 13:15 | 2025 |  |  | 2025-12-16 13:15 | 1 | 0 | 0 | 0 | 0 | 36 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002807 | OSPWO0026015 | RITM0079705 |  | 2382301
JED-HRR2-WAFA-90 | 2602OSPCA0000469 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:16 |  |  | 2026 |  |  | 2026-02-16 12:17 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000469 | OSPWO0032389
JED-HRR2-RIYA-38 | 2502OSPCA0002827 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:39 |  |  | 2025 |  |  | 2025-11-10 17:52 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002986 | OSPWO0024397
JED-FRDS-AMWA-11 | 2602OSPCI0000652 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 472544 | 472544 | 2026-03-28 21:52 | 2026-03-28 21:52 | 2026-03-28 21:53 | 2026 |  |  | 2026-03-28 21:53 | 1 | 0 | 0 | 0 | 0 |  |  | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001018 | OSPWO0034882 | RITM0095198 |  | 2381401
JED-FRDS-BUHA-24 | 2502OSPFA0003243 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:10 |  |  | 2025 |  |  | 2025-12-16 13:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003265 | OSPWO0025992
JED-HRR2-WAFA-20 | 2602OSPFI0000691 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:30 | 2026-03-26 11:30 | 2026-03-26 11:30 | 2026 |  |  | 2026-03-26 11:30 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000693 | OSPWO0034831 | RITM0095092 |  | 2378601
JED-HRR2-WAFA-101 | 2602OSPCI0000459 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:13 | 2026-02-15 22:13 | 2026-02-15 22:14 | 2026 |  |  | 2026-03-01 15:45 | 2 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000611 | OSPWO0032348 | RITM0091371 |  | 2378501
JED-HRR2-RIYA-45 | 2502OSPCA0002833 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:43 |  |  | 2025 |  |  | 2025-11-05 10:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002992 | OSPWO0024421
JED-HRR2-RIYA-25 | 2502OSPCA0002819 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:34 |  |  | 2025 |  |  | 2025-11-05 10:35 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002978 | OSPWO0024365
TAI-QAIM-QIAA-09 | 2602OSPFA0000444 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  |  | 2026 |  |  | 2026-01-28 15:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000444 | OSPWO0028761
JED-FRDS-BUHA-F2 | 2502OSPFI0003272 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 693462 | 693462 | 2025-12-16 13:15 |  | 2025-12-16 13:15 | 2025 |  |  | 2025-12-16 13:16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002809 | OSPWO0026019 | RITM0079707 |  | 2382301
TAI-MELI-FIYS-01 | 2602OSPCA0000104 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:42 |  |  | 2026 |  |  | 2026-01-06 14:43 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000104 | OSPWO0026972
JED-HRR2-WAFA-173 | 2602OSPCI0000595 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:11 | 2026-03-17 11:11 | 2026-03-17 11:12 | 2026 |  |  | 2026-03-17 11:12 | 1 | 0 | 0 | 0 | 0 |  |  | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000980 | OSPWO0034606 | RITM0094712 |  | 2378501
TAI-MELI-JUBR-10 | 2602OSPFA0000402 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:51 |  |  | 2026 |  |  | 2026-01-28 14:51 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000402 | OSPWO0028677
JED-HRR2-RIYA-41 | 2502OSPFA0002980 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:41 |  |  | 2025 |  |  | 2025-11-10 17:53 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003002 | OSPWO0024407
JED-HRR2-WAFA-80 | 2602OSPFI0000511 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:08 |  | 2026-02-16 12:08 | 2026 |  |  | 2026-03-01 15:41 | 2 | 0 | 0 | 0 | 0 | 11 | 86 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000590 | OSPWO0032362 | RITM0091397 |  | 2378501
JED-HRR2-WAFA-87 | 2602OSPFA0000515 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:13 |  |  | 2026 |  |  | 2026-02-16 12:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000515 | OSPWO0032379
JED-HRR2-WAFA-91 | 2602OSPFA0000519 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:18 |  |  | 2026 |  |  | 2026-02-16 12:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000519 | OSPWO0032395
JED-FRDS-BUHA-30 | 2502OSPFA0003249 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:15 |  |  | 2025 |  |  | 2025-12-16 13:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003271 | OSPWO0026016
JED-FRDS-BUHA-28 | 2502OSPCA0003079 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:12 |  |  | 2025 |  |  | 2025-12-16 13:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003238 | OSPWO0026006
JED-HRR2-RIYA-64 | 2602OSPCI0000332 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 13:54 |  | 2026-01-28 13:54 | 2026 |  |  | 2026-01-28 13:54 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028392 | RITM0088769 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-ARIF-01 | 2612OSPCA0000222 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:28 |  |  | 2026 |  |  | 2026-01-14 14:29 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000222 | OSPWO0027734
TAI-QRAU-SABA-03 | 2602OSPFI0000624 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 144855 | 144855 | 2026-03-16 01:31 | 2026-03-16 01:31 | 2026-03-16 01:31 | 2026 |  |  | 2026-03-16 01:31 | 1 | 0 | 0 | 0 | 0 | 88 | 185 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002389 | OSPWO0034511 | RITM0094606 |  | 2651701
JED-FRDS-BUHA-F2 | 2502OSPFA0003250 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:15 |  |  | 2025 |  |  | 2025-12-16 13:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003272 | OSPWO0026020
BAH-BCPS-MASA-01 | 2612OSPCA0000216 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:22 |  |  | 2026 |  |  | 2026-01-14 14:23 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000216 | OSPWO0027708
TAI-QAIM-HASH-09 | 2602OSPFA0000109 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:45 |  |  | 2026 |  |  | 2026-01-06 14:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000109 | OSPWO0026986
BAH-BCPS-SARA-01 | 2612OSPCI0000217 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2999446 | 2999446 | 2026-01-14 14:23 |  | 2026-01-14 14:23 | 2026 |  |  | 2026-01-14 14:23 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027711 | RITM0087558 |  | 6558101
TAI-QAIM-QIAA-10 | 2602OSPFI0000443 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:07 |  | 2026-01-28 15:07 | 2026 |  |  | 2026-01-28 15:07 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028758 | RITM0088960 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
TAI-QRAU-SABA-05 | 2602OSPCI0000573 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 891498 | 891498 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026 |  |  | 2026-03-16 01:35 | 1 | 0 | 0 | 0 | 0 |  |  | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002377 | OSPWO0034517 | RITM0094610 |  | 2651701
JED-HRR2-WAFA-09 | 2602OSPFI0000684 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026 |  |  | 2026-03-26 11:06 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000682 | OSPWO0034799 | RITM0095076 |  | 2378601
JED-HRR2-RIYA-41 | 2602OSPFA0000448 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:09 |  |  | 2026 |  |  | 2026-01-28 15:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000448 | OSPWO0028769
JED-HRR2-RIYA-34 | 2502OSPFA0002974 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:37 |  |  | 2025 |  |  | 2025-11-05 10:38 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002996 | OSPWO0024383
JED-HRR2-RIYA-46 | 2502OSPFA0002985 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:45 |  |  | 2025 |  |  | 2025-11-05 10:46 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003007 | OSPWO0024427
JED-HRR2-WAFA-32 | 2602OSPFI0000697 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:24 | 2026-03-26 12:24 | 2026-03-26 12:24 | 2026 |  |  | 2026-03-26 12:24 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000705 | OSPWO0034855 | RITM0095105 |  | 2378601
JED-HRR2-WAFA-06 | 2602OSPCI0000600 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:29 | 2026-03-17 11:29 | 2026-03-17 11:30 | 2026 |  |  | 2026-03-17 11:30 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000654 | OSPWO0034624 | RITM0094720 |  | 2378601
JED-HRR2-RIYA-39 | 2502OSPCA0002828 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:40 |  |  | 2025 |  |  | 2025-11-05 10:41 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002987 | OSPWO0024401
JED-HRR2-WAFA-23 | 2602OSPFI0000692 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026 |  |  | 2026-03-26 11:32 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000696 | OSPWO0034835 | RITM0095094 |  | 2378601
JED-FRDS-MANA-16 | 2502OSPCA0002811 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:16 |  |  | 2025 |  |  | 2025-11-05 10:17 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002970 | OSPWO0024333
JED-HRR2-RIYA-54 | 2502OSPFA0002990 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:48 |  |  | 2025 |  |  | 2025-11-05 10:50 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003012 | OSPWO0024447
JED-HRR2-SALH-08 | 2602OSPCA0000397 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:20 |  |  | 2026 |  |  | 2026-01-28 14:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000397 | OSPWO0028523
JED-HRR2-WAFA-13 | 2602OSPFI0000686 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026 |  |  | 2026-03-26 11:12 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000686 | OSPWO0034807 | RITM0095079 |  | 2378601
JED-HRR2-WAFA-27 | 2602OSPFI0000695 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026 |  |  | 2026-03-26 11:45 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000700 | OSPWO0034847 | RITM0095101 |  | 2378601
JED-HRR2-RIYA-39 | 2502OSPFA0002979 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:40 |  |  | 2025 |  |  | 2025-11-05 10:42 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003001 | OSPWO0024403
BAH-BCPS-ADEL-01 | 2612OSPFA0000245 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:24 |  |  | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000245 | OSPWO0027716
JED-HRR2-RIYA-41 | 2502OSPCI0002988 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1020256 | 1020256 | 2025-11-05 10:41 |  | 2025-11-05 10:41 | 2025 |  |  | 2025-11-10 17:52 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000786 | OSPWO0024404 | RITM0076819 |  | 2387401
JED-HRR2-RIYA-23 | 2602OSPCA0000399 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:21 |  |  | 2026 |  |  | 2026-01-28 14:22 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000399 | OSPWO0028527
JED-FRDS-BUHA-29 | 2502OSPCA0003080 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:13 |  |  | 2025 |  |  | 2025-12-16 13:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003239 | OSPWO0026010
TAI-QAIM-QIAA-11 | 2602OSPFI0000441 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:06 |  | 2026-01-28 15:06 | 2026 |  |  | 2026-03-07 23:37 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-07 23:37 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028754 | RITM0088958 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-32 | 2602OSPCI0000646 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:23 | 2026-03-26 12:23 | 2026-03-26 12:24 | 2026 |  |  | 2026-03-26 12:24 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000680 | OSPWO0034853 | RITM0095106 |  | 2378601
JED-HRR2-RIYA-44 | 2502OSPCA0002832 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:43 |  |  | 2025 |  |  | 2025-11-05 10:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002991 | OSPWO0024417
JED-FRDS-MANA-05 | 2502OSPFA0002956 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:12 |  |  | 2025 |  |  | 2025-11-05 10:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002978 | OSPWO0024311
JED-HRR2-RIYA-41 | 2502OSPCA0002829 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:41 |  |  | 2025 |  |  | 2025-11-10 17:53 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002988 | OSPWO0024405
BAH-BCPS-ARIF-01 | 2612OSPFI0000248 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 67224 | 67224 | 2026-01-14 14:27 |  | 2026-01-14 14:27 | 2026 |  |  | 2026-01-14 14:27 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027729 | RITM0087568 |  | 6574301
JED-HRR2-WAFA-09 | 2602OSPCI0000632 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026 |  |  | 2026-03-26 11:06 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000657 | OSPWO0034797 | RITM0095075 |  | 2378601
TAI-QAIM-QIAA-09 | 2602OSPCI0000394 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026-01-28 14:19 | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028516 | RITM0088835 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-MASA-01 | 2612OSPFI0000243 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 369663 | 369663 | 2026-01-14 14:23 |  | 2026-01-14 14:23 | 2026 |  |  | 2026-01-14 14:23 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027709 | RITM0087557 |  | 6557601
JED-HRR2-RIYA-36 | 2502OSPFA0002976 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:38 |  |  | 2025 |  |  | 2025-11-05 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002998 | OSPWO0024391
JED-HRR2-WAFA-17 | 2602OSPFI0000688 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:22 | 2026-03-26 11:22 | 2026-03-26 11:22 | 2026 |  |  | 2026-03-26 11:22 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000690 | OSPWO0034819 | RITM0095086 |  | 2378601
JED-HRR2-WAFA-85 | 2602OSPFA0000513 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:10 |  |  | 2026 |  |  | 2026-02-16 12:11 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000513 | OSPWO0032371
JED-HRR2-WAFA-92 | 2602OSPFA0000520 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:19 |  |  | 2026 |  |  | 2026-02-16 12:20 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000520 | OSPWO0032399
TAI-QRAU-SABA-04 | 2602OSPCI0000572 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1343637 | 1343637 | 2026-03-16 01:32 | 2026-03-16 01:32 | 2026-03-16 01:33 | 2026 |  |  | 2026-03-16 01:33 | 1 | 0 | 0 | 0 | 0 |  |  | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002376 | OSPWO0034513 | RITM0094607 |  | 2651701
JED-FRDS-MANA-19 | 2502OSPFA0002964 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:17 |  |  | 2025 |  |  | 2025-11-05 10:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002986 | OSPWO0024343
JED-FRDS-MANA-08 | 2502OSPFA0002959 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:14 |  |  | 2025 |  |  | 2025-11-05 10:15 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002981 | OSPWO0024323
JED-HRR2-WAFA-92 | 2602OSPCA0000471 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:19 |  |  | 2026 |  |  | 2026-02-16 12:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000471 | OSPWO0032397
JED-FRDS-MANA-06 | 2502OSPFA0002957 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:12 |  |  | 2025 |  |  | 2025-11-05 10:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002979 | OSPWO0024315
JED-FRDS-BUHA-26 | 2502OSPFI0003267 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 139597 | 139597 | 2025-12-16 13:11 |  | 2025-12-16 13:11 | 2025 |  |  | 2025-12-16 13:11 | 1 | 0 | 0 | 0 | 0 | 46 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002803 | OSPWO0025999 | RITM0079697 |  | 2382301
JED-FRDS-BUHA-27 | 2502OSPFI0003268 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 122675 | 122675 | 2025-12-16 13:12 |  | 2025-12-16 13:12 | 2025 |  |  | 2025-12-16 13:12 | 1 | 0 | 0 | 0 | 0 | 56 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002804 | OSPWO0026003 | RITM0079699 |  | 2382301
JED-HRR2-WAFA-91 | 2602OSPCI0000470 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:17 |  | 2026-02-16 12:17 | 2026 |  |  | 2026-02-16 12:17 | 1 | 0 | 0 | 0 | 0 |  |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000601 | OSPWO0032392 | RITM0091412 |  | 2378501
TAB-TBK5-MASY-02 | 2607OSPFA0000135 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  |  | 2026 |  |  | 2026-01-07 12:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000135 | OSPWO0027074
JED-HRR2-WAFA-25 | 2602OSPFI0000694 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:41 | 2026-03-26 11:41 | 2026-03-26 11:42 | 2026 |  |  | 2026-03-26 11:42 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000698 | OSPWO0034843 | RITM0095097 |  | 2378601
JED-HRR2-RIYA-56 | 2502OSPCA0002841 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:49 |  |  | 2025 |  |  | 2025-11-10 17:54 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003000 | OSPWO0024453
JED-HRR2-RIYA-70 | 2602OSPFI0000440 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:06 |  | 2026-01-28 15:06 | 2026 |  |  | 2026-01-28 15:06 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028752 | RITM0088957 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-11 | 2602OSPCI0000391 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:18 |  | 2026-01-28 14:18 | 2026 |  |  | 2026-03-07 23:37 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-07 23:37 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028510 | RITM0088832 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-89 | 2602OSPCI0000468 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:15 |  | 2026-02-16 12:15 | 2026 |  |  | 2026-02-16 12:15 | 1 | 0 | 0 | 0 | 0 |  |  | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000599 | OSPWO0032384 | RITM0091408 |  | 2378501
JED-HRR2-RIYA-37 | 2502OSPCA0002826 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:39 |  |  | 2025 |  |  | 2025-11-05 10:40 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002985 | OSPWO0024393
JED-FRDS-BUHA-26 | 2502OSPFA0003245 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:11 |  |  | 2025 |  |  | 2025-12-16 13:12 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003267 | OSPWO0026000
JED-FRDS-BUHA-27 | 2502OSPFA0003246 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:12 |  |  | 2025 |  |  | 2025-12-16 13:13 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003268 | OSPWO0026004
TAI-MELI-JUFE-04 | 2602OSPFA0000450 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:10 |  |  | 2026 |  |  | 2026-01-28 15:11 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000450 | OSPWO0028773
BAH-BCPS-GHAD-01 | 2612OSPCI0000219 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 383374 | 383374 | 2026-01-14 14:25 |  | 2026-01-14 14:25 | 2026 |  |  | 2026-01-14 14:25 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027721 | RITM0087564 |  | 6574301
JED-HRR2-WAFA-25 | 2602OSPCI0000643 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:41 | 2026-03-26 11:41 | 2026-03-26 11:42 | 2026 |  |  | 2026-03-26 11:42 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000673 | OSPWO0034841 | RITM0095098 |  | 2378601
JED-HRR2-WAFA-86 | 2602OSPCI0000465 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:11 |  | 2026-02-16 12:11 | 2026 |  |  | 2026-03-01 15:37 | 2 | 0 | 0 | 0 | 0 |  |  | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000620 | OSPWO0032372 | RITM0091402 |  | 2378501
JED-HRR2-RIYA-56 | 2502OSPCI0003000 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 710415 | 710415 | 2025-11-05 10:49 |  | 2025-11-05 10:49 | 2025 |  |  | 2025-11-10 17:52 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000798 | OSPWO0024452 | RITM0076843 |  | 2387401
JED-HRR2-RIYA-29 | 2502OSPFA0002973 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:36 |  |  | 2025 |  |  | 2025-11-05 10:38 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002995 | OSPWO0024379
JED-HRR2-TEEB-11 | 2602OSPFA0000405 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:52 |  |  | 2026 |  |  | 2026-01-28 14:53 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000405 | OSPWO0028683
JED-HRR2-WAFA-99 | 2602OSPCI0000473 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:21 |  | 2026-02-16 12:21 | 2026 |  |  | 2026-02-16 12:21 | 1 | 0 | 0 | 0 | 0 |  |  | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000609 | OSPWO0032404 | RITM0091418 |  | 2378501
JED-HRR2-RIYA-46 | 2502OSPCA0002834 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:44 |  |  | 2025 |  |  | 2025-11-05 10:46 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002993 | OSPWO0024425
JED-HRR2-RIYA-23 | 2602OSPFA0000449 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:10 |  |  | 2026 |  |  | 2026-01-28 15:10 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000449 | OSPWO0028771
JED-HRR2-FURO-29 | 2602OSPFI0000507 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:11 | 2026-02-15 22:11 | 2026-02-15 22:12 | 2026 |  |  | 2026-03-01 15:46 | 2 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000609 | OSPWO0032346 | RITM0091369 |  | 2378501
JED-HRR2-RIYA-56 | 2502OSPFA0002992 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:49 |  |  | 2025 |  |  | 2025-11-10 17:54 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003014 | OSPWO0024455
BAH-BCPS-SARA-01 | 2612OSPFA0000244 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:24 |  |  | 2026 |  |  | 2026-01-14 14:24 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000244 | OSPWO0027714
JED-HRR2-RIYA-F3 | 2502OSPCA0002842 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:50 |  |  | 2025 |  |  | 2025-11-10 17:51 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003001 | OSPWO0024457
BAH-BCPS-ARIF-01 | 2612OSPCI0000222 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 438579 | 438579 | 2026-01-14 14:28 |  | 2026-01-14 14:28 | 2026 |  |  | 2026-01-14 14:28 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027733 | RITM0087570 |  | 6574301
JED-HRR2-RIYA-25 | 2502OSPFA0002970 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:34 |  |  | 2025 |  |  | 2025-11-05 10:36 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002992 | OSPWO0024367
JED-FRDS-MANA-07 | 2502OSPCA0002807 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:13 |  |  | 2025 |  |  | 2025-11-05 10:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002966 | OSPWO0024317
TAI-QAIM-QIAA-09 | 2602OSPFI0000444 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026-01-28 15:08 | 2026 |  |  | 2026-01-28 15:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028760 | RITM0088961 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-HASH-F4 | 2602OSPFA0000110 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:46 |  |  | 2026 |  |  | 2026-01-06 14:47 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000110 | OSPWO0026990
JED-HRR2-WAFA-28 | 2602OSPFI0000696 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:50 | 2026-03-26 11:50 | 2026-03-26 11:50 | 2026 |  |  | 2026-03-26 11:50 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000701 | OSPWO0034851 | RITM0095103 |  | 2378601
JED-HRR2-WAFA-86 | 2602OSPFI0000514 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:12 |  | 2026-02-16 12:12 | 2026 |  |  | 2026-03-01 15:37 | 2 | 0 | 0 | 0 | 0 | 31 | 63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000596 | OSPWO0032374 | RITM0091403 |  | 2378501
JED-HRR2-WAFA-52 | 2602OSPCI0000649 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:30 | 2026-03-26 12:30 | 2026-03-26 12:31 | 2026 |  |  | 2026-03-26 12:31 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000700 | OSPWO0034865 | RITM0095112 |  | 2378601
JED-HRR2-SALH-18 | 2602OSPCA0000129 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-07 15:44 |  |  | 2026 |  |  | 2026-01-07 15:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000129 | OSPWO0027098
BAH-BCPS-AREE-01 | 2612OSPCA0000221 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:27 |  |  | 2026 |  |  | 2026-01-14 14:27 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000221 | OSPWO0027728
JED-HRR2-RIYA-23 | 2602OSPFI0000271 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 211409 | 211409 | 2026-01-15 16:24 |  | 2026-01-15 16:24 | 2026 |  |  | 2026-01-26 08:52 | 2 | 0 | 0 | 0 | 0 | 65 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-26 08:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000732 | OSPWO0027801 | RITM0087656 |  | 2387401
JED-HRR2-RIYA-45 | 2502OSPFA0002984 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:44 |  |  | 2025 |  |  | 2025-11-05 10:45 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003006 | OSPWO0024423
TAI-QAIM-HASH-08 | 2602OSPCA0000106 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:44 |  |  | 2026 |  |  | 2026-01-06 14:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000106 | OSPWO0026980
JED-HRR2-RIYA-38 | 2502OSPFI0002861 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 219834 | 219834 | 2025-10-11 22:39 | 2025-10-11 22:39 | 2025-10-11 22:39 | 2025 |  |  | 2025-11-10 17:51 | 3 | 0 | 0 | 0 | 0 | 59 | 185 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:51 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000629 | OSPWO0023696 | RITM0075248 |  | 2387401
JED-HRR2-WAFA-86 | 2602OSPFA0000514 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:12 |  |  | 2026 |  |  | 2026-02-16 12:12 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000514 | OSPWO0032375
JED-HRR2-WAFA-90 | 2602OSPFA0000518 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:17 |  |  | 2026 |  |  | 2026-02-16 12:18 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000518 | OSPWO0032391
JED-HRR2-RIYA-56 | 2502OSPFI0003014 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 184795 | 184795 | 2025-11-05 10:49 |  | 2025-11-05 10:49 | 2025 |  |  | 2025-11-10 17:52 | 2 | 0 | 0 | 0 | 0 | 75 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000727 | OSPWO0024454 | RITM0076844 |  | 2387401
JED-HRR2-RIYA-F3 | 2502OSPCI0003001 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 214465 | 214465 | 2025-11-05 10:50 |  | 2025-11-05 10:50 | 2025 |  |  | 2025-11-10 17:50 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000779 | OSPWO0024456 | RITM0076845 |  | 2387401
TAI-AYKB-QAMA-01 | 2502OSPCI0002758 | 0 | MAKKAH | FEP-Phase1 | Civil | 1 - PIP Submission | 1818336.8 | 1818336.8 | 2025-09-28 08:35 | 2025-09-28 08:35 | 2025-09-28 08:36 | 2025 |  |  | 2025-10-01 08:03 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-10-01 08:03 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023233 | RITM0073988 |  | 2634901
TAI-QRAU-SABA-04 | 2602OSPFI0000625 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 329236 | 329236 | 2026-03-16 01:33 | 2026-03-16 01:33 | 2026-03-16 01:33 | 2026 |  |  | 2026-03-16 01:33 | 1 | 0 | 0 | 0 | 0 | 186 | 813 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002390 | OSPWO0034515 | RITM0094608 |  | 2651701
JED-FRDS-BUHA-F2 | 2502OSPCA0003082 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:15 |  |  | 2025 |  |  | 2025-12-16 13:16 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003241 | OSPWO0026018
JED-HRR2-WAFA-24 | 2602OSPFI0000693 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:36 | 2026-03-26 11:36 | 2026-03-26 11:36 | 2026 |  |  | 2026-03-26 11:36 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000697 | OSPWO0034839 | RITM0095096 |  | 2378601
JED-HRR2-WAFA-11 | 2602OSPFI0000656 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:40 | 2026-03-17 11:40 | 2026-03-17 11:40 | 2026 |  |  | 2026-03-17 11:40 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000684 | OSPWO0034642 | RITM0094730 |  | 2378601
JED-FRDS-BUHA-28 | 2502OSPFI0003269 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 130244 | 130244 | 2025-12-16 13:13 |  | 2025-12-16 13:13 | 2025 |  |  | 2025-12-16 13:13 | 1 | 0 | 0 | 0 | 0 | 62 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002805 | OSPWO0026007 | RITM0079701 |  | 2382301
JED-HRR2-WAFA-42 | 2602OSPFI0000698 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:26 | 2026-03-26 12:26 | 2026-03-26 12:26 | 2026 |  |  | 2026-03-26 12:26 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000715 | OSPWO0034859 | RITM0095108 |  | 2378601
MAK-WHD2-QASA-15 | 2602OSPFA0000145 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-07 15:47 |  |  | 2026 |  |  | 2026-01-07 17:58 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000145 | OSPWO0027108
JED-FRDS-MANA-F1 | 2502OSPFA0002968 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:20 |  |  | 2025 |  |  | 2025-11-05 10:22 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002990 | OSPWO0024359
JED-HRR2-WAFA-02 | 2602OSPCI0000603 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:37 | 2026-03-17 11:37 | 2026-03-17 11:38 | 2026 |  |  | 2026-03-17 11:38 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000650 | OSPWO0034636 | RITM0094728 |  | 2378601
TAI-QAIM-QIAA-10 | 2602OSPFA0000443 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:07 |  |  | 2026 |  |  | 2026-01-28 15:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000443 | OSPWO0028759
JED-FRDS-BUHA-22 | 2502OSPFI0003263 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 146064 | 146064 | 2025-12-16 13:08 |  | 2025-12-16 13:08 | 2025 |  |  | 2025-12-16 13:08 | 1 | 0 | 0 | 0 | 0 | 71 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002799 | OSPWO0025983 | RITM0079689 |  | 2382301
JED-HRR2-WAFA-13 | 2602OSPCI0000634 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026 |  |  | 2026-03-26 11:12 | 1 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000661 | OSPWO0034805 | RITM0095080 |  | 2378601
JED-HRR2-WAFA-98 | 2602OSPFA0000521 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:20 |  |  | 2026 |  |  | 2026-02-16 12:21 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000521 | OSPWO0032403
JED-HRR2-RIYA-38 | 2502OSPFA0002978 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:40 |  |  | 2025 |  |  | 2025-11-05 10:41 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003000 | OSPWO0024399
JED-FRDS-BUHA-28 | 2502OSPFA0003247 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:13 |  |  | 2025 |  |  | 2025-12-16 13:14 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003269 | OSPWO0026008
MAK-WHD2-QASA-15 | 2602OSPFI0000145 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 103731 | 103731 | 2026-01-07 15:47 |  | 2026-01-07 15:47 | 2026 |  |  | 2026-01-07 17:57 | 2 | 0 | 0 | 0 | 0 | 64 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-07 17:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001804 | OSPWO0027107 | RITM0086641 |  | 2457701
JED-HRR2-WAFA-88 | 2602OSPCI0000467 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:14 |  | 2026-02-16 12:14 | 2026 |  |  | 2026-02-16 12:14 | 1 | 0 | 0 | 0 | 0 |  |  | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000598 | OSPWO0032380 | RITM0091406 |  | 2378501
JED-HRR2-RIYA-43 | 2502OSPCA0002831 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:42 |  |  | 2025 |  |  | 2025-11-05 10:44 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002990 | OSPWO0024413
JED-FRDS-BUHA-22 | 2502OSPFA0003241 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:08 |  |  | 2025 |  |  | 2025-12-16 13:08 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003263 | OSPWO0025984
JED-HRR2-WAFA-51 | 2602OSPFI0000699 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:28 | 2026-03-26 12:28 | 2026-03-26 12:29 | 2026 |  |  | 2026-03-26 12:29 | 1 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000724 | OSPWO0034863 | RITM0095110 |  | 2378601
JED-HRR2-RIYA-F3 | 2502OSPFI0002860 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 3859165 | 3859165 | 2025-10-11 22:31 | 2025-10-11 22:31 | 2025-10-11 22:32 | 2025 |  |  | 2025-11-10 17:50 | 3 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000737 | OSPWO0023692 | RITM0075246 |  | 2387401
JED-HRR2-RIYA-56 | 2602OSPCI0000395 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026-01-28 14:19 | 2026 |  |  | 2026-01-28 14:19 | 1 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028518 | RITM0088836 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-RIYA-23 | 2602OSPCA0000234 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-15 16:24 |  |  | 2026 |  |  | 2026-01-26 08:53 | 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000234 | OSPWO0027800
JED-FRDS-MANA-05 | 2502OSPFI0002978 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 136321 | 136321 | 2025-11-05 10:12 |  | 2025-11-05 10:12 | 2025 | 2026-06-28 |  | 2025-12-17 10:37 | 9 | 0 | 0 | 0 | 0 | 82 | 161 | 0 | 0 | 11292 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001885 | OSPWO0024310 | RITM0076771 |  | 2382901
SAM-SMTH-AMUD-01 | 2510OSPCI0003076 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 500700 | 500700 | 2025-11-16 10:40 |  | 2025-11-16 10:40 | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 15 | 0 | 3773 | 0 | 16 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024855 | RITM0077595 |  | 8684101
TAI-MELI-JUFE-02 | 2502OSPFI0003300 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 221229 | 221229 | 2025-12-17 10:33 | 2025-12-17 10:33 | 2025-12-17 10:33 | 2025 | 2026-05-31 |  | 2026-02-24 11:20 | 12 | 0 | 0 | 0 | 0 | 142 | 547 |  | 0 | 21101 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001768 | OSPWO0026129 | RITM0079813 |  | 2652502
TAI-MELI-NASE-03 | 2502OSPCI0003271 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1600420 | 1600420 | 2025-12-17 10:47 | 2025-12-17 10:47 | 2025-12-17 10:48 | 2025 | 2026-02-28 |  | 2026-02-24 10:52 | 12 | 0 | 13276 | 0 | 23 | 219 | 1171 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000019 | OSPWO0026146 | RITM0079821 |  | 2651801
JED-HRR2-RIYA-57 | 2602OSPFI0000127 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 169308 | 169308 | 2026-01-06 14:58 |  | 2026-01-06 14:58 | 2026 | 2026-06-30 |  | 2026-02-10 14:18 | 7 | 0 | 0 | 0 | 0 | 55 | 113 | 0 | 0 | 8383 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 11 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000694 | OSPWO0027043 | RITM0086078 |  | 2387401
TAI-MELI-JUFE-03 | 2502OSPCI0003268 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 983261 | 983261 | 2025-12-17 10:34 | 2025-12-17 10:34 | 2025-12-17 10:35 | 2025 | 2026-04-30 |  | 2026-02-24 11:21 | 12 | 0 | 9579 | 0 | 13 | 163 | 549 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001728 | OSPWO0026131 | RITM0079814 |  | 2652502
JED-HRR2-RIYA-47 | 2502OSPFI0003008 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 197261 | 197261 | 2025-11-05 10:45 |  | 2025-11-05 10:45 | 2025 | 2026-02-25 |  | 2026-03-01 14:13 | 10 | 0 | 0 | 0 | 0 | 79 | 268 | 0 | 0 | 10100 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000760 | OSPWO0024430 | RITM0076832 |  | 2387401
SAM-SMTH-TURS-01 | 2510OSPCI0003074 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 380983 | 380983 | 2025-11-16 10:39 |  | 2025-11-16 10:39 | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 15 | 0 | 2902 | 0 | 12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024847 | RITM0077591 |  | 8674201
JED-HRR2-RIYA-53 | 2502OSPCI0002997 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 709548 | 709548 | 2025-11-05 10:47 |  | 2025-11-05 10:47 | 2025 | 2026-04-25 |  | 2025-12-17 10:35 | 9 | 0 | 6521 | 0 | 13 | 59 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000766 | OSPWO0024440 | RITM0076837 |  | 2387401
SAM-SMTH-MASO-01 | 2510OSPCI0003075 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 180723 | 180723 | 2025-11-16 10:40 |  | 2025-11-16 10:40 | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 15 | 0 | 1398 | 0 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024851 | RITM0077593 |  | 8679401
JED-HRR2-RIYA-35 | 2502OSPFI0002997 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 170387 | 170387 | 2025-11-05 10:38 |  | 2025-11-05 10:38 | 2025 | 2026-03-28 |  | 2025-12-17 10:33 | 9 | 0 | 0 | 0 | 0 | 48 | 302 | 0 | 0 | 7968 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000779 | OSPWO0024386 | RITM0076810 |  | 2387401
JED-FRDS-BUHA-22 | 2502OSPCI0003232 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 894379 | 894379 | 2025-12-16 13:07 |  | 2025-12-16 13:07 | 2025 | 2026-07-30 |  | 2026-01-28 14:23 | 7 | 0 | 8852 | 0 | 15 | 71 | 146 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002748 | OSPWO0025981 | RITM0079688 |  | 2382301
JED-FRDS-MANA-17 | 2602OSPCI0000117 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 659281 | 659281 | 2026-01-06 14:56 |  | 2026-01-06 14:56 | 2026 | 2026-07-30 |  | 2026-01-28 14:21 | 7 | 0 | 7780 | 0 | 12 | 54 | 170 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001855 | OSPWO0027037 | RITM0086075 |  | 2382901
SAM-SMTH-MASO-01 | 2510OSPFI0003095 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 26756 | 26756 | 2025-11-16 10:40 |  | 2025-11-16 10:40 | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1495 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024853 | RITM0077594 |  | 8679401
JED-FRDS-MANA-06 | 2502OSPCI0002965 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 754708 | 754708 | 2025-11-05 10:12 |  | 2025-11-05 10:12 | 2025 | 2026-05-29 |  | 2025-12-17 10:25 | 10 | 0 | 7065 | 0 | 14 | 110 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001844 | OSPWO0024312 | RITM0076772 |  | 2382901
TAI-MELI-JUFE-F1 | 2502OSPFI0003304 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 108806 | 108806 | 2025-12-17 10:46 | 2025-12-17 10:46 | 2025-12-17 10:46 | 2025 | 2026-02-28 |  | 2026-02-24 10:49 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4794 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001772 | OSPWO0026144 | RITM0079820 |  | 2652502
JED-FRDS-MANA-09 | 2502OSPFI0002982 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 108345 | 108345 | 2025-11-05 10:14 |  | 2025-11-05 10:14 | 2025 | 2026-07-20 |  | 2025-12-17 10:32 | 8 | 0 | 0 | 0 | 0 | 58 | 154 | 0 | 0 | 8283 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001889 | OSPWO0024326 | RITM0076779 |  | 2382901
JED-HRR2-RIYA-24 | 2502OSPFI0002991 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 202694 | 202694 | 2025-11-05 10:33 |  | 2025-11-05 10:33 | 2025 | 2026-02-22 |  | 2026-03-01 14:13 | 9 | 0 | 0 | 0 | 0 | 79 | 264 | 0 | 0 | 10989 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000676 | OSPWO0024362 | RITM0076798 |  | 2387401
TAI-MELI-JUFE-02 | 2502OSPCI0003267 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 868963 | 868963 | 2025-12-17 10:32 | 2025-12-17 10:32 | 2025-12-17 10:33 | 2025 | 2026-04-30 |  | 2026-02-24 11:19 | 12 | 0 | 8990 | 0 | 10 | 142 | 547 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001727 | OSPWO0026127 | RITM0079812 |  | 2652502
SAM-SMTH-MAJA-01 | 2510OSPFI0003097 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 191528 | 191528 | 2025-11-16 10:41 |  | 2025-11-16 10:41 | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10190 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024861 | RITM0077598 |  | 8684101
JED-HRR2-RIYA-55 | 2502OSPFI0003013 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 204518 | 204518 | 2025-11-05 10:49 |  | 2025-11-05 10:49 | 2025 | 2026-05-23 |  | 2025-12-17 10:41 | 9 | 0 | 0 | 0 | 0 | 73 | 281 | 0 | 0 | 10934 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000600 | OSPWO0024450 | RITM0076842 |  | 2387401
TAI-QAIM-HASH-F4 | 2602OSPCI0000108 |  | MAKKAH | FTTH | Civil | 2 - PIP Approval | 1240 | 1240 | 2026-01-06 14:46 |  | 2026-01-06 14:46 | 2026 |  |  | 2026-02-24 12:09 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000559 | OSPWO0026987 | RITM0086049 |  | 2656301
JED-HRR2-SALH-19 | 2502OSPFI0002964 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 172425.9 | 172426 | 2025-11-04 22:04 | 2025-11-04 22:04 | 2025-11-04 22:05 | 2025 | 2026-03-28 |  | 2026-03-09 17:16 | 11 | 0 | 0 | 0 | 0 | 131 | 179 |  | 0 | 14673 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002487 | OSPWO0024247 | RITM0076719 |  | 2376401
JED-HRR2-RIYA-40 | 2502OSPCI0002900 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1106083 | 1106083 | 2025-10-27 13:48 | 2025-10-27 13:48 | 2025-10-27 13:49 | 2025 | 2026-03-30 |  | 2025-12-17 10:21 | 8 | 0 | 9612 | 0 | 16 | 50 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000629 | OSPWO0023942 | RITM0076064 |  | 2387401
JED-HRR2-RIYA-29 | 2502OSPCI0002981 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 769265 | 769265 | 2025-11-05 10:36 |  | 2025-11-05 10:36 | 2025 | 2026-02-28 |  | 2025-12-17 10:24 | 8 | 0 | 6830 | 0 | 13 | 94 | 302 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000751 | OSPWO0024376 | RITM0076805 |  | 2387401
JED-FRDS-MANA-17 | 2602OSPFI0000126 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 133041 | 133041 | 2026-01-06 14:57 |  | 2026-01-06 14:57 | 2026 | 2026-08-20 |  | 2026-02-22 22:25 | 7 | 0 | 0 | 0 | 0 | 54 | 170 | 0 | 0 | 11220 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 14 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001897 | OSPWO0027039 | RITM0086076 |  | 2382901
JED-HRR2-RIYA-55 | 2502OSPCI0002999 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 840954 | 840954 | 2025-11-05 10:48 |  | 2025-11-05 10:48 | 2025 | 2026-04-25 |  | 2025-12-17 10:28 | 9 | 0 | 7186 | 0 | 15 | 73 | 281 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000648 | OSPWO0024448 | RITM0076841 |  | 2387401
JED-FRDS-BUHA-26 | 2502OSPCI0003236 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 838712 | 838712 | 2025-12-16 13:11 |  | 2025-12-16 13:11 | 2025 | 2026-07-29 |  | 2026-01-28 14:24 | 7 | 0 | 9339 | 0 | 18 | 46 | 119 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002752 | OSPWO0025997 | RITM0079696 |  | 2382301
JED-HRR2-RIYA-44 | 2502OSPFI0003005 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 167845 | 167845 | 2025-11-05 10:43 |  | 2025-11-05 10:43 | 2025 | 2026-05-30 |  | 2025-12-17 10:41 | 8 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 9604 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000762 | OSPWO0024418 | RITM0076826 |  | 2387401
TAI-MELI-JUFE-05 | 2502OSPFI0003303 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 0 | 0 | 2025-12-17 10:43 | 2025-12-17 10:43 | 2025-12-17 10:44 | 2025 | 2026-05-31 |  | 2026-02-24 11:28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001771 | OSPWO0026142 | RITM0079819 |  | 2652502
JED-FRDS-BUHA-25 | 2502OSPCI0003235 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 768706 | 768706 | 2025-12-16 13:10 |  | 2025-12-16 13:10 | 2025 | 2026-07-29 |  | 2026-01-28 14:24 | 7 | 0 | 8718 | 0 | 13 | 71 | 174 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002751 | OSPWO0025993 | RITM0079694 |  | 2382301
JED-FRDS-MANA-09 | 2502OSPCI0002968 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 580928 | 580928 | 2025-11-05 10:14 |  | 2025-11-05 10:14 | 2025 | 2026-06-25 |  | 2025-12-17 10:26 | 7 | 0 | 6761 | 0 | 12 | 58 | 154 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001847 | OSPWO0024324 | RITM0076778 |  | 2382901
JED-FRDS-MANA-21 | 2502OSPCI0002974 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 824615 | 824615 | 2025-11-05 10:18 |  | 2025-11-05 10:18 | 2025 | 2026-05-30 |  | 2025-12-17 10:27 | 7 | 0 | 8246 | 0 | 13 | 61 | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001859 | OSPWO0024348 | RITM0076790 |  | 2382901
JED-HRR2-RIYA-41 | 2502OSPFI0003002 |  | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 216927 | 216927 | 2025-11-05 10:41 |  | 2025-11-05 10:41 | 2025 |  |  | 2025-12-17 01:55 | 6 | 0 | 0 | 0 | 0 | 65 | 170 | 0 | 0 | 14355 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000772 | OSPWO0024406 | RITM0076820 |  | 2387401
TAB-TBK5-MASY-F1 | 2607OSPFI0000138 |  | TABUK | FTTH | Fiber | 3 - Implementation | 60084 | 60084 | 2026-01-07 12:24 |  | 2026-01-07 12:24 | 2026 | 2026-03-30 |  | 2026-02-11 14:24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2182 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2409OSPFD0002441 | OSPWO0027079 | RITM0086554 |  | 4732401
TAI-THVT-YASM-02 | 2502OSPFI0003244 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 196871 | 196871 | 2025-12-16 10:02 | 2025-12-16 10:02 | 2025-12-16 10:02 | 2025 | 2026-03-31 |  | 2026-02-24 12:02 | 10 | 0 | 0 | 0 | 0 | 137 | 472 |  | 0 | 16547 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000577 | OSPWO0025907 | RITM0079641 |  | 2656201
TAI-QAIM-QIAA-F2 | 2602OSPCI0000111 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 5200 | 5200 | 2026-01-06 14:48 |  | 2026-01-06 14:48 | 2026 | 2026-02-28 |  | 2026-02-24 12:03 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000473 | OSPWO0026999 | RITM0086055 |  | 2656101
EDA-AYBN-EDAB-01 | 2510OSPFI0002900 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 949010 | 831746.7 | 2025-10-27 08:39 | 2025-10-27 08:39 | 2025-10-27 08:39 | 2025 | 2026-10-31 |  | 2026-03-02 14:38 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023904 | RITM0076014 |  | 8574601
TAI-MELI-FIYS-01 | 2602OSPFI0000106 |  | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:42 |  | 2026-01-06 14:42 | 2026 |  |  | 2026-01-22 13:49 | 2 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026973 | RITM0086035 |  | 2652602
TAI-QAIM-HASH-08 | 2602OSPFI0000108 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130567 | 130567 | 2026-01-06 14:44 |  | 2026-01-06 14:44 | 2026 | 2026-04-30 |  | 2026-02-24 11:52 | 10 | 0 | 0 | 0 | 0 | 62 | 310 | 0 | 0 | 9035 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000533 | OSPWO0026981 | RITM0086040 |  | 2656301
JED-FRDS-BUHA-24 | 2502OSPCI0003234 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 849302 | 849302 | 2025-12-16 13:09 |  | 2025-12-16 13:09 | 2025 | 2026-07-31 |  | 2026-01-28 14:24 | 7 | 0 | 8391 | 0 | 15 | 71 | 163 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002750 | OSPWO0025989 | RITM0079692 |  | 2382301
JED-HRR2-RAHA-18 | 2502OSPFI0003125 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 257236.75 | 258927 | 2025-11-16 22:39 | 2025-11-16 22:39 | 2025-11-16 22:39 | 2025 | 2026-01-29 |  | 2026-03-09 17:22 | 9 | 0 | 0 | 0 | 0 | 170 | 220 |  | 0 | 20347 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000008 | OSPWO0024974 | RITM0077706 |  | 2376401
TAB-TBHH-MASY-01 | 2607OSPFI0000134 |  | TABUK | FTTH | Fiber | 3 - Implementation | 280379 | 280379 | 2026-01-07 12:24 |  | 2026-01-07 12:24 | 2026 | 2026-03-26 |  | 2026-02-11 14:24 | 11 | 0 | 0 | 0 | 0 | 186 | 186 |  | 0 | 16903 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002383 | OSPWO0027071 | RITM0086547 |  | 4732401
JED-HRR2-SALH-07 | 2502OSPFI0002436 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 189442.35 | 189442.35 | 2025-08-14 15:51 | 2025-08-14 15:51 | 2025-08-14 15:51 | 2025 | 2025-12-19 |  | 2026-03-09 16:02 | 11 | 0 | 0 | 0 | 0 | 142 | 291 |  | 0 | 18952 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000014 | OSPWO0021672 | RITM0070644 |  | 2376401
JED-HRR2-RIYA-57 | 2602OSPCI0000118 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 751838 | 751838 | 2026-01-06 14:57 |  | 2026-01-06 14:57 | 2026 | 2026-06-30 |  | 2026-02-10 08:25 | 7 | 0 | 5449 | 0 | 16 | 55 | 113 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000749 | OSPWO0027041 | RITM0086077 |  | 2387401
JED-HRR2-SALH-17 | 2502OSPFI0002833 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 239877.7 | 239878 | 2025-10-06 10:25 | 2025-10-06 10:25 | 2025-10-06 10:25 | 2025 | 2026-03-28 |  | 2026-03-02 14:32 | 10 | 0 | 0 | 0 | 0 | 161 | 142 |  | 0 | 22706 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002485 | OSPWO0023573 | RITM0074743 |  | 2376401
TAI-QAIM-QIAA-F2 | 2602OSPFI0000113 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 59839 | 59839 | 2026-01-06 14:49 |  | 2026-01-06 14:49 | 2026 | 2026-03-31 |  | 2026-02-24 12:04 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000449 | OSPWO0027001 | RITM0086056 |  | 2656101
JED-FRDS-MANA-21 | 2502OSPFI0002988 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 128671 | 128671 | 2025-11-05 10:19 |  | 2025-11-05 10:19 | 2025 | 2026-06-24 |  | 2025-12-17 10:39 | 7 | 0 | 0 | 0 | 0 | 61 | 190 | 0 | 0 | 9506 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001901 | OSPWO0024350 | RITM0076791 |  | 2382901
JED-FRDS-MANA-22 | 2502OSPCI0002975 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 804013 | 804013 | 2025-11-05 10:19 |  | 2025-11-05 10:19 | 2025 | 2026-05-30 |  | 2025-12-17 10:27 | 8 | 0 | 7917 | 0 | 14 | 57 | 171 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001860 | OSPWO0024352 | RITM0076792 |  | 2382901
SAM-SMTH-TURS-01 | 2510OSPFI0003094 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 60718 | 60718 | 2025-11-16 10:39 |  | 2025-11-16 10:39 | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024849 | RITM0077592 |  | 8674201
JED-HRR2-RIYA-27 | 2502OSPCI0002980 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 808790 | 808790 | 2025-11-05 10:35 |  | 2025-11-05 10:35 | 2025 | 2026-02-25 |  | 2025-12-17 10:23 | 8 | 0 | 6670 | 0 | 15 | 79 | 281 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000698 | OSPWO0024372 | RITM0076803 |  | 2387401
JED-HRR2-RIYA-36 | 2502OSPCI0002984 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1012456 | 1012456 | 2025-11-05 10:38 |  | 2025-11-05 10:38 | 2025 | 2026-03-24 |  | 2025-12-17 10:28 | 8 | 0 | 6300 | 0 | 17 | 59 | 291 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000760 | OSPWO0024388 | RITM0076811 |  | 2387401
JED-HRR2-RIYA-40 | 2502OSPFI0002909 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 183272 | 183272 | 2025-10-27 13:49 | 2025-10-27 13:49 | 2025-10-27 13:49 | 2025 | 2026-04-25 |  | 2025-12-17 10:32 | 9 | 0 | 0 | 0 | 0 | 50 | 293 |  | 0 | 10102 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000776 | OSPWO0023944 | RITM0076065 |  | 2387401
TAI-THVT-YASM-01 | 2502OSPCI0003212 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 615453 | 615453 | 2025-12-16 09:59 | 2025-12-16 09:59 | 2025-12-16 09:59 | 2025 | 2026-02-28 |  | 2026-02-24 11:59 | 10 | 0 | 7671 | 0 | 13 | 86 | 314 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000557 | OSPWO0025901 | RITM0079639 |  | 2656201
TAI-THVT-YASM-01 | 2502OSPFI0003243 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 144002 | 144002 | 2025-12-16 09:59 | 2025-12-16 09:59 | 2025-12-16 10:00 | 2025 | 2026-03-31 |  | 2026-02-24 12:00 | 10 | 0 | 0 | 0 | 0 | 86 | 314 |  | 0 | 11412 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000576 | OSPWO0025903 | RITM0079640 |  | 2656201
JED-FRDS-MANA-08 | 2502OSPCI0002967 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 631849 | 631849 | 2025-11-05 10:13 |  | 2025-11-05 10:13 | 2025 | 2026-06-30 |  | 2025-12-17 10:26 | 7 | 0 | 4217 | 0 | 12 | 51 | 157 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001846 | OSPWO0024320 | RITM0076776 |  | 2382901
JED-FRDS-MANA-18 | 2502OSPFI0002985 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130417 | 130417 | 2025-11-05 10:17 |  | 2025-11-05 10:17 | 2025 | 2026-07-25 |  | 2025-12-17 10:34 | 8 | 0 | 0 | 0 | 0 | 62 | 178 | 0 | 0 | 10071 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001898 | OSPWO0024338 | RITM0076785 |  | 2382901
SAM-SMTH-KHAD-01 | 2510OSPFI0003093 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 115316 | 115316 | 2025-11-16 10:39 |  | 2025-11-16 10:39 | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024845 | RITM0077590 |  | 8673901
TAI-AYKB-QUDS-01 | 2502OSPCI0002756 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 2538475.7 | 2664847.4 | 2025-09-28 08:31 | 2025-09-28 08:31 | 2025-09-28 08:37 | 2025 | 2026-04-30 |  | 2025-12-01 16:59 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023227 | RITM0073989 |  | 2634701
TAI-MELI-NASE-03 | 2502OSPFI0003305 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 515873 | 515873 | 2025-12-17 10:48 | 2025-12-17 10:48 | 2025-12-17 10:48 | 2025 | 2026-03-31 |  | 2026-02-24 10:53 | 13 | 0 | 0 | 0 | 0 | 219 | 1171 |  | 0 | 37390 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000019 | OSPWO0026148 | RITM0079822 |  | 2651801
JED-FRDS-BUHA-27 | 2502OSPCI0003237 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 727041 | 727041 | 2025-12-16 13:12 |  | 2025-12-16 13:12 | 2025 | 2026-07-28 |  | 2026-01-28 14:24 | 7 | 0 | 8092 | 0 | 14 | 56 | 137 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002753 | OSPWO0026001 | RITM0079698 |  | 2382301
JED-FRDS-BUHA-23 | 2502OSPCI0003233 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 586418 | 586418 | 2025-12-16 13:08 |  | 2025-12-16 13:08 | 2025 | 2026-07-30 |  | 2026-02-22 22:23 | 8 | 0 | 4164 | 0 | 10 | 48 | 93 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002749 | OSPWO0025985 | RITM0079690 |  | 2382301
JED-FRDS-BUHA-30 | 2502OSPCI0003240 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 693068 | 693068 | 2025-12-16 13:14 |  | 2025-12-16 13:14 | 2025 | 2026-08-31 |  | 2026-02-22 22:23 | 7 | 0 | 4779 | 0 | 11 | 36 | 92 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002756 | OSPWO0026013 | RITM0079704 |  | 2382301
JED-FRDS-MANA-06 | 2502OSPFI0002979 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 168819 | 168819 | 2025-11-05 10:12 |  | 2025-11-05 10:12 | 2025 | 2026-06-24 |  | 2025-12-17 10:38 | 8 | 0 | 0 | 0 | 0 | 110 | 163 | 0 | 0 | 13656 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001886 | OSPWO0024314 | RITM0076773 |  | 2382901
JED-HRR2-RIYA-59 | 2602OSPFI0000015 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 131792 | 131792 | 2026-01-04 09:02 | 2026-01-04 09:02 | 2026-01-04 09:02 | 2026 | 2026-06-30 |  | 2026-02-10 14:19 | 7 | 0 | 0 | 0 | 0 | 37 | 94 |  | 0 | 5781 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 10 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000668 | OSPWO0026593 | RITM0084708 |  | 2387401
JED-FRDS-MANA-F1 | 2502OSPCI0002976 |  | MAKKAH | FTTH | Civil | 1 - PIP Submission | 0 | 0 | 2025-11-05 10:20 |  | 2025-11-05 10:20 | 2025 |  |  | 2026-02-09 23:43 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001866 | OSPWO0024356 | RITM0076794 |  | 2382901
JED-FRDS-MANA-20 | 2502OSPFI0002987 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 137448 | 137448 | 2025-11-05 10:18 |  | 2025-11-05 10:18 | 2025 | 2026-06-25 |  | 2025-12-17 10:38 | 8 | 0 | 0 | 0 | 0 | 74 | 174 | 0 | 0 | 10309 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001900 | OSPWO0024346 | RITM0076789 |  | 2382901
JED-HRR2-RIYA-50 | 2502OSPCI0002995 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 596304 | 596304 | 2025-11-05 10:46 |  | 2025-11-05 10:46 | 2025 | 2026-04-25 |  | 2025-12-17 10:28 | 9 | 0 | 4255 | 0 | 11 | 64 | 290 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000653 | OSPWO0024432 | RITM0076833 |  | 2387401
JED-HRR2-RIYA-37 | 2502OSPFI0002999 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 180887 | 180887 | 2025-11-05 10:39 |  | 2025-11-05 10:39 | 2025 | 2026-04-27 |  | 2025-12-17 10:40 | 8 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 11418 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000604 | OSPWO0024394 | RITM0076814 |  | 2387401
JED-FRDS-MANA-22 | 2502OSPFI0002989 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130834 | 130834 | 2025-11-05 10:19 |  | 2025-11-05 10:19 | 2025 | 2026-06-25 |  | 2025-12-17 10:34 | 8 | 0 | 0 | 0 | 0 | 57 | 171 | 0 | 0 | 9419 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001902 | OSPWO0024354 | RITM0076793 |  | 2382901
JED-HRR2-RIYA-50 | 2502OSPFI0003009 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 153573 | 153573 | 2025-11-05 10:46 |  | 2025-11-05 10:46 | 2025 | 2026-05-24 |  | 2025-12-17 10:41 | 8 | 0 | 0 | 0 | 0 | 64 | 290 | 0 | 0 | 8028 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000599 | OSPWO0024434 | RITM0076834 |  | 2387401
JED-HRR2-RIYA-F3 | 2502OSPFI0003015 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 3859165 | 3859165 | 2025-11-05 10:50 |  | 2025-11-05 10:50 | 2025 | 2026-02-21 |  | 2025-12-17 10:36 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152899 | 0 | 0 | 0 | 15 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000737 | OSPWO0024458 | RITM0076846 |  | 2387401
JED-FRDS-MANA-F1 | 2502OSPFI0002990 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 1116248 | 1116248 | 2025-11-05 10:20 |  | 2025-11-05 10:20 | 2025 | 2026-06-21 |  | 2025-12-17 10:39 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43083 | 0 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001908 | OSPWO0024358 | RITM0076795 |  | 2382901
TAI-MELI-JUFE-01 | 2502OSPCI0003266 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 744980 | 744980 | 2025-12-17 10:01 | 2025-12-17 10:01 | 2025-12-17 10:02 | 2025 | 2026-04-30 |  | 2026-02-24 11:17 | 11 | 0 | 7249 | 0 | 12 | 120 | 471 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001726 | OSPWO0026123 | RITM0079810 |  | 2652502
JED-HRR2-SALH-13 | 2602OSPCI0000010 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 896064 | 896064 | 2026-01-04 00:50 | 2026-01-04 00:50 | 2026-01-04 00:51 | 2026 | 2026-05-31 |  | 2026-02-10 08:29 | 7 | 0 | 6313 | 0 | 15 | 143 | 257 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000020 | OSPWO0026572 | RITM0084629 |  | 2376401
JED-HRR2-SALH-06 | 2502OSPFI0002826 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 191872.45 | 191872 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025 | 2026-02-26 |  | 2026-03-09 16:03 | 11 | 0 | 0 | 0 | 0 | 135 | 148 |  | 0 | 19132 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000013 | OSPWO0023545 | RITM0074728 |  | 2376401
JED-FRDS-MANA-20 | 2502OSPCI0002973 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 747315 | 747315 | 2025-11-05 10:18 |  | 2025-11-05 10:18 | 2025 | 2026-05-30 |  | 2025-12-17 10:26 | 8 | 0 | 5404 | 0 | 13 | 74 | 174 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001858 | OSPWO0024344 | RITM0076788 |  | 2382901
JED-FRDS-MANA-10 | 2502OSPFI0002983 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 125939 | 125939 | 2025-11-05 10:15 |  | 2025-11-05 10:15 | 2025 | 2026-07-20 |  | 2025-12-17 10:34 | 8 | 0 | 0 | 0 | 0 | 65 | 163 | 0 | 0 | 9110 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001890 | OSPWO0024330 | RITM0076781 |  | 2382901
TAI-QAIM-QIAA-10 | 2602OSPCI0000009 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 885820 | 885820 | 2026-01-03 00:57 | 2026-01-03 00:57 | 2026-01-03 00:58 | 2026 | 2026-03-31 |  | 2026-02-24 11:57 | 10 | 0 | 6383 | 0 | 18 | 55 | 135 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000470 | OSPWO0026558 | RITM0084115 |  | 2656101
JED-HRR2-RIYA-38 | 2502OSPFI0003000 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 219834 | 219834 | 2025-11-05 10:40 |  | 2025-11-05 10:40 | 2025 | 2026-04-27 |  | 2025-12-17 10:40 | 8 | 0 | 0 | 0 | 0 | 59 | 290 | 0 | 0 | 13795 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000629 | OSPWO0024398 | RITM0076816 |  | 2387401
JED-HRR2-RIYA-52 | 2502OSPCI0002996 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 814566 | 814566 | 2025-11-05 10:46 |  | 2025-11-05 10:46 | 2025 | 2026-04-28 |  | 2025-12-17 10:23 | 8 | 0 | 5560 | 0 | 14 | 83 | 299 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000778 | OSPWO0024436 | RITM0076835 |  | 2387401
TAI-MELI-JUFE-04 | 2502OSPCI0003269 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 582247 | 582247 | 2025-12-17 10:39 | 2025-12-17 10:39 | 2025-12-17 10:41 | 2025 | 2026-04-30 |  | 2026-02-24 11:24 | 12 | 0 | 7390 | 0 | 12 | 120 | 420 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001729 | OSPWO0026135 | RITM0079816 |  | 2652502
JED-HRR2-RIYA-52 | 2502OSPFI0003010 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 208651 | 208651 | 2025-11-05 10:47 |  | 2025-11-05 10:47 | 2025 | 2026-05-24 |  | 2025-12-17 10:41 | 9 | 0 | 0 | 0 | 0 | 83 | 299 | 0 | 0 | 11988 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000698 | OSPWO0024438 | RITM0076836 |  | 2387401
JED-HRR2-RIYA-26 | 2502OSPFI0002993 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 186530 | 186530 | 2025-11-05 10:35 |  | 2025-11-05 10:35 | 2025 | 2026-02-25 |  | 2025-12-17 10:40 | 8 | 0 | 0 | 0 | 0 | 56 | 276 | 0 | 0 | 10462 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000658 | OSPWO0024370 | RITM0076802 |  | 2387401
JED-HRR2-RIYA-42 | 2502OSPCI0002989 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 902935 | 902935 | 2025-11-05 10:41 |  | 2025-11-05 10:41 | 2025 | 2026-03-31 |  | 2025-12-17 10:27 | 8 | 0 | 6164 | 0 | 18 | 46 | 294 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000743 | OSPWO0024408 | RITM0076821 |  | 2387401
TAI-QAIM-QIAA-08 | 2602OSPCI0000109 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1055534 | 1055534 | 2026-01-06 14:46 |  | 2026-01-06 14:46 | 2026 | 2026-03-31 |  | 2026-02-24 11:54 | 9 | 0 | 7411 | 0 | 19 | 72 | 140 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000468 | OSPWO0026991 | RITM0086051 |  | 2656101
JED-FRDS-MANA-16 | 2502OSPFI0002984 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 71468 | 71468 | 2025-11-05 10:16 |  | 2025-11-05 10:16 | 2025 | 2026-07-25 |  | 2025-12-17 10:33 | 8 | 0 | 0 | 0 | 0 | 31 | 154 | 0 | 0 | 5163 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001896 | OSPWO0024334 | RITM0076783 |  | 2382901
JED-HRR2-SALH-18 | 2602OSPFI0000143 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 223528 | 223528 | 2026-01-07 15:45 |  | 2026-01-07 15:45 | 2026 | 2026-07-30 |  | 2026-02-22 22:24 | 7 | 0 | 0 | 0 | 0 | 161 | 285 | 0 | 0 | 20347 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 17 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002486 | OSPWO0027099 | RITM0086637 |  | 2376401
JED-HRR2-RIYA-54 | 2502OSPCI0002998 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 800512 | 800512 | 2025-11-05 10:48 |  | 2025-11-05 10:48 | 2025 | 2026-04-28 |  | 2025-12-17 10:30 | 8 | 0 | 5740 | 0 | 14 | 78 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000703 | OSPWO0024444 | RITM0076839 |  | 2387401
JED-HRR2-RIYA-53 | 2502OSPFI0003011 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 160895 | 160895 | 2025-11-05 10:47 |  | 2025-11-05 10:47 | 2025 | 2026-05-23 |  | 2025-12-17 10:34 | 8 | 0 | 0 | 0 | 0 | 59 | 293 | 0 | 0 | 7998 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000659 | OSPWO0024442 | RITM0076838 |  | 2387401
SAM-SMTH-AMUD-01 | 2510OSPFI0003096 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 80211 | 80211 | 2025-11-16 10:41 |  | 2025-11-16 10:41 | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024857 | RITM0077596 |  | 8684101
JED-HRR2-RIYA-56 | 2502OSPFI0002908 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 184795 | 184795 | 2025-10-27 13:28 | 2025-10-27 13:28 | 2025-10-27 13:28 | 2025 | 2026-05-15 |  | 2025-12-18 13:35 | 8 | 0 | 0 | 0 | 0 | 75 | 274 |  | 0 | 9799 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000727 | OSPWO0023940 | RITM0076060 |  | 2387401
TAI-QAIM-QIAA-09 | 2602OSPFI0000303 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 323132 | 323132 | 2026-01-20 09:18 | 2026-01-20 09:18 | 2026-01-20 09:18 | 2026 | 2026-04-30 |  | 2026-02-24 11:56 | 10 | 0 | 0 | 0 | 0 | 111 | 503 |  | 0 | 21973 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000445 | OSPWO0028044 | RITM0088067 |  | 2656101
JED-FRDS-MANA-18 | 2502OSPCI0002971 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 755028 | 755028 | 2025-11-05 10:16 |  | 2025-11-05 10:16 | 2025 | 2026-06-28 |  | 2025-12-18 13:33 | 9 | 0 | 5453 | 0 | 13 | 62 | 178 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001856 | OSPWO0024336 | RITM0076784 |  | 2382901
TAI-QAIM-QIAA-08 | 2602OSPFI0000111 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 223585 | 223585 | 2026-01-06 14:47 |  | 2026-01-06 14:47 | 2026 | 2026-04-30 |  | 2026-02-24 11:55 | 10 | 0 | 0 | 0 | 0 | 72 | 140 | 0 | 0 | 16571 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000444 | OSPWO0026993 | RITM0086052 |  | 2656101
JED-HRR2-RIYA-28 | 2602OSPFI0000306 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 209040 | 209040 | 2026-01-20 09:35 | 2026-01-20 09:35 | 2026-01-20 09:35 | 2026 | 2026-06-30 |  | 2026-02-10 14:17 | 7 | 0 | 0 | 0 | 0 | 72 | 231 |  | 0 | 11877 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000660 | OSPWO0028063 | RITM0088077 |  | 2387401
TAI-MELI-JUBR-10 | 2502OSPCI0003265 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 600000 | 600000 | 2025-12-17 09:57 | 2025-12-17 09:57 | 2025-12-17 09:58 | 2025 | 2026-04-30 |  | 2026-02-24 10:56 | 12 | 0 | 10034 | 0 | 16 | 294 | 294 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026119 | RITM0079808 |  | 2652504
JED-HRR2-RIYA-49 | 2602OSPFI0000001 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 174131 | 174131 | 2026-01-01 11:53 | 2026-01-01 11:53 | 2026-01-01 11:53 | 2026 | 2026-03-28 |  | 2026-01-25 13:32 | 7 | 0 | 0 | 0 | 0 | 63 | 262 |  | 0 | 9920 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000638 | OSPWO0026527 | RITM0083099 |  | 2387401
JED-HRR2-SALH-13 | 2602OSPFI0000010 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 220776 | 220776 | 2026-01-04 00:51 | 2026-01-04 00:51 | 2026-01-04 00:51 | 2026 | 2026-07-29 |  | 2026-02-22 22:22 | 7 | 0 | 0 | 0 | 0 | 143 | 257 |  | 0 | 21707 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000020 | OSPWO0026574 | RITM0084628 |  | 2376401
TAI-QAIM-HASH-09 | 2602OSPCI0000107 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 105221 | 105221 | 2026-01-06 14:45 |  | 2026-01-06 14:45 | 2026 | 2026-03-31 |  | 2026-02-24 11:53 | 10 | 0 | 3947 | 0 | 7 | 20 | 83 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000558 | OSPWO0026983 | RITM0086047 |  | 2656301
JED-FRDS-MANA-19 | 2502OSPCI0002972 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 784999 | 784999 | 2025-11-05 10:17 |  | 2025-11-05 10:17 | 2025 | 2026-06-29 |  | 2025-12-18 13:33 | 8 | 0 | 5663 | 0 | 14 | 47 | 164 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001857 | OSPWO0024340 | RITM0076786 |  | 2382901
SAM-SMTH-MAJA-01 | 2510OSPCI0003077 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 1245407 | 1245407 | 2025-11-16 10:41 |  | 2025-11-16 10:41 | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 15 | 0 | 9520 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024859 | RITM0077597 |  | 8684101
JED-FRDS-MANA-10 | 2502OSPCI0002969 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 594385 | 594385 | 2025-11-05 10:15 |  | 2025-11-05 10:15 | 2025 | 2026-06-29 |  | 2025-12-18 13:32 | 8 | 0 | 4318 | 0 | 13 | 65 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001848 | OSPWO0024328 | RITM0076780 |  | 2382901
JED-HRR2-RIYA-27 | 2502OSPFI0002994 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 203152 | 203152 | 2025-11-05 10:35 |  | 2025-11-05 10:35 | 2025 | 2026-03-25 |  | 2025-12-18 13:35 | 8 | 0 | 0 | 0 | 0 | 79 | 281 | 0 | 0 | 10597 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000667 | OSPWO0024374 | RITM0076804 |  | 2387401
TAI-THVT-YASM-F1 | 2502OSPFI0003297 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 38564 | 38564 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025 | 2026-03-31 |  | 2026-02-24 12:06 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000579 | OSPWO0026117 | RITM0079807 |  | 2656201
TUR-TRBH::TUR-SECO:01 | 2502OSPCI0002589 |  | MAKKAH | CBU | Civil | 3 - Implementation | 0 |  | 2025-09-01 12:00 |  | 2025-09-01 12:03 | 2025 | 2026-04-30 |  | 2026-02-24 10:48 | 9 | 0 | 4453 | 0 | 14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022345 | RITM0072157 |  | 0 |  | Torbah PP 21.287766076248896, 41.70283329787832
JED-HRR2-RIYA-59 | 2602OSPCI0000014 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 550728 | 550728 | 2026-01-04 09:01 | 2026-01-04 09:01 | 2026-01-04 09:02 | 2026 | 2026-06-30 |  | 2026-02-10 08:29 | 8 | 0 | 3783 | 0 | 12 | 37 | 94 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000702 | OSPWO0026591 | RITM0084709 |  | 2387401
JED-HRR2-RIYA-F3 | 2502OSPCI0002860 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 214465 | 214465 | 2025-10-11 22:30 | 2025-10-11 22:30 | 2025-10-11 22:31 | 2025 | 2026-01-31 |  | 2025-12-21 20:59 | 8 | 0 | 862 | 0 | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000779 | OSPWO0023690 | RITM0075245 |  | 2387401
JED-FRDS-BUHA-28 | 2502OSPCI0003238 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 795100 | 795100 | 2025-12-16 13:12 |  | 2025-12-16 13:12 | 2025 | 2026-08-30 |  | 2026-02-22 22:23 | 7 | 0 | 5705 | 0 | 13 | 62 | 112 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002754 | OSPWO0026005 | RITM0079700 |  | 2382301
TAI-THVT-YASM-F1 | 2502OSPCI0003264 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 100436 | 100436 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025 | 2026-02-28 |  | 2026-02-24 12:05 | 10 | 0 | 875 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000560 | OSPWO0026115 | RITM0079806 |  | 2656201
JED-HRR2-RIYA-34 | 2502OSPCI0002982 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 810212 | 810212 | 2025-11-05 10:36 |  | 2025-11-05 10:36 | 2025 | 2026-02-26 |  | 2025-12-18 13:34 | 8 | 0 | 5970 | 0 | 12 | 88 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000718 | OSPWO0024380 | RITM0076807 |  | 2387401
JED-HRR2-RIYA-45 | 2502OSPCI0002992 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 758652 | 758652 | 2025-11-05 10:43 |  | 2025-11-05 10:43 | 2025 | 2026-04-30 |  | 2025-12-18 13:34 | 8 | 0 | 5369 | 0 | 14 | 54 | 297 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000642 | OSPWO0024420 | RITM0076827 |  | 2387401
JED-HRR2-SALH-18 | 2602OSPCI0000129 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 860735 | 860735 | 2026-01-07 15:44 |  | 2026-01-07 15:45 | 2026 | 2026-06-30 |  | 2026-03-10 23:02 | 15 | 0 | 5988 | 0 | 17 | 161 | 285 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002462 | OSPWO0027097 | RITM0086636 |  | 2376401 | 10/02/2026 08:25:39 - Mufleh Alsulami (Notes) update target date as agreed with project manger
JED-FRDS-MANA-07 | 2502OSPCI0002966 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 729065 | 729065 | 2025-11-05 10:13 |  | 2025-11-05 10:13 | 2025 | 2026-05-30 |  | 2025-12-18 13:28 | 8 | 0 | 5222 | 0 | 13 | 96 | 164 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001845 | OSPWO0024316 | RITM0076774 |  | 2382901
TAI-AYKB-QUDS-01 | 2502OSPFI0002769 |  | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 592193 | 448619.5 | 2025-09-28 08:32 | 2025-09-28 08:32 | 2025-09-28 08:37 | 2025 | 2026-04-30 |  | 2025-12-01 16:59 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023229 | RITM0073990 |  | 2634701
TAI-MELI-JUBR-10 | 2502OSPFI0003298 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 200000 | 200000 | 2025-12-17 09:58 | 2025-12-17 09:58 | 2025-12-17 09:58 | 2025 | 2026-05-31 |  | 2026-02-24 11:16 | 13 | 0 | 0 | 0 | 0 | 294 | 294 |  | 0 | 21064 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026121 | RITM0079809 |  | 2652504
TAI-AYKB-SAKA-01 | 2502OSPCI0002755 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 3606464.6 | 3782217.2 | 2025-09-28 08:29 | 2025-09-28 08:29 | 2025-09-28 08:37 | 2025 | 2026-04-30 |  | 2025-12-01 16:58 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023223 | RITM0073991 |  | 2634701
JED-HRR2-SALH-15 | 2602OSPCI0000015 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 759659 | 759659 | 2026-01-04 09:04 | 2026-01-04 09:04 | 2026-01-04 09:05 | 2026 | 2026-06-30 |  | 2026-03-01 13:47 | 15 | 0 | 5283 | 0 | 14 | 133 | 258 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002459 | OSPWO0026595 | RITM0084715 |  | 2376401 | 10/02/2026 08:28:45 - Mufleh Alsulami (Notes) update target date as agreed with the project manger
JED-HRR2-RIYA-34 | 2502OSPFI0002996 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 213942 | 213942 | 2025-11-05 10:37 |  | 2025-11-05 10:37 | 2025 | 2026-03-26 |  | 2025-12-18 13:35 | 8 | 0 | 0 | 0 | 0 | 88 | 298 | 0 | 0 | 11746 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000652 | OSPWO0024382 | RITM0076808 |  | 2387401
TAI-MELI-JUFE-03 | 2502OSPFI0003301 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 232355 | 232355 | 2025-12-17 10:35 | 2025-12-17 10:35 | 2025-12-17 10:36 | 2025 | 2026-05-31 |  | 2026-02-24 11:22 | 11 | 0 | 0 | 0 | 0 | 163 | 549 |  | 0 | 24233 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001769 | OSPWO0026133 | RITM0079815 |  | 2652502
JED-HRR2-RIYA-46 | 2502OSPFI0003007 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 172543 | 172543 | 2025-11-05 10:45 |  | 2025-11-05 10:45 | 2025 | 2026-05-26 |  | 2025-12-18 13:36 | 8 | 0 | 0 | 0 | 0 | 48 | 301 | 0 | 0 | 8212 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000646 | OSPWO0024426 | RITM0076830 |  | 2387401
TAI-MELI-JUFE-05 | 2502OSPCI0003270 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 2830 | 2830 | 2025-12-17 10:43 | 2025-12-17 10:43 | 2025-12-17 10:44 | 2025 | 2026-05-31 |  | 2026-02-24 11:26 | 10 | 0 | 6058 | 0 | 12 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001730 | OSPWO0026140 | RITM0079818 |  | 2652502
JED-HRR2-RIYA-39 | 2502OSPCI0002987 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 772418 | 772418 | 2025-11-05 10:40 |  | 2025-11-05 10:40 | 2025 | 2026-03-28 |  | 2025-12-18 13:34 | 8 | 0 | 5595 | 0 | 12 | 47 | 289 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000731 | OSPWO0024400 | RITM0076817 |  | 2387401
JED-FRDS-MANA-07 | 2502OSPFI0002980 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 152230 | 152230 | 2025-11-05 10:13 |  | 2025-11-05 10:13 | 2025 | 2026-06-24 |  | 2025-12-18 13:35 | 8 | 0 | 0 | 0 | 0 | 96 | 164 | 0 | 0 | 12550 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001887 | OSPWO0024318 | RITM0076775 |  | 2382901
JED-FRDS-MANA-16 | 2502OSPCI0002970 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 471431 | 471431 | 2025-11-05 10:16 |  | 2025-11-05 10:16 | 2025 | 2026-06-30 |  | 2025-12-18 13:32 | 8 | 0 | 3423 | 0 | 8 | 31 | 154 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001854 | OSPWO0024332 | RITM0076782 |  | 2382901
TAI-QAIM-HASH-09 | 2602OSPFI0000109 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 50062 | 50062 | 2026-01-06 14:45 |  | 2026-01-06 14:45 | 2026 | 2026-04-30 |  | 2026-02-24 11:53 | 10 | 0 | 0 | 0 | 0 | 20 | 83 | 0 | 0 | 3161 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000534 | OSPWO0026985 | RITM0086048 |  | 2656301
TAI-QAIM-QIAA-09 | 2602OSPCI0000261 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1091571 | 1091571 | 2026-01-20 09:17 | 2026-01-20 09:17 | 2026-01-20 09:18 | 2026 | 2026-03-31 |  | 2026-02-24 11:56 | 10 | 0 | 8104 | 0 | 18 | 111 | 503 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000469 | OSPWO0028042 | RITM0088066 |  | 2656101
JED-HRR2-SALH-07 | 2502OSPCI0002400 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 744983 | 744983 | 2025-08-14 15:49 | 2025-08-14 15:49 | 2025-08-14 15:51 | 2025 | 2025-11-29 | 2025-12-31 | 2026-03-09 16:02 | 19 | 0 | 5361 | 0 | 11 | 142 | 291 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 2502OSPCD0000014 | OSPWO0021670 | RITM0070645 |  | 2376401 | 30/09/2025 09:32:51 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-42 | 2502OSPFI0003003 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 194356 | 194356 | 2025-11-05 10:42 |  | 2025-11-05 10:42 | 2025 | 2026-04-30 |  | 2025-12-18 13:35 | 8 | 0 | 0 | 0 | 0 | 46 | 294 | 0 | 0 | 10357 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000682 | OSPWO0024410 | RITM0076822 |  | 2387401
JED-HRR2-SALH-19 | 2502OSPCI0002951 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 801709.7 | 801710 | 2025-11-04 22:04 | 2025-11-04 22:04 | 2025-11-04 22:05 | 2025 | 2026-02-28 |  | 2026-03-09 17:15 | 12 | 0 | 5721 | 0 | 15 | 107 | 147 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002463 | OSPWO0024245 | RITM0076720 |  | 2376401
JED-FRDS-BUHA-29 | 2502OSPCI0003239 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 605352 | 605352 | 2025-12-16 13:13 |  | 2025-12-16 13:13 | 2025 | 2026-08-30 |  | 2026-02-22 22:23 | 8 | 0 | 4228 | 0 | 11 | 49 | 84 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002755 | OSPWO0026009 | RITM0079702 |  | 2382301
JED-HRR2-RIYA-43 | 2502OSPFI0003004 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 173770 | 173770 | 2025-11-05 10:42 |  | 2025-11-05 10:42 | 2025 | 2026-04-30 |  | 2025-12-18 13:36 | 8 | 0 | 0 | 0 | 0 | 56 | 279 | 0 | 0 | 10286 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000710 | OSPWO0024414 | RITM0076824 |  | 2387401
JED-HRR2-RIYA-44 | 2502OSPCI0002991 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 902831 | 902831 | 2025-11-05 10:43 |  | 2025-11-05 10:43 | 2025 | 2026-04-30 |  | 2025-12-18 13:34 | 8 | 0 | 6511 | 0 | 15 | 45 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000746 | OSPWO0024416 | RITM0076825 |  | 2387401
TAI-MELI-JUFE-04 | 2502OSPFI0003302 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 177103 | 177103 | 2025-12-17 10:40 | 2025-12-17 10:40 | 2025-12-17 10:41 | 2025 | 2026-05-31 |  | 2026-02-24 11:25 | 11 | 0 | 0 | 0 | 0 | 120 | 420 |  | 0 | 19390 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001770 | OSPWO0026137 | RITM0079817 |  | 2652502
JED-HRR2-RIYA-54 | 2502OSPFI0003012 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 207626 | 207626 | 2025-11-05 10:48 |  | 2025-11-05 10:48 | 2025 | 2026-05-26 |  | 2025-12-18 13:36 | 8 | 0 | 0 | 0 | 0 | 78 | 300 | 0 | 0 | 11086 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000689 | OSPWO0024446 | RITM0076840 |  | 2387401
TAI-AYKB-QAMA-01 | 2502OSPCI0002757 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 1531196.4 | 1818336.8 | 2025-09-28 08:34 | 2025-09-28 08:34 | 2025-09-28 08:36 | 2025 | 2026-04-30 |  | 2026-02-18 11:55 | 16 | 0 | 13824 | 0 | 57 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023231 | RITM0073987 |  | 2634901
JED-HRR2-RIYA-39 | 2502OSPFI0003001 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 171209 | 171209 | 2025-11-05 10:40 |  | 2025-11-05 10:40 | 2025 | 2026-04-27 |  | 2025-12-20 17:36 | 8 | 0 | 0 | 0 | 0 | 47 | 289 | 0 | 0 | 9658 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000637 | OSPWO0024402 | RITM0076818 |  | 2387401
JED-HRR2-RIYA-23 | 2502OSPFI0003337 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 211409 | 211409 | 2025-12-22 22:52 | 2025-12-22 22:52 | 2025-12-22 22:52 | 2025 | 2026-04-30 |  | 2026-02-10 14:19 | 7 | 0 | 0 | 0 | 0 | 65 | 204 |  | 0 | 13511 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 11 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000732 | OSPWO0026341 | RITM0080200 |  | 2387401
JED-HRR2-RIYA-56 | 2502OSPCI0002899 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 710415 | 710415 | 2025-10-27 13:27 | 2025-10-27 13:27 | 2025-10-27 13:28 | 2025 | 2026-04-30 |  | 2025-12-20 17:37 | 8 | 0 | 5138 | 0 | 13 | 75 | 274 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000798 | OSPWO0023938 | RITM0076061 |  | 2387401
TAI-THVT-YASM-02 | 2502OSPCI0003213 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 683267 | 683267 | 2025-12-16 10:01 | 2025-12-16 10:01 | 2025-12-16 10:03 | 2025 | 2026-02-28 |  | 2026-02-24 12:01 | 10 | 0 | 7691 | 0 | 12 | 137 | 472 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000558 | OSPWO0025905 | RITM0079642 |  | 2656201
JED-HRR2-SALH-06 | 2502OSPCI0002825 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 731160.5 | 731161 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025 | 2026-01-31 |  | 2026-03-09 16:03 | 11 | 0 | 5240 | 0 | 11 | 135 | 148 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000013 | OSPWO0023543 | RITM0074727 |  | 2376401
JED-HRR2-RIYA-36 | 2502OSPFI0002998 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 193593 | 193593 | 2025-11-05 10:38 |  | 2025-11-05 10:38 | 2025 | 2026-04-26 |  | 2025-12-20 17:37 | 8 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 10735 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000756 | OSPWO0024390 | RITM0076812 |  | 2387401
JED-FRDS-MANA-19 | 2502OSPFI0002986 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 112532 | 112532 | 2025-11-05 10:17 |  | 2025-11-05 10:17 | 2025 | 2026-07-23 |  | 2025-12-20 17:37 | 8 | 0 | 0 | 0 | 0 | 47 | 164 | 0 | 0 | 8129 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001899 | OSPWO0024342 | RITM0076787 |  | 2382901
JED-FRDS-MANA-08 | 2502OSPFI0002981 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 106866 | 106866 | 2025-11-05 10:14 |  | 2025-11-05 10:14 | 2025 | 2026-07-23 |  | 2025-12-20 17:38 | 8 | 0 | 0 | 0 | 0 | 51 | 157 | 0 | 0 | 7523 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001888 | OSPWO0024322 | RITM0076777 |  | 2382901
JED-HRR2-SALH-16 | 2502OSPFI0002835 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 215774.45 | 215774 | 2025-10-06 10:30 | 2025-10-06 10:30 | 2025-10-06 10:31 | 2025 | 2026-03-29 |  | 2026-03-02 14:32 | 10 | 0 | 0 | 0 | 0 | 137 | 159 |  | 0 | 21047 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002484 | OSPWO0023581 | RITM0074747 |  | 2376401
JED-HRR2-RIYA-45 | 2502OSPFI0003006 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 176603 | 176603 | 2025-11-05 10:44 |  | 2025-11-05 10:44 | 2025 | 2026-05-28 |  | 2025-12-20 17:36 | 8 | 0 | 0 | 0 | 0 | 54 | 297 | 0 | 0 | 9125 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000624 | OSPWO0024422 | RITM0076828 |  | 2387401
TAI-QAIM-HASH-08 | 2602OSPCI0000106 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 400457 | 400457 | 2026-01-06 14:44 |  | 2026-01-06 14:44 | 2026 | 2026-03-31 |  | 2026-02-24 11:51 | 10 | 0 | 3155 | 0 | 6 | 62 | 310 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000557 | OSPWO0026979 | RITM0086038 |  | 2656301
JED-HRR2-SALH-14 | 2502OSPFI0003368 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 234669 | 234669 | 2025-12-31 16:11 | 2025-12-31 16:11 | 2025-12-31 16:11 | 2025 | 2026-07-29 |  | 2026-02-22 22:24 | 7 | 0 | 0 | 0 | 0 | 164 | 257 |  | 0 | 23093 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 19 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002482 | OSPWO0026487 | RITM0082469 |  | 2376401
TAI-AYKB-SAKA-01 | 2502OSPFI0002768 |  | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 712019.4 | 648267.2 | 2025-09-28 08:30 | 2025-09-28 08:30 | 2025-09-28 08:37 | 2025 | 2026-04-30 |  | 2025-12-01 16:58 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023225 | RITM0073992 |  | 2634701
TAI-MELI-JUFE-01 | 2502OSPFI0003299 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 187701 | 187701 | 2025-12-17 10:02 | 2025-12-17 10:02 | 2025-12-17 10:02 | 2025 | 2026-05-31 |  | 2026-02-24 11:18 | 11 | 0 | 0 | 0 | 0 | 120 | 471 |  | 0 | 19345 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001767 | OSPWO0026125 | RITM0079811 |  | 2652502
JED-HRR2-RIYA-28 | 2602OSPCI0000267 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 786977 | 786977 | 2026-01-20 09:34 | 2026-01-20 09:34 | 2026-01-20 09:35 | 2026 | 2026-05-31 |  | 2026-02-10 08:24 | 7 | 0 | 5890 | 0 | 12 | 72 | 231 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000707 | OSPWO0028061 | RITM0088076 |  | 2387401
JED-HRR2-RIYA-41 | 2502OSPCI0002896 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1020256 | 1020256 | 2025-10-27 13:19 | 2025-10-27 13:19 | 2025-10-27 13:23 | 2025 | 2026-03-29 |  | 2025-12-21 20:59 | 8 | 0 | 7394 | 0 | 16 | 65 | 284 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000786 | OSPWO0023926 | RITM0076051 |  | 2387401
JED-HRR2-RIYA-29 | 2502OSPFI0002995 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 209866 | 209866 | 2025-11-05 10:36 |  | 2025-11-05 10:36 | 2025 | 2026-03-29 |  | 2025-12-21 21:01 | 8 | 0 | 0 | 0 | 0 | 94 | 302 | 0 | 0 | 11396 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000653 | OSPWO0024378 | RITM0076806 |  | 2387401
JED-HRR2-RIYA-46 | 2502OSPCI0002993 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 798422 | 798422 | 2025-11-05 10:44 |  | 2025-11-05 10:44 | 2025 | 2026-04-30 |  | 2025-12-21 21:00 | 8 | 0 | 5824 | 0 | 16 | 48 | 301 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000664 | OSPWO0024424 | RITM0076829 |  | 2387401
JED-HRR2-RIYA-25 | 2502OSPFI0002992 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 190265 | 190265 | 2025-11-05 10:34 |  | 2025-11-05 10:34 | 2025 | 2026-02-25 |  | 2026-03-01 14:13 | 9 | 0 | 0 | 0 | 0 | 84 | 257 | 0 | 0 | 10462 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000627 | OSPWO0024366 | RITM0076800 |  | 2387401
TAI-QAIM-HASH-F4 | 2602OSPFI0000110 |  | MAKKAH | FTTH | Fiber | 2 - PIP Approval | 24533 | 24533 | 2026-01-06 14:46 |  | 2026-01-06 14:46 | 2026 |  |  | 2026-02-24 12:11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000535 | OSPWO0026989 | RITM0086050 |  | 2656301
JED-HRR2-RIYA-41 | 2502OSPFI0002905 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 216927 | 216927 | 2025-10-27 13:19 | 2025-10-27 13:19 | 2025-10-27 13:23 | 2025 | 2026-04-30 |  | 2025-12-24 17:08 | 8 | 0 | 0 | 0 | 0 | 65 | 284 |  | 0 | 14591 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000772 | OSPWO0023928 | RITM0076052 |  | 2387401
JED-HRR2-SALH-15 | 2602OSPFI0000016 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 197912 | 197912 | 2026-01-04 09:05 | 2026-01-04 09:05 | 2026-01-04 09:05 | 2026 | 2026-07-30 |  | 2026-03-01 13:47 | 9 | 0 | 0 | 0 | 0 | 133 | 258 |  | 0 | 18633 | 0 | 133 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002483 | OSPWO0026597 | RITM0084714 |  | 2376401
TAI-QAIM-QIAA-10 | 2602OSPFI0000009 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 229673 | 229673 | 2026-01-03 00:58 | 2026-01-03 00:58 | 2026-01-03 00:58 | 2026 | 2026-04-30 |  | 2026-02-24 11:58 | 9 | 0 | 0 | 0 | 0 | 55 | 135 |  | 0 | 16159 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000446 | OSPWO0026560 | RITM0084116 |  | 2656101
JED-HRR2-RIYA-43 | 2502OSPCI0002990 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 778031 | 778031 | 2025-11-05 10:42 |  | 2025-11-05 10:42 | 2025 | 2026-03-31 |  | 2025-12-21 21:00 | 8 | 0 | 5766 | 0 | 12 | 56 | 279 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000753 | OSPWO0024412 | RITM0076823 |  | 2387401
JED-FRDS-MANA-05 | 2502OSPCI0002964 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 729090 | 729090 | 2025-11-05 10:11 |  | 2025-11-05 10:11 | 2025 | 2026-05-30 |  | 2025-12-21 21:00 | 8 | 0 | 4679 | 0 | 14 | 82 | 161 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001843 | OSPWO0024308 | RITM0076770 |  | 2382901
JED-FRDS-BUHA-F2 | 2502OSPCI0003241 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 254819 | 254819 | 2025-12-16 13:15 |  | 2025-12-16 13:15 | 2025 | 2026-07-30 |  | 2026-02-22 22:25 | 7 | 0 | 1176 | 0 | 5 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002758 | OSPWO0026017 | RITM0079706 |  | 2382301
TUR-TRBH::TUR-SECO:01 | 2502OSPFI0002599 |  | MAKKAH | CBU | Fiber | 3 - Implementation | 0 |  | 2025-09-01 12:00 |  | 2025-09-01 12:04 | 2025 | 2026-04-30 |  | 2026-02-24 10:48 | 9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4455 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022347 | RITM0072158 |  | 0 |  | Torbah PP 21.287766076248896, 41.70283329787832

## District
Link Code | Work Order | Region | City | District
JED-HRR2-SALH-04 | 2502OSPFI0002425 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-63 | 2502OSPCI0002401 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-60 | 2502OSPFI0002428 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-71 | 2502OSPFI0002431 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-64 | 2502OSPFI0002429 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-63 | 2502OSPFI0002437 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-69 | 2502OSPFI0002440 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-67 | 2502OSPFI0002441 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-49 | 2602OSPCI0000001 | Western | Jeddah | Riyadh
SHU-AZRQ-JORI-01 | 2510OSPCI0002892 | Southern | Jizan | ASH-SHUQAYRI
JED-HRR2-SALH-11 | 2502OSPCI0002952 | Western | Jeddah | Salhiya
SHU-AZRQ-JORI-01 | 2510OSPFI0002901 | Southern | Jizan | ASH-SHUQAYRI
JED-HRR2-SALH-03 | 2502OSPCI0002389 | Western | Jeddah | Salhiya
JED-HRR2-RAHA-18 | 2502OSPCI0003104 | Western | Jeddah | Rahmaniya
JED-HRR2-RIYA-38 | 2502OSPCI0002861 | Western | Jeddah | Riyadh
JED-HRR2-SALH-05 | 2502OSPCI0002391 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-F6 | 2502OSPFI0002488 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-60 | 2502OSPCI0002392 | Western | Jeddah | Riyadh
JED-HRR2-SALH-02 | 2502OSPFI0002415 | Western | Jeddah | Salhiya
JED-HRR2-SALH-02 | 2502OSPCI0002388 | Western | Jeddah | Salhiya
MOY-MOYH-KHAL-01 | 2502OSPFI0002445 | Western | Taif | MOYH
JED-HRR2-RIYA-66 | 2502OSPFI0002438 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-64 | 2502OSPCI0002393 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-67 | 2502OSPCI0002405 | Western | Jeddah | Riyadh
JED-HRR2-SALH-10 | 2502OSPCI0002823 | Western | Jeddah | Salhiya
SHU-AZRQ-SHUQ-01 | 2510OSPCI0002893 | Southern | Jizan | ASH-SHUQAYRI
JED-HRR2-RIYA-68 | 2502OSPCI0002403 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-35 | 2502OSPCI0002983 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-47 | 2502OSPCI0002994 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-26 | 2502OSPCI0002979 | Western | Jeddah | Riyadh
JED-HRR2-SALH-09 | 2502OSPFI0002954 | Western | Jeddah | Salhiya
JED-HRR2-SALH-12 | 2502OSPFI0002839 | Western | Jeddah | Salhiya
JED-HRR2-SALH-08 | 2502OSPFI0002822 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-66 | 2502OSPCI0002402 | Western | Jeddah | Riyadh
SAM-SMTH-KHAD-01 | 2510OSPCI0003073 | Southern | Jizan | SAMTA
JED-HRR2-SALH-08 | 2502OSPCI0002821 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-25 | 2502OSPCI0002978 | Western | Jeddah | Riyadh
SHU-AZRQ-SHUQ-01 | 2510OSPFI0002902 | Southern | Jizan | ASH-SHUQAYRI
JED-HRR2-RIYA-24 | 2502OSPCI0002977 | Western | Jeddah | Riyadh
TAI-AYKB-QAMA-01 | 2502OSPFI0002770 | Western | Taif | N/A
JED-HRR2-RIYA-23 | 2502OSPCI0003303 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-69 | 2502OSPCI0002404 | Western | Jeddah | Riyadh
JED-HRR2-SALH-09 | 2502OSPCI0002941 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-37 | 2502OSPCI0002985 | Western | Jeddah | Riyadh
JED-HRR2-SALH-04 | 2502OSPCI0002390 | Western | Jeddah | Salhiya
MOY-MOYH-KHAL-01 | 2502OSPCI0002409 | Western | Taif | MOYH
JED-HRR2-RIYA-68 | 2502OSPFI0002439 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-65 | 2502OSPCI0002695 | Western | Jeddah | Riyadh
JED-HRR2-SALH-12 | 2502OSPCI0002838 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-70 | 2502OSPCI0002394 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-71 | 2502OSPCI0002395 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-65 | 2502OSPFI0002703 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-70 | 2502OSPFI0002430 | Western | Jeddah | Riyadh
JED-HRR2-SALH-10 | 2502OSPFI0002824 | Western | Jeddah | Salhiya
JED-HRR2-SALH-05 | 2502OSPFI0002426 | Western | Jeddah | Salhiya
TAB-TBK5-MASY-02 | 2607OSPFI0000135 | Western | Tabuk | N/A
TAB-TBK5-MASY-04 | 2607OSPFI0000137 | Western | Tabuk | N/A
TAB-TBK5-MASY-03 | 2607OSPFI0000136 | Western | Tabuk | N/A
JED-HRR2-SALH-03 | 2502OSPFI0002424 | Western | Jeddah | Salhiya
JED-HRR2-SALH-16 | 2502OSPCI0002834 | Western | Jeddah | Salhiya
JED-HRR2-SALH-17 | 2502OSPCI0002832 | Western | Jeddah | Salhiya
JED-HRR2-SALH-14 | 2502OSPCI0003326 | Western | Jeddah | Salhiya
JED-HRR2-SALH-11 | 2502OSPFI0002965 | Western | Jeddah | Salhiya
JED-HRR2-SALH-F2 | 2502OSPFI0002427 | Western | Jeddah | Salhiya
EDA-AYBN-EDAB-01 | 2510OSPCI0002891 | Southern | Jizan | AL-EDABI
DAI-ADAR-DAIR-01 | 2510OSPCI0003072 | Southern | Jizan | DAIR
DAI-ADAR-DAIR-01 | 2510OSPFI0003092 | Southern | Jizan | DAIR
JED-HRR2-RIYA-53 | 2502OSPCA0002838 | Western | Jeddah | Riyadh
TAI-MELI-FIYS-02 | 2602OSPCA0000105 | Western | Taif | N/A
SAM-SMTH-MASO-01 | 2510OSPCA0002916 | Southern | Jizan | SAMTA
JED-HRR2-WAFA-05 | 2602OSPFI0000682 | Western | Jeddah | N/A
JED-HRR2-RIYA-35 | 2502OSPFA0002975 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-24 | 2502OSPCA0002818 | Western | Jeddah | Riyadh
TAI-QRAU-SABA-05 | 2602OSPFI0000626 | Western | Taif | N/A
TAI-MELI-FIYS-01 | 2602OSPFI0000446 | Western | Taif | N/A
TAI-QRAU-MUAS-01 | 2602OSPCA0000112 | Western | Taif | N/A
JED-FRDS-MANA-17 | 2602OSPCA0000117 | Western | Jeddah | N/A
SAM-SMTH-AMUD-01 | 2510OSPFA0003074 | Southern | Jizan | SAMTA
JED-HRR2-WAFA-87 | 2602OSPCA0000466 | Western | Jeddah | N/A
BAH-BCPS-RADW-01 | 2612OSPCA0000220 | Southern | Baha | N/A
SAM-SMTH-AMUD-01 | 2510OSPCA0002917 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-23 | 2602OSPCI0000399 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-11 | 2602OSPFA0000441 | Western | Taif | N/A
TAI-QRAU-MUAS-01 | 2602OSPCI0000112 | Western | Taif | N/A
SAM-SMTH-TURS-01 | 2510OSPCA0002915 | Southern | Jizan | SAMTA
BAH-BCPS-ADEL-01 | 2612OSPFI0000245 | Southern | Baha | N/A
JED-HRR2-RIYA-29 | 2502OSPCA0002822 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-55 | 2502OSPCA0002840 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-06 | 2602OSPFI0000652 | Western | Jeddah | N/A
JED-FRDS-BUHA-26 | 2502OSPCA0003077 | Western | Jeddah | N/A
JED-HRR2-WAFA-14 | 2602OSPFI0000653 | Western | Jeddah | N/A
JED-HRR2-RIYA-44 | 2502OSPFA0002983 | Western | Jeddah | Riyadh
TAI-QRAU-SABA-02 | 2602OSPFI0000623 | Western | Taif | N/A
JED-HRR2-WAFA-85 | 2602OSPFI0000513 | Western | Jeddah | N/A
JED-HRR2-WAFA-19 | 2602OSPCI0000639 | Western | Jeddah | N/A
JED-HRR2-WAFA-27 | 2602OSPCI0000644 | Western | Jeddah | N/A
BAH-BCPS-NAIM-01 | 2612OSPFA0000250 | Southern | Baha | N/A
JED-HRR2-WAFA-07 | 2602OSPFI0000683 | Western | Jeddah | N/A
JED-FRDS-BUHA-25 | 2502OSPCA0003076 | Western | Jeddah | N/A
JED-FRDS-MANA-09 | 2502OSPCA0002809 | Western | Jeddah | N/A
JED-FRDS-MANA-09 | 2502OSPFA0002960 | Western | Jeddah | N/A
JED-HRR2-RIYA-24 | 2502OSPFA0002969 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-98 | 2602OSPCI0000472 | Western | Jeddah | N/A
JED-HRR2-WAFA-24 | 2602OSPCI0000642 | Western | Jeddah | N/A
SAM-SMTH-MAJA-01 | 2510OSPFA0003075 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-55 | 2502OSPFA0002991 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-28 | 2602OSPCI0000645 | Western | Jeddah | N/A
JED-HRR2-WAFA-101 | 2602OSPFI0000508 | Western | Jeddah | N/A
TAI-QAIM-HASH-F4 | 2602OSPCA0000108 | Western | Taif | N/A
TAI-MELI-JUBR-10 | 2602OSPCI0000352 | Western | Taif | N/A
JED-HRR2-WAFA-99 | 2602OSPFA0000522 | Western | Jeddah | N/A
JED-HRR2-WAFA-57 | 2602OSPCI0000650 | Western | Jeddah | N/A
JED-HRR2-WAFA-89 | 2602OSPFI0000517 | Western | Jeddah | N/A
JED-HRR2-WAFA-91 | 2602OSPFI0000519 | Western | Jeddah | N/A
JED-HRR2-RIYA-47 | 2502OSPFA0002986 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-79 | 2602OSPFI0000510 | Western | Jeddah | N/A
JED-HRR2-RIYA-64 | 2602OSPCA0000332 | Western | Jeddah | Riyadh
BAH-BCPS-SARA-01 | 2612OSPFI0000244 | Southern | Baha | N/A
BAH-BCPS-ADEL-01 | 2612OSPCA0000218 | Southern | Baha | N/A
| 2602OSPOF0000021 | Western | N/A | N/A
JED-HRR2-RIYA-37 | 2502OSPFA0002977 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-64 | 2602OSPFA0000382 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-70 | 2602OSPCI0000390 | Western | Jeddah | Riyadh
BAH-BCPS-GHAD-01 | 2612OSPFA0000247 | Southern | Baha | N/A
BAH-BCPS-AREE-01 | 2612OSPCI0000221 | Southern | Baha | N/A
BAH-BCPS-BADR-01 | 2612OSPCI0000224 | Southern | Baha | N/A
JED-HRR2-RIYA-70 | 2602OSPCA0000390 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-90 | 2602OSPCI0000469 | Western | Jeddah | N/A
TAI-QRAU-SABA-02 | 2602OSPCI0000570 | Western | Taif | N/A
JED-HRR2-WAFA-84 | 2602OSPCI0000463 | Western | Jeddah | N/A
JED-HRR2-RIYA-23 | 2602OSPFI0000449 | Western | Jeddah | Riyadh
| 2602OSPOF0000022 | Western | N/A | N/A
JED-HRR2-WAFA-10 | 2602OSPFI0000685 | Western | Jeddah | N/A
TAI-MELI-JUBR-10 | 2602OSPFI0000402 | Western | Taif | N/A
TAB-TBK5-MASY-F1 | 2607OSPFA0000138 | Western | Tabuk | N/A
JED-HRR2-WAFA-85 | 2602OSPCI0000464 | Western | Jeddah | N/A
JED-HRR2-WAFA-85 | 2602OSPCA0000464 | Western | Jeddah | N/A
JED-HRR2-RIYA-38 | 2502OSPCI0002986 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-16 | 2602OSPCI0000636 | Western | Jeddah | N/A
JED-HRR2-WAFA-173 | 2602OSPFI0000648 | Western | Jeddah | N/A
JED-HRR2-RIYA-64 | 2602OSPFI0000382 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-145 | 2602OSPFI0000647 | Western | Jeddah | N/A
JED-HRR2-WAFA-160 | 2602OSPFI0000645 | Western | Jeddah | N/A
JED-HRR2-WAFA-22 | 2602OSPCI0000602 | Western | Jeddah | N/A
JED-FRDS-BUHA-24 | 2502OSPCA0003075 | Western | Jeddah | N/A
JED-HRR2-WAFA-57 | 2602OSPFI0000701 | Western | Jeddah | N/A
JED-HRR2-WAFA-15 | 2602OSPCI0000635 | Western | Jeddah | N/A
BAH-BCPS-RADW-01 | 2612OSPFA0000246 | Southern | Baha | N/A
JED-HRR2-RIYA-56 | 2602OSPCA0000395 | Western | Jeddah | Riyadh
JED-FRDS-MANA-07 | 2502OSPFA0002958 | Western | Jeddah | N/A
JED-HRR2-WAFA-16 | 2602OSPOI0000001 | Western | Jeddah | N/A
JED-HRR2-WAFA-84 | 2602OSPFI0000512 | Western | Jeddah | N/A
TAB-TBK5-MASY-03 | 2607OSPFA0000136 | Western | Tabuk | N/A
JED-HRR2-RIYA-57 | 2602OSPCA0000118 | Western | Jeddah | Riyadh
JUB-DHAH-AZIZ-16 | 2605OSPFI0000020 | Eastern | Jubail | N/A
JED-FRDS-MANA-21 | 2502OSPCA0002815 | Western | Jeddah | N/A
BAH-BCPS-MASA-01 | 2612OSPCI0000216 | Southern | Baha | N/A
JED-HRR2-RIYA-47 | 2502OSPCA0002835 | Western | Jeddah | Riyadh
| 2502OSPOF0000415 | Western | N/A | N/A
TAI-MELI-FIYS-01 | 2602OSPFA0000106 | Western | Taif | N/A
JED-HRR2-RIYA-42 | 2502OSPFA0002981 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-23 | 2602OSPCI0000234 | Western | Jeddah | Riyadh
TAI-QAIM-HASH-08 | 2602OSPFA0000108 | Western | Taif | N/A
BAH-BCPS-BADR-01 | 2612OSPCA0000224 | Southern | Baha | N/A
JED-HRR2-WAFA-17 | 2602OSPCI0000637 | Western | Jeddah | N/A
BAH-BCPS-NAIM-01 | 2612OSPCA0000223 | Southern | Baha | N/A
JED-HRR2-FURO-29 | 2602OSPCI0000458 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPFI0000442 | Western | Taif | N/A
BAH-BCPS-RADW-01 | 2612OSPCI0000220 | Southern | Baha | N/A
JED-FRDS-BUHA-23 | 2502OSPFA0003242 | Western | Jeddah | N/A
JED-HRR2-WAFA-51 | 2602OSPCI0000648 | Western | Jeddah | N/A
JED-HRR2-WAFA-19 | 2602OSPFI0000690 | Western | Jeddah | N/A
JED-HRR2-SALH-08 | 2602OSPFI0000447 | Western | Jeddah | Salhiya
JED-HRR2-WAFA-80 | 2602OSPCI0000462 | Western | Jeddah | N/A
JED-HRR2-WAFA-80 | 2602OSPCA0000462 | Western | Jeddah | N/A
JED-FRDS-MANA-08 | 2502OSPCA0002808 | Western | Jeddah | N/A
JED-FRDS-MANA-16 | 2502OSPFA0002962 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2602OSPCI0000398 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-42 | 2602OSPCI0000647 | Western | Jeddah | N/A
JED-HRR2-WAFA-18 | 2602OSPFI0000689 | Western | Jeddah | N/A
JED-FRDS-MANA-18 | 2502OSPFA0002963 | Western | Jeddah | N/A
BAH-BCPS-AREE-01 | 2612OSPFA0000249 | Southern | Baha | N/A
JED-FRDS-AMWA-11 | 2602OSPFI0000704 | Western | Jeddah | N/A
TAI-QAIM-QIAA-F2 | 2602OSPFA0000113 | Western | Taif | N/A
TAI-MELI-JALL-01 | 2602OSPCI0000606 | Western | Taif | N/A
JED-HRR2-WAFA-87 | 2602OSPCI0000466 | Western | Jeddah | N/A
TAB-TBK5-MASY-04 | 2607OSPFA0000137 | Western | Tabuk | N/A
JED-FRDS-MANA-21 | 2502OSPFA0002966 | Western | Jeddah | N/A
JED-FRDS-MANA-22 | 2502OSPCA0002816 | Western | Jeddah | N/A
JED-FRDS-BUHA-23 | 2502OSPFI0003264 | Western | Jeddah | N/A
JED-HRR2-WAFA-170 | 2602OSPFI0000651 | Western | Jeddah | N/A
SAM-SMTH-TURS-01 | 2510OSPFA0003072 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-27 | 2502OSPCA0002821 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-43 | 2502OSPFA0002982 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-11 | 2602OSPCI0000604 | Western | Jeddah | N/A
JED-HRR2-WAFA-137 | 2602OSPFI0000509 | Western | Jeddah | N/A
JED-HRR2-WAFA-05 | 2602OSPCI0000630 | Western | Jeddah | N/A
JED-HRR2-RIYA-36 | 2502OSPCA0002825 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-56 | 2602OSPFI0000445 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-78 | 2602OSPFI0000702 | Western | Jeddah | N/A
JED-FRDS-BUHA-29 | 2502OSPFA0003248 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPCA0000392 | Western | Taif | N/A
JED-HRR2-WAFA-86 | 2602OSPCA0000465 | Western | Jeddah | N/A
JED-FRDS-BUHA-23 | 2502OSPCA0003074 | Western | Jeddah | N/A
TAI-QRAU-MUAS-01 | 2602OSPFI0000121 | Western | Taif | N/A
JED-FRDS-BUHA-30 | 2502OSPCA0003081 | Western | Jeddah | N/A
JED-HRR2-WAFA-92 | 2602OSPFI0000520 | Western | Jeddah | N/A
JED-HRR2-WAFA-91 | 2602OSPCA0000470 | Western | Jeddah | N/A
JED-HRR2-WAFA-07 | 2602OSPCI0000631 | Western | Jeddah | N/A
JED-HRR2-WAFA-137 | 2602OSPCI0000460 | Western | Jeddah | N/A
JED-HRR2-WAFA-92 | 2602OSPCI0000471 | Western | Jeddah | N/A
TAI-QAIM-QIAA-10 | 2602OSPCI0000393 | Western | Taif | N/A
JED-HRR2-WAFA-78 | 2602OSPCI0000651 | Western | Jeddah | N/A
TAI-MELI-FIYS-01 | 2602OSPFA0000446 | Western | Taif | N/A
SAM-SMTH-KHAD-01 | 2510OSPFA0003071 | Southern | Jizan | SAMTA
JED-FRDS-BUHA-29 | 2502OSPFI0003270 | Western | Jeddah | N/A
JED-HRR2-RIYA-70 | 2602OSPFA0000440 | Western | Jeddah | Riyadh
BAH-BCPS-BADR-01 | 2612OSPFA0000251 | Southern | Baha | N/A
TAI-QRAU-MUAS-01 | 2602OSPFA0000121 | Western | Taif | N/A
JED-HRR2-WAFA-89 | 2602OSPCA0000468 | Western | Jeddah | N/A
BAH-BCPS-NAIM-01 | 2612OSPFI0000250 | Southern | Baha | N/A
JED-FRDS-BUHA-27 | 2502OSPCA0003078 | Western | Jeddah | N/A
JED-HRR2-WAFA-90 | 2602OSPFI0000518 | Western | Jeddah | N/A
JED-FRDS-MANA-22 | 2502OSPFA0002967 | Western | Jeddah | N/A
TAI-QAIM-QIAA-F2 | 2602OSPCA0000111 | Western | Taif | N/A
JED-HRR2-RIYA-50 | 2502OSPFA0002987 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-F3 | 2502OSPFA0002993 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-15 | 2602OSPFI0000687 | Western | Jeddah | N/A
JED-HRR2-WAFA-99 | 2602OSPCA0000473 | Western | Jeddah | N/A
JED-HRR2-WAFA-54 | 2602OSPFI0000663 | Western | Jeddah | N/A
JED-HRR2-WAFA-23 | 2602OSPCI0000641 | Western | Jeddah | N/A
JED-HRR2-RIYA-65 | 2502OSPCA0002547 | Western | Jeddah | Riyadh
JED-FRDS-MANA-20 | 2502OSPCA0002814 | Western | Jeddah | N/A
JED-HRR2-WAFA-88 | 2602OSPFI0000516 | Western | Jeddah | N/A
JED-HRR2-WAFA-88 | 2602OSPFA0000516 | Western | Jeddah | N/A
JED-FRDS-MANA-10 | 2502OSPFA0002961 | Western | Jeddah | N/A
JED-HRR2-WAFA-84 | 2602OSPCA0000463 | Western | Jeddah | N/A
BAH-BCPS-ADEL-01 | 2612OSPCI0000218 | Southern | Baha | N/A
JED-FRDS-MANA-F1 | 2502OSPCA0002817 | Western | Jeddah | N/A
JED-HRR2-WAFA-141 | 2602OSPFI0000646 | Western | Jeddah | N/A
JED-FRDS-MANA-20 | 2502OSPFA0002965 | Western | Jeddah | N/A
BAH-BCPS-GHAD-01 | 2612OSPFI0000247 | Southern | Baha | N/A
JED-HRR2-RIYA-50 | 2502OSPCA0002836 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-F6 | 2502OSPCI0002485 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-80 | 2602OSPFA0000511 | Western | Jeddah | N/A
JED-FRDS-BUHA-25 | 2502OSPFA0003244 | Western | Jeddah | N/A
JED-HRR2-WAFA-141 | 2602OSPCI0000593 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPCA0000109 | Western | Taif | N/A
JED-HRR2-RIYA-65 | 2502OSPFA0002680 | Western | Jeddah | Riyadh
JED-FRDS-MANA-05 | 2502OSPCA0002805 | Western | Jeddah | N/A
JED-HRR2-WAFA-84 | 2602OSPFA0000512 | Western | Jeddah | N/A
JED-HRR2-RIYA-35 | 2502OSPCA0002824 | Western | Jeddah | Riyadh
TAI-MELI-JALL-01 | 2602OSPFI0000658 | Western | Taif | N/A
JED-HRR2-RIYA-26 | 2502OSPCA0002820 | Western | Jeddah | Riyadh
JED-HRR2-SALH-18 | 2602OSPFA0000143 | Western | Jeddah | Salhiya
JED-HRR2-WAFA-145 | 2602OSPCI0000594 | Western | Jeddah | N/A
TAI-MELI-FIYS-02 | 2602OSPFI0000107 | Western | Taif | N/A
JED-FRDS-BUHA-25 | 2502OSPFI0003266 | Western | Jeddah | N/A
TAB-TBHH-MASY-01 | 2607OSPFA0000134 | Western | Tabuk | N/A
JED-HRR2-WAFA-53 | 2602OSPFI0000650 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2602OSPFI0000448 | Western | Jeddah | Riyadh
BAH-BCPS-SARA-01 | 2612OSPCA0000217 | Southern | Baha | N/A
| 2602OSPOF0000015 | Western | N/A | N/A
JED-HRR2-WAFA-98 | 2602OSPFI0000521 | Western | Jeddah | N/A
JED-HRR2-WAFA-18 | 2602OSPCI0000638 | Western | Jeddah | N/A
JED-HRR2-RIYA-52 | 2502OSPCA0002837 | Western | Jeddah | Riyadh
BAH-BCPS-RADW-01 | 2612OSPFI0000246 | Southern | Baha | N/A
JED-HRR2-RIYA-52 | 2502OSPFA0002988 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-26 | 2502OSPFA0002971 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-88 | 2602OSPCA0000467 | Western | Jeddah | N/A
JED-HRR2-WAFA-53 | 2602OSPCI0000597 | Western | Jeddah | N/A
JED-HRR2-WAFA-170 | 2602OSPCI0000599 | Western | Jeddah | N/A
JED-HRR2-RIYA-42 | 2502OSPCA0002830 | Western | Jeddah | Riyadh
TAI-MELI-FIYS-02 | 2602OSPFA0000107 | Western | Taif | N/A
JED-HRR2-SALH-08 | 2602OSPCI0000397 | Western | Jeddah | Salhiya
TAI-MELI-FIYS-02 | 2602OSPCI0000105 | Western | Taif | N/A
JED-HRR2-RIYA-53 | 2502OSPFA0002989 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-160 | 2602OSPCI0000592 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPFA0000442 | Western | Taif | N/A
JED-FRDS-BUHA-22 | 2502OSPCA0003073 | Western | Jeddah | N/A
JED-HRR2-SALH-08 | 2602OSPFA0000447 | Western | Jeddah | Salhiya
BAH-BCPS-ARIF-01 | 2612OSPFA0000248 | Southern | Baha | N/A
JED-HRR2-WAFA-79 | 2602OSPCI0000461 | Western | Jeddah | N/A
JED-HRR2-WAFA-14 | 2602OSPCI0000601 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2602OSPCA0000398 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-20 | 2602OSPCI0000640 | Western | Jeddah | N/A
SAM-SMTH-MASO-01 | 2510OSPFA0003073 | Southern | Jizan | SAMTA
JED-FRDS-MANA-18 | 2502OSPCA0002812 | Western | Jeddah | N/A
JED-HRR2-WAFA-53 | 2602OSPCI0000598 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPFA0000111 | Western | Taif | N/A
BAH-BCPS-MASA-01 | 2612OSPFA0000243 | Southern | Baha | N/A
BAH-BCPS-NAIM-01 | 2612OSPCI0000223 | Southern | Baha | N/A
JED-HRR2-WAFA-02 | 2602OSPFI0000655 | Western | Jeddah | N/A
JED-HRR2-RIYA-57 | 2602OSPFA0000127 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-09 | 2602OSPCA0000394 | Western | Taif | N/A
JED-HRR2-RIYA-54 | 2502OSPCA0002839 | Western | Jeddah | Riyadh
BAH-BCPS-AREE-01 | 2612OSPFI0000249 | Southern | Baha | N/A
JED-HRR2-RIYA-56 | 2602OSPFA0000445 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-54 | 2602OSPCI0000611 | Western | Jeddah | N/A
SHA-ADAR-DAIR-01 | 2510OSPFA0003070 | Southern | Jizan | DAIR
JED-FRDS-MANA-17 | 2602OSPFA0000126 | Western | Jeddah | N/A
MAK-WHD2-QASA-15 | 2602OSPCA0000131 | Western | Makkah | N/A
TAI-QAIM-HASH-09 | 2602OSPCA0000107 | Western | Taif | N/A
JED-FRDS-MANA-06 | 2502OSPCA0002806 | Western | Jeddah | N/A
JED-FRDS-MANA-19 | 2502OSPCA0002813 | Western | Jeddah | N/A
BAH-BCPS-BADR-01 | 2612OSPFI0000251 | Southern | Baha | N/A
TAI-QRAU-SABA-03 | 2602OSPCI0000571 | Western | Taif | N/A
JED-HRR2-WAFA-98 | 2602OSPCA0000472 | Western | Jeddah | N/A
SAM-SMTH-MAJA-01 | 2510OSPCA0002918 | Southern | Jizan | SAMTA
SAM-SMTH-KHAD-01 | 2510OSPCA0002914 | Southern | Jizan | SAMTA
JED-FRDS-MANA-10 | 2502OSPCA0002810 | Western | Jeddah | N/A
JED-HRR2-WAFA-22 | 2602OSPFI0000654 | Western | Jeddah | N/A
BAH-BCPS-GHAD-01 | 2612OSPCA0000219 | Southern | Baha | N/A
JED-HRR2-RIYA-27 | 2502OSPFA0002972 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-10 | 2602OSPCA0000393 | Western | Taif | N/A
JED-HRR2-WAFA-89 | 2602OSPFA0000517 | Western | Jeddah | N/A
| 2502OSPOF0000407 | Western | N/A | N/A
JED-HRR2-WAFA-87 | 2602OSPFI0000515 | Western | Jeddah | N/A
MAK-WHD2-QASA-15 | 2602OSPCI0000131 | Western | Makkah | N/A
TAI-MELI-JUBR-10 | 2602OSPCA0000352 | Western | Taif | N/A
JED-HRR2-WAFA-99 | 2602OSPFI0000522 | Western | Jeddah | N/A
JED-FRDS-BUHA-24 | 2502OSPFI0003265 | Western | Jeddah | N/A
TAI-QAIM-QIAA-11 | 2602OSPCA0000391 | Western | Taif | N/A
TAI-MELI-JUFE-04 | 2602OSPFI0000450 | Western | Taif | N/A
TAI-QAIM-QIAA-08 | 2602OSPCI0000392 | Western | Taif | N/A
SHA-ADAR-DAIR-01 | 2510OSPCA0002913 | Southern | Jizan | DAIR
TAI-MELI-FIYS-01 | 2602OSPCI0000104 | Western | Taif | N/A
JED-HRR2-WAFA-10 | 2602OSPCI0000633 | Western | Jeddah | N/A
JED-HRR2-RIYA-23 | 2602OSPFA0000271 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-34 | 2502OSPCA0002823 | Western | Jeddah | Riyadh
JED-HRR2-TEEB-11 | 2602OSPFI0000405 | Western | Jeddah | N/A
JED-HRR2-WAFA-52 | 2602OSPFI0000700 | Western | Jeddah | N/A
JED-FRDS-BUHA-30 | 2502OSPFI0003271 | Western | Jeddah | N/A
JED-HRR2-WAFA-90 | 2602OSPCA0000469 | Western | Jeddah | N/A
JED-HRR2-RIYA-38 | 2502OSPCA0002827 | Western | Jeddah | Riyadh
JED-FRDS-AMWA-11 | 2602OSPCI0000652 | Western | Jeddah | N/A
JED-FRDS-BUHA-24 | 2502OSPFA0003243 | Western | Jeddah | N/A
JED-HRR2-WAFA-20 | 2602OSPFI0000691 | Western | Jeddah | N/A
JED-HRR2-WAFA-101 | 2602OSPCI0000459 | Western | Jeddah | N/A
JED-HRR2-RIYA-45 | 2502OSPCA0002833 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-25 | 2502OSPCA0002819 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-09 | 2602OSPFA0000444 | Western | Taif | N/A
JED-FRDS-BUHA-F2 | 2502OSPFI0003272 | Western | Jeddah | N/A
TAI-MELI-FIYS-01 | 2602OSPCA0000104 | Western | Taif | N/A
JED-HRR2-WAFA-173 | 2602OSPCI0000595 | Western | Jeddah | N/A
TAI-MELI-JUBR-10 | 2602OSPFA0000402 | Western | Taif | N/A
JED-HRR2-RIYA-41 | 2502OSPFA0002980 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-80 | 2602OSPFI0000511 | Western | Jeddah | N/A
JED-HRR2-WAFA-87 | 2602OSPFA0000515 | Western | Jeddah | N/A
JED-HRR2-WAFA-91 | 2602OSPFA0000519 | Western | Jeddah | N/A
JED-FRDS-BUHA-30 | 2502OSPFA0003249 | Western | Jeddah | N/A
JED-FRDS-BUHA-28 | 2502OSPCA0003079 | Western | Jeddah | N/A
JED-HRR2-RIYA-64 | 2602OSPCI0000332 | Western | Jeddah | Riyadh
BAH-BCPS-ARIF-01 | 2612OSPCA0000222 | Southern | Baha | N/A
TAI-QRAU-SABA-03 | 2602OSPFI0000624 | Western | Taif | N/A
JED-FRDS-BUHA-F2 | 2502OSPFA0003250 | Western | Jeddah | N/A
BAH-BCPS-MASA-01 | 2612OSPCA0000216 | Southern | Baha | N/A
TAI-QAIM-HASH-09 | 2602OSPFA0000109 | Western | Taif | N/A
BAH-BCPS-SARA-01 | 2612OSPCI0000217 | Southern | Baha | N/A
TAI-QAIM-QIAA-10 | 2602OSPFI0000443 | Western | Taif | N/A
TAI-QRAU-SABA-05 | 2602OSPCI0000573 | Western | Taif | N/A
JED-HRR2-WAFA-09 | 2602OSPFI0000684 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2602OSPFA0000448 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-34 | 2502OSPFA0002974 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-46 | 2502OSPFA0002985 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-32 | 2602OSPFI0000697 | Western | Jeddah | N/A
JED-HRR2-WAFA-06 | 2602OSPCI0000600 | Western | Jeddah | N/A
JED-HRR2-RIYA-39 | 2502OSPCA0002828 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-23 | 2602OSPFI0000692 | Western | Jeddah | N/A
JED-FRDS-MANA-16 | 2502OSPCA0002811 | Western | Jeddah | N/A
JED-HRR2-RIYA-54 | 2502OSPFA0002990 | Western | Jeddah | Riyadh
JED-HRR2-SALH-08 | 2602OSPCA0000397 | Western | Jeddah | Salhiya
JED-HRR2-WAFA-13 | 2602OSPFI0000686 | Western | Jeddah | N/A
JED-HRR2-WAFA-27 | 2602OSPFI0000695 | Western | Jeddah | N/A
JED-HRR2-RIYA-39 | 2502OSPFA0002979 | Western | Jeddah | Riyadh
BAH-BCPS-ADEL-01 | 2612OSPFA0000245 | Southern | Baha | N/A
JED-HRR2-RIYA-41 | 2502OSPCI0002988 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-23 | 2602OSPCA0000399 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-29 | 2502OSPCA0003080 | Western | Jeddah | N/A
TAI-QAIM-QIAA-11 | 2602OSPFI0000441 | Western | Taif | N/A
JED-HRR2-WAFA-32 | 2602OSPCI0000646 | Western | Jeddah | N/A
JED-HRR2-RIYA-44 | 2502OSPCA0002832 | Western | Jeddah | Riyadh
JED-FRDS-MANA-05 | 2502OSPFA0002956 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2502OSPCA0002829 | Western | Jeddah | Riyadh
BAH-BCPS-ARIF-01 | 2612OSPFI0000248 | Southern | Baha | N/A
JED-HRR2-WAFA-09 | 2602OSPCI0000632 | Western | Jeddah | N/A
TAI-QAIM-QIAA-09 | 2602OSPCI0000394 | Western | Taif | N/A
BAH-BCPS-MASA-01 | 2612OSPFI0000243 | Southern | Baha | N/A
JED-HRR2-RIYA-36 | 2502OSPFA0002976 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-17 | 2602OSPFI0000688 | Western | Jeddah | N/A
JED-HRR2-WAFA-85 | 2602OSPFA0000513 | Western | Jeddah | N/A
JED-HRR2-WAFA-92 | 2602OSPFA0000520 | Western | Jeddah | N/A
TAI-QRAU-SABA-04 | 2602OSPCI0000572 | Western | Taif | N/A
JED-FRDS-MANA-19 | 2502OSPFA0002964 | Western | Jeddah | N/A
JED-FRDS-MANA-08 | 2502OSPFA0002959 | Western | Jeddah | N/A
JED-HRR2-WAFA-92 | 2602OSPCA0000471 | Western | Jeddah | N/A
JED-FRDS-MANA-06 | 2502OSPFA0002957 | Western | Jeddah | N/A
JED-FRDS-BUHA-26 | 2502OSPFI0003267 | Western | Jeddah | N/A
JED-FRDS-BUHA-27 | 2502OSPFI0003268 | Western | Jeddah | N/A
JED-HRR2-WAFA-91 | 2602OSPCI0000470 | Western | Jeddah | N/A
TAB-TBK5-MASY-02 | 2607OSPFA0000135 | Western | Tabuk | N/A
JED-HRR2-WAFA-25 | 2602OSPFI0000694 | Western | Jeddah | N/A
JED-HRR2-RIYA-56 | 2502OSPCA0002841 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-70 | 2602OSPFI0000440 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-11 | 2602OSPCI0000391 | Western | Taif | N/A
JED-HRR2-WAFA-89 | 2602OSPCI0000468 | Western | Jeddah | N/A
JED-HRR2-RIYA-37 | 2502OSPCA0002826 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-26 | 2502OSPFA0003245 | Western | Jeddah | N/A
JED-FRDS-BUHA-27 | 2502OSPFA0003246 | Western | Jeddah | N/A
TAI-MELI-JUFE-04 | 2602OSPFA0000450 | Western | Taif | N/A
BAH-BCPS-GHAD-01 | 2612OSPCI0000219 | Southern | Baha | N/A
JED-HRR2-WAFA-25 | 2602OSPCI0000643 | Western | Jeddah | N/A
JED-HRR2-WAFA-86 | 2602OSPCI0000465 | Western | Jeddah | N/A
JED-HRR2-RIYA-56 | 2502OSPCI0003000 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-29 | 2502OSPFA0002973 | Western | Jeddah | Riyadh
JED-HRR2-TEEB-11 | 2602OSPFA0000405 | Western | Jeddah | N/A
JED-HRR2-WAFA-99 | 2602OSPCI0000473 | Western | Jeddah | N/A
JED-HRR2-RIYA-46 | 2502OSPCA0002834 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-23 | 2602OSPFA0000449 | Western | Jeddah | Riyadh
JED-HRR2-FURO-29 | 2602OSPFI0000507 | Western | Jeddah | N/A
JED-HRR2-RIYA-56 | 2502OSPFA0002992 | Western | Jeddah | Riyadh
BAH-BCPS-SARA-01 | 2612OSPFA0000244 | Southern | Baha | N/A
JED-HRR2-RIYA-F3 | 2502OSPCA0002842 | Western | Jeddah | Riyadh
BAH-BCPS-ARIF-01 | 2612OSPCI0000222 | Southern | Baha | N/A
JED-HRR2-RIYA-25 | 2502OSPFA0002970 | Western | Jeddah | Riyadh
JED-FRDS-MANA-07 | 2502OSPCA0002807 | Western | Jeddah | N/A
TAI-QAIM-QIAA-09 | 2602OSPFI0000444 | Western | Taif | N/A
TAI-QAIM-HASH-F4 | 2602OSPFA0000110 | Western | Taif | N/A
JED-HRR2-WAFA-28 | 2602OSPFI0000696 | Western | Jeddah | N/A
JED-HRR2-WAFA-86 | 2602OSPFI0000514 | Western | Jeddah | N/A
JED-HRR2-WAFA-52 | 2602OSPCI0000649 | Western | Jeddah | N/A
JED-HRR2-SALH-18 | 2602OSPCA0000129 | Western | Jeddah | Salhiya
BAH-BCPS-AREE-01 | 2612OSPCA0000221 | Southern | Baha | N/A
JED-HRR2-RIYA-23 | 2602OSPFI0000271 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-45 | 2502OSPFA0002984 | Western | Jeddah | Riyadh
TAI-QAIM-HASH-08 | 2602OSPCA0000106 | Western | Taif | N/A
JED-HRR2-RIYA-38 | 2502OSPFI0002861 | Western | Jeddah | Riyadh
JED-HRR2-WAFA-86 | 2602OSPFA0000514 | Western | Jeddah | N/A
JED-HRR2-WAFA-90 | 2602OSPFA0000518 | Western | Jeddah | N/A
JED-HRR2-RIYA-56 | 2502OSPFI0003014 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-F3 | 2502OSPCI0003001 | Western | Jeddah | Riyadh
TAI-AYKB-QAMA-01 | 2502OSPCI0002758 | Western | Taif | N/A
TAI-QRAU-SABA-04 | 2602OSPFI0000625 | Western | Taif | N/A
JED-FRDS-BUHA-F2 | 2502OSPCA0003082 | Western | Jeddah | N/A
JED-HRR2-WAFA-24 | 2602OSPFI0000693 | Western | Jeddah | N/A
JED-HRR2-WAFA-11 | 2602OSPFI0000656 | Western | Jeddah | N/A
JED-FRDS-BUHA-28 | 2502OSPFI0003269 | Western | Jeddah | N/A
JED-HRR2-WAFA-42 | 2602OSPFI0000698 | Western | Jeddah | N/A
MAK-WHD2-QASA-15 | 2602OSPFA0000145 | Western | Makkah | N/A
JED-FRDS-MANA-F1 | 2502OSPFA0002968 | Western | Jeddah | N/A
JED-HRR2-WAFA-02 | 2602OSPCI0000603 | Western | Jeddah | N/A
TAI-QAIM-QIAA-10 | 2602OSPFA0000443 | Western | Taif | N/A
JED-FRDS-BUHA-22 | 2502OSPFI0003263 | Western | Jeddah | N/A
JED-HRR2-WAFA-13 | 2602OSPCI0000634 | Western | Jeddah | N/A
JED-HRR2-WAFA-98 | 2602OSPFA0000521 | Western | Jeddah | N/A
JED-HRR2-RIYA-38 | 2502OSPFA0002978 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-28 | 2502OSPFA0003247 | Western | Jeddah | N/A
MAK-WHD2-QASA-15 | 2602OSPFI0000145 | Western | Makkah | N/A
JED-HRR2-WAFA-88 | 2602OSPCI0000467 | Western | Jeddah | N/A
JED-HRR2-RIYA-43 | 2502OSPCA0002831 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-22 | 2502OSPFA0003241 | Western | Jeddah | N/A
JED-HRR2-WAFA-51 | 2602OSPFI0000699 | Western | Jeddah | N/A
JED-HRR2-RIYA-F3 | 2502OSPFI0002860 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-56 | 2602OSPCI0000395 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-23 | 2602OSPCA0000234 | Western | Jeddah | Riyadh
JED-FRDS-MANA-05 | 2502OSPFI0002978 | Western | Jeddah | N/A
SAM-SMTH-AMUD-01 | 2510OSPCI0003076 | Southern | Jizan | SAMTA
TAI-MELI-JUFE-02 | 2502OSPFI0003300 | Western | Taif | N/A
TAI-MELI-NASE-03 | 2502OSPCI0003271 | Western | Taif | N/A
JED-HRR2-RIYA-57 | 2602OSPFI0000127 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-03 | 2502OSPCI0003268 | Western | Taif | N/A
JED-HRR2-RIYA-47 | 2502OSPFI0003008 | Western | Jeddah | Riyadh
SAM-SMTH-TURS-01 | 2510OSPCI0003074 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-53 | 2502OSPCI0002997 | Western | Jeddah | Riyadh
SAM-SMTH-MASO-01 | 2510OSPCI0003075 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-35 | 2502OSPFI0002997 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-22 | 2502OSPCI0003232 | Western | Jeddah | N/A
JED-FRDS-MANA-17 | 2602OSPCI0000117 | Western | Jeddah | N/A
SAM-SMTH-MASO-01 | 2510OSPFI0003095 | Southern | Jizan | SAMTA
JED-FRDS-MANA-06 | 2502OSPCI0002965 | Western | Jeddah | N/A
TAI-MELI-JUFE-F1 | 2502OSPFI0003304 | Western | Taif | N/A
JED-FRDS-MANA-09 | 2502OSPFI0002982 | Western | Jeddah | N/A
JED-HRR2-RIYA-24 | 2502OSPFI0002991 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-02 | 2502OSPCI0003267 | Western | Taif | N/A
SAM-SMTH-MAJA-01 | 2510OSPFI0003097 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-55 | 2502OSPFI0003013 | Western | Jeddah | Riyadh
TAI-QAIM-HASH-F4 | 2602OSPCI0000108 | Western | Taif | N/A
JED-HRR2-SALH-19 | 2502OSPFI0002964 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-40 | 2502OSPCI0002900 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-29 | 2502OSPCI0002981 | Western | Jeddah | Riyadh
JED-FRDS-MANA-17 | 2602OSPFI0000126 | Western | Jeddah | N/A
JED-HRR2-RIYA-55 | 2502OSPCI0002999 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-26 | 2502OSPCI0003236 | Western | Jeddah | N/A
JED-HRR2-RIYA-44 | 2502OSPFI0003005 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-05 | 2502OSPFI0003303 | Western | Taif | N/A
JED-FRDS-BUHA-25 | 2502OSPCI0003235 | Western | Jeddah | N/A
JED-FRDS-MANA-09 | 2502OSPCI0002968 | Western | Jeddah | N/A
JED-FRDS-MANA-21 | 2502OSPCI0002974 | Western | Jeddah | N/A
JED-HRR2-RIYA-41 | 2502OSPFI0003002 | Western | Jeddah | Riyadh
TAB-TBK5-MASY-F1 | 2607OSPFI0000138 | Western | Tabuk | N/A
TAI-THVT-YASM-02 | 2502OSPFI0003244 | Western | Taif | N/A
TAI-QAIM-QIAA-F2 | 2602OSPCI0000111 | Western | Taif | N/A
EDA-AYBN-EDAB-01 | 2510OSPFI0002900 | Southern | Jizan | AL-EDABI
TAI-MELI-FIYS-01 | 2602OSPFI0000106 | Western | Taif | N/A
TAI-QAIM-HASH-08 | 2602OSPFI0000108 | Western | Taif | N/A
JED-FRDS-BUHA-24 | 2502OSPCI0003234 | Western | Jeddah | N/A
JED-HRR2-RAHA-18 | 2502OSPFI0003125 | Western | Jeddah | Rahmaniya
TAB-TBHH-MASY-01 | 2607OSPFI0000134 | Western | Tabuk | N/A
JED-HRR2-SALH-07 | 2502OSPFI0002436 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-57 | 2602OSPCI0000118 | Western | Jeddah | Riyadh
JED-HRR2-SALH-17 | 2502OSPFI0002833 | Western | Jeddah | Salhiya
TAI-QAIM-QIAA-F2 | 2602OSPFI0000113 | Western | Taif | N/A
JED-FRDS-MANA-21 | 2502OSPFI0002988 | Western | Jeddah | N/A
JED-FRDS-MANA-22 | 2502OSPCI0002975 | Western | Jeddah | N/A
SAM-SMTH-TURS-01 | 2510OSPFI0003094 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-27 | 2502OSPCI0002980 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-36 | 2502OSPCI0002984 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-40 | 2502OSPFI0002909 | Western | Jeddah | Riyadh
TAI-THVT-YASM-01 | 2502OSPCI0003212 | Western | Taif | N/A
TAI-THVT-YASM-01 | 2502OSPFI0003243 | Western | Taif | N/A
JED-FRDS-MANA-08 | 2502OSPCI0002967 | Western | Jeddah | N/A
JED-FRDS-MANA-18 | 2502OSPFI0002985 | Western | Jeddah | N/A
SAM-SMTH-KHAD-01 | 2510OSPFI0003093 | Southern | Jizan | SAMTA
TAI-AYKB-QUDS-01 | 2502OSPCI0002756 | Western | Taif | N/A
TAI-MELI-NASE-03 | 2502OSPFI0003305 | Western | Taif | N/A
JED-FRDS-BUHA-27 | 2502OSPCI0003237 | Western | Jeddah | N/A
JED-FRDS-BUHA-23 | 2502OSPCI0003233 | Western | Jeddah | N/A
JED-FRDS-BUHA-30 | 2502OSPCI0003240 | Western | Jeddah | N/A
JED-FRDS-MANA-06 | 2502OSPFI0002979 | Western | Jeddah | N/A
JED-HRR2-RIYA-59 | 2602OSPFI0000015 | Western | Jeddah | Riyadh
JED-FRDS-MANA-F1 | 2502OSPCI0002976 | Western | Jeddah | N/A
JED-FRDS-MANA-20 | 2502OSPFI0002987 | Western | Jeddah | N/A
JED-HRR2-RIYA-50 | 2502OSPCI0002995 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-37 | 2502OSPFI0002999 | Western | Jeddah | Riyadh
JED-FRDS-MANA-22 | 2502OSPFI0002989 | Western | Jeddah | N/A
JED-HRR2-RIYA-50 | 2502OSPFI0003009 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-F3 | 2502OSPFI0003015 | Western | Jeddah | Riyadh
JED-FRDS-MANA-F1 | 2502OSPFI0002990 | Western | Jeddah | N/A
TAI-MELI-JUFE-01 | 2502OSPCI0003266 | Western | Taif | N/A
JED-HRR2-SALH-13 | 2602OSPCI0000010 | Western | Jeddah | Salhiya
JED-HRR2-SALH-06 | 2502OSPFI0002826 | Western | Jeddah | Salhiya
JED-FRDS-MANA-20 | 2502OSPCI0002973 | Western | Jeddah | N/A
JED-FRDS-MANA-10 | 2502OSPFI0002983 | Western | Jeddah | N/A
TAI-QAIM-QIAA-10 | 2602OSPCI0000009 | Western | Taif | N/A
JED-HRR2-RIYA-38 | 2502OSPFI0003000 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-52 | 2502OSPCI0002996 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-04 | 2502OSPCI0003269 | Western | Taif | N/A
JED-HRR2-RIYA-52 | 2502OSPFI0003010 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-26 | 2502OSPFI0002993 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-42 | 2502OSPCI0002989 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-08 | 2602OSPCI0000109 | Western | Taif | N/A
JED-FRDS-MANA-16 | 2502OSPFI0002984 | Western | Jeddah | N/A
JED-HRR2-SALH-18 | 2602OSPFI0000143 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-54 | 2502OSPCI0002998 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-53 | 2502OSPFI0003011 | Western | Jeddah | Riyadh
SAM-SMTH-AMUD-01 | 2510OSPFI0003096 | Southern | Jizan | SAMTA
JED-HRR2-RIYA-56 | 2502OSPFI0002908 | Western | Jeddah | Riyadh
TAI-QAIM-QIAA-09 | 2602OSPFI0000303 | Western | Taif | N/A
JED-FRDS-MANA-18 | 2502OSPCI0002971 | Western | Jeddah | N/A
TAI-QAIM-QIAA-08 | 2602OSPFI0000111 | Western | Taif | N/A
JED-HRR2-RIYA-28 | 2602OSPFI0000306 | Western | Jeddah | Riyadh
TAI-MELI-JUBR-10 | 2502OSPCI0003265 | Western | Taif | N/A
JED-HRR2-RIYA-49 | 2602OSPFI0000001 | Western | Jeddah | Riyadh
JED-HRR2-SALH-13 | 2602OSPFI0000010 | Western | Jeddah | Salhiya
TAI-QAIM-HASH-09 | 2602OSPCI0000107 | Western | Taif | N/A
JED-FRDS-MANA-19 | 2502OSPCI0002972 | Western | Jeddah | N/A
SAM-SMTH-MAJA-01 | 2510OSPCI0003077 | Southern | Jizan | SAMTA
JED-FRDS-MANA-10 | 2502OSPCI0002969 | Western | Jeddah | N/A
JED-HRR2-RIYA-27 | 2502OSPFI0002994 | Western | Jeddah | Riyadh
TAI-THVT-YASM-F1 | 2502OSPFI0003297 | Western | Taif | N/A
TUR-TRBH::TUR-SECO:01 | 2502OSPCI0002589 | Western | Taif | Turba
JED-HRR2-RIYA-59 | 2602OSPCI0000014 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-F3 | 2502OSPCI0002860 | Western | Jeddah | Riyadh
JED-FRDS-BUHA-28 | 2502OSPCI0003238 | Western | Jeddah | N/A
TAI-THVT-YASM-F1 | 2502OSPCI0003264 | Western | Taif | N/A
JED-HRR2-RIYA-34 | 2502OSPCI0002982 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-45 | 2502OSPCI0002992 | Western | Jeddah | Riyadh
JED-HRR2-SALH-18 | 2602OSPCI0000129 | Western | Jeddah | Salhiya
JED-FRDS-MANA-07 | 2502OSPCI0002966 | Western | Jeddah | N/A
TAI-AYKB-QUDS-01 | 2502OSPFI0002769 | Western | Taif | N/A
TAI-MELI-JUBR-10 | 2502OSPFI0003298 | Western | Taif | N/A
TAI-AYKB-SAKA-01 | 2502OSPCI0002755 | Western | Taif | N/A
JED-HRR2-SALH-15 | 2602OSPCI0000015 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-34 | 2502OSPFI0002996 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-03 | 2502OSPFI0003301 | Western | Taif | N/A
JED-HRR2-RIYA-46 | 2502OSPFI0003007 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-05 | 2502OSPCI0003270 | Western | Taif | N/A
JED-HRR2-RIYA-39 | 2502OSPCI0002987 | Western | Jeddah | Riyadh
JED-FRDS-MANA-07 | 2502OSPFI0002980 | Western | Jeddah | N/A
JED-FRDS-MANA-16 | 2502OSPCI0002970 | Western | Jeddah | N/A
TAI-QAIM-HASH-09 | 2602OSPFI0000109 | Western | Taif | N/A
TAI-QAIM-QIAA-09 | 2602OSPCI0000261 | Western | Taif | N/A
JED-HRR2-SALH-07 | 2502OSPCI0002400 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-42 | 2502OSPFI0003003 | Western | Jeddah | Riyadh
JED-HRR2-SALH-19 | 2502OSPCI0002951 | Western | Jeddah | Salhiya
JED-FRDS-BUHA-29 | 2502OSPCI0003239 | Western | Jeddah | N/A
JED-HRR2-RIYA-43 | 2502OSPFI0003004 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-44 | 2502OSPCI0002991 | Western | Jeddah | Riyadh
TAI-MELI-JUFE-04 | 2502OSPFI0003302 | Western | Taif | N/A
JED-HRR2-RIYA-54 | 2502OSPFI0003012 | Western | Jeddah | Riyadh
TAI-AYKB-QAMA-01 | 2502OSPCI0002757 | Western | Taif | N/A
JED-HRR2-RIYA-39 | 2502OSPFI0003001 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-23 | 2502OSPFI0003337 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-56 | 2502OSPCI0002899 | Western | Jeddah | Riyadh
TAI-THVT-YASM-02 | 2502OSPCI0003213 | Western | Taif | N/A
JED-HRR2-SALH-06 | 2502OSPCI0002825 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-36 | 2502OSPFI0002998 | Western | Jeddah | Riyadh
JED-FRDS-MANA-19 | 2502OSPFI0002986 | Western | Jeddah | N/A
JED-FRDS-MANA-08 | 2502OSPFI0002981 | Western | Jeddah | N/A
JED-HRR2-SALH-16 | 2502OSPFI0002835 | Western | Jeddah | Salhiya
JED-HRR2-RIYA-45 | 2502OSPFI0003006 | Western | Jeddah | Riyadh
TAI-QAIM-HASH-08 | 2602OSPCI0000106 | Western | Taif | N/A
JED-HRR2-SALH-14 | 2502OSPFI0003368 | Western | Jeddah | Salhiya
TAI-AYKB-SAKA-01 | 2502OSPFI0002768 | Western | Taif | N/A
TAI-MELI-JUFE-01 | 2502OSPFI0003299 | Western | Taif | N/A
JED-HRR2-RIYA-28 | 2602OSPCI0000267 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-41 | 2502OSPCI0002896 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-29 | 2502OSPFI0002995 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-46 | 2502OSPCI0002993 | Western | Jeddah | Riyadh
JED-HRR2-RIYA-25 | 2502OSPFI0002992 | Western | Jeddah | Riyadh
TAI-QAIM-HASH-F4 | 2602OSPFI0000110 | Western | Taif | N/A
JED-HRR2-RIYA-41 | 2502OSPFI0002905 | Western | Jeddah | Riyadh
JED-HRR2-SALH-15 | 2602OSPFI0000016 | Western | Jeddah | Salhiya
TAI-QAIM-QIAA-10 | 2602OSPFI0000009 | Western | Taif | N/A
JED-HRR2-RIYA-43 | 2502OSPCI0002990 | Western | Jeddah | Riyadh
JED-FRDS-MANA-05 | 2502OSPCI0002964 | Western | Jeddah | N/A
JED-FRDS-BUHA-F2 | 2502OSPCI0003241 | Western | Jeddah | N/A
TUR-TRBH::TUR-SECO:01 | 2502OSPFI0002599 | Western | Taif | Turba

## Penalties
Region | Cluster Name | Scope | System | Assigned Date | Inspection Consultant | Implementation Contractor | Deviation name | Remarks | Number of Deviations | Penalties Amount
MAKKAH | JED-HRR2-RIYA-60 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 202
MAKKAH | JED-HRR2-RIYA-63 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 108
MAKKAH | JED-HRR2-RIYA-64 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 65
MAKKAH | JED-HRR2-RIYA-65 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 86
MAKKAH | JED-HRR2-RIYA-70 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 224
MAKKAH | JED-HRR2-RIYA-71 | Inspection | GIS | 21-Aug-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 118
MAKKAH | JED-HRR2-RIYA-67 | Inspection | GIS | 2-Oct-25 | OTC | MET | ODBs No MP | (Sticker Installed) | 124
MAKKAH | JED-HRR2-RIYA-66 | Inspection | GIS | 2-Oct-25 | OTC | MET | Safety Penalty ODBs No MP | (No Signboard No Traffic Sign No Safety net No Proper Safety Barricades Debris on Site) (Sticker Installed) | 108 | 5000
MAKKAH | JED-HRR2-RAHA-18 | Inspection | GIS | 30-Nov-25 | OTC | MET | Quality Penalty | (04 FQNs No Flyer No Material Supply Form No DN & BOQ) | 12 | 12000
MAKKAH | JED-HRR2-RIYA-25 | Inspection | GIS | 8-Dec-25 | OTC | MET | Quality Penalty | (12 FQNs No Flyer No Material Supply Form No DN & BOQ) | 36 | 36000
MAKKAH | JED-HRR2-RIYA-68 | Inspection | GIS | 2025-10-02 | OTC | MET | ODBs No MP | (Sticker Installed) | 114
JIZAN | SAM-SMTH-KHAD-01 | Inspection | GIS | 2026-01-15 | OTC | MET | Safety Penalty | (No PPE, No safety Net, No Safety Lights, No Warning Signs, No Proper safety barricades, No Steel Plates) | 6 | 6000
[9 empty] | 1203 | 59000

## Workorder details
Link Code | Percentage of Completion | Region | Project | Subclass | Stage | WO Cost | Cost | Created | Assigned at | Year | Targeted Completion | Updated Target Date | Updated | Trench Progress | Trench Scope | MH/HH Progress | MH/HH Scope | Number of Buildings | Number of Households | Parcels | Fiber Progress | Fiber Scope | ODBs Progress | ODBs Scope | ODFs Progress | ODFs Scope | JCL Progress | JCL Scope | FAT Progress | FAT Scope | PFAT Progress | PFAT Scope | SFAT Progress | SFAT Scope | Work Order Status | Cancel Reason | Type | Class | Closed at | Permit Review | Permit Completion Status | Permits Progress | Permits Scope | PIP rejection count | PAT rejection count | Approval rejection count | As-Built Rejection Count | Handover Rejection Count | Parent | Number | Request | SOR Reference Number | Target Area | Notes | Scope of Work
JED-HRR2-SALH-04 | 116.34 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 212790.6 | 212790.6 | 2025-08-12 13:27 | 2025-08-12 13:27 | 2025 | 2025-12-25 |  | 2026-03-01 12:48 | 0 | 0 | 0 | 0 | 151 | 300 |  | 22800 | 19590 | 156 | 151 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002480 | OSPWO0021620 | RITM0070553 |  | 2376401 | 17/02/2026 13:58:43 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-63 | 100.42 | MAKKAH | FTTH | Civil | 6 - PAT Approval | 656375.1 | 655335 | 2025-08-15 13:47 | 2025-08-15 13:47 | 2025 | 2025-09-30 | 2025-09-30 | 2026-03-26 14:59 | 4072 | 4055 | 14 | 14 | 291 | 117 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001497 | OSPWO0021676 | RITM0070690 |  | 2383801 | 13/11/2025 11:13:49 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-60 | 100.12 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 253854.55 | 255575 | 2025-08-12 22:56 | 2025-08-12 22:56 | 2025 | 2025-10-31 | 2025-11-30 | 2026-01-21 16:57 | 0 | 0 | 0 | 0 | 200 | 237 |  | 26028 | 26028 | 225 | 200 | 0 | 0 | 0 | 0 | 6 | 12 | 0 | 0 | 12 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001532 | OSPWO0021636 | RITM0070557 |  | 2383801 | 21/01/2026 16:57:19 - Mohammad Nasser AlHayaya (Notes) Approved by DWT PM 01 ODB not Implemented (D9175475001)as customer refused the service. 19/01/2026 23:13:50 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 03/12/2025 19:18:27 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs not yet implemented 30/09/2025 09:24:07 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-71 | 100.09 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 155991.15 | 157081 | 2025-08-12 23:08 | 2025-08-12 23:08 | 2025 | 2025-10-19 |  | 2026-01-12 22:09 | 0 | 0 | 0 | 0 | 109 | 117 |  | 14680 | 14680 | 110 | 109 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 12 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001534 | OSPWO0021648 | RITM0070563 |  | 2383801 | 12/01/2026 22:09:18 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-64 | 100.06 | MAKKAH | FTTH | Fiber | 6 - PAT Approval | 116028.5 | 116689 | 2025-08-12 22:59 | 2025-08-12 22:59 | 2025 | 2025-10-18 | 2025-11-27 | 2026-03-26 15:05 | 0 | 0 | 0 | 0 | 66 | 107 |  | 10780 | 10780 | 78 | 72 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 10 | 10 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 2402OSPFD0001536 | OSPWO0021640 | RITM0070559 |  | 2383801 | 12/01/2026 22:12:12 - Mohammad Nasser AlHayaya (Notes) Approved 06/01/2026 12:35:18 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs not yet implemented 24/12/2025 14:16:18 - Mohammad Nasser AlHayaya (Notes) Reject 1 ODB not yet implemented 25/11/2025 15:45:39 - Muhammad Nabeel Shahid (Notes) Reject, 1 ODB not implemented
JED-HRR2-RIYA-63 | 100.04 | MAKKAH | FTTH | Fiber | 6 - PAT Approval | 153548.6 | 154589 | 2025-08-15 13:48 | 2025-08-15 13:48 | 2025 | 2025-10-22 | 2025-11-30 | 2026-03-26 15:02 | 0 | 0 | 0 | 0 | 104 | 117 |  | 14108 | 14108 | 110 | 104 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 12 | 12 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001535 | OSPWO0021678 | RITM0070691 |  | 2383801 | 12/01/2026 22:10:06 - Mohammad Nasser AlHayaya (Notes) Approved 24/12/2025 14:14:49 - Mohammad Nasser AlHayaya (Notes) Reject 12 ODBs not yet implemented 25/11/2025 15:41:48 - Muhammad Nabeel Shahid (Notes) Reject, 12 ODBs not implemented 30/09/2025 09:24:55 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-69 | 100.01 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 160210.05 | 161020 | 2025-08-15 14:00 | 2025-08-15 14:00 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:49 | 0 | 0 | 0 | 0 | 81 | 242 |  | 13654 | 13654 | 81 | 81 | 0 | 0 | 0 | 0 | 13 | 12 | 0 | 0 | 16 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2402OSPFD0001541 | OSPWO0021690 | RITM0070696 |  | 2383801 | 29/01/2026 10:43:38 - Mohammad Nasser AlHayaya (Notes) Approved 21/01/2026 16:51:08 - Mohammad Nasser AlHayaya (Notes) Reject, 4 ODBs still not implemented
JED-HRR2-RIYA-67 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 189267 | 190367 | 2025-08-15 14:03 | 2025-08-15 14:03 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:46 | 0 | 0 | 0 | 0 | 110 | 314 |  | 17905 | 17905 | 110 | 110 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001539 | OSPWO0021694 | RITM0070698 |  | 2383801 | 06/01/2026 12:33:34 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-49 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 726851 | 726851 | 2026-01-01 11:52 | 2026-01-01 11:52 | 2026 | 2026-02-28 |  | 2026-02-25 01:00 | 6446 | 6446 | 15 | 15 | 63 | 282 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000732 | OSPWO0026525 | RITM0083098 |  | 2387401
SHU-AZRQ-JORI-01 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 282978.6 | 282978.6 | 2025-10-27 08:48 | 2025-10-27 08:48 | 2025 | 2026-09-30 |  | 2026-02-18 11:36 | 2153 | 2153 | 9 | 9 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 5 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023906 | RITM0076018 |  | 8485201 | 27/01/2026 14:22:48 - Husam Jari (Notes) Proposed Target is Rejected. Revise the Date with PM
JED-HRR2-SALH-11 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 813766.1 | 813766 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025 | 2026-01-30 |  | 2026-03-09 16:06 | 7854 | 7854 | 15 | 15 | 170 | 139 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2502OSPCD0000018 | OSPWO0024249 | RITM0076721 |  | 2376401 | 29/01/2026 10:41:06 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still in Progress
SHU-AZRQ-JORI-01 | 100 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 45367.1 | 45367.1 | 2025-10-27 08:49 | 2025-10-27 08:49 | 2025 | 2026-09-30 |  | 2026-02-18 11:37 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2304 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023908 | RITM0076019 |  | 8485201
JED-HRR2-SALH-03 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 803540.7 | 803540.7 | 2025-08-12 13:24 | 2025-08-12 13:24 | 2025 | 2025-11-30 | 2025-12-10 | 2026-03-01 12:48 | 5626 | 5626 | 12 | 12 | 155 | 342 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 2402OSPCD0002455 | OSPWO0021614 | RITM0070520 |  | 2376401 | 29/01/2026 10:42:02 - Mohammad Nasser AlHayaya (Notes) Approved 25/01/2026 13:35:36 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress 30/09/2025 09:31:44 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RAHA-18 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 1364392.9 | 1362703 | 2025-11-16 22:38 | 2025-11-16 22:38 | 2025 | 2026-01-11 |  | 2026-03-09 17:22 | 10280 | 10280 | 18 | 18 | 170 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000008 | OSPWO0024972 | RITM0077705 |  | 2376401
JED-HRR2-RIYA-38 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 932366 | 932366 | 2025-10-11 22:38 | 2025-10-11 22:38 | 2025 | 2026-03-28 |  | 2026-03-10 22:49 | 7550 | 7550 | 16 | 16 |  |  | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000693 | OSPWO0023694 | RITM0075247 |  | 2387401
JED-HRR2-SALH-05 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 913312.1 | 913312.1 | 2025-08-12 13:28 | 2025-08-12 13:28 | 2025 | 2025-12-04 | 2026-01-12 | 2026-03-01 13:21 | 6628 | 6628 | 14 | 14 | 169 | 368 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002457 | OSPWO0021622 | RITM0070522 |  | 2376401 | 24/02/2026 15:33:07 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:32:28 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-F6 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 304001.2 | 304001 | 2025-08-23 21:28 | 2025-08-23 21:28 | 2025 | 2025-10-25 | 2025-11-30 | 2026-03-03 13:46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26520 | 26520 | 0 | 0 | 4 | 4 | 3 | 3 | 4 | 4 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001542 | OSPWO0021887 | RITM0072341 |  | 2383801 | 03/03/2026 13:45:46 - Mohammad Nasser AlHayaya (Notes) Approved 21/01/2026 16:50:06 - Mohammad Nasser AlHayaya (Notes) Reject, work not yet started 12/01/2026 21:48:28 - Mohammad Nasser AlHayaya (Notes) Reject, No inspector assignment requested 30/09/2025 09:30:50 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-60 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 900061.6 | 821262 | 2025-08-12 22:55 | 2025-08-12 22:55 | 2025 | 2025-10-05 | 2025-10-18 | 2026-01-21 16:58 | 6547 | 6547 | 12 | 12 | 297 | 236 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 2402OSPCD0001494 | OSPWO0021634 | RITM0070556 |  | 2383801 | 21/01/2026 16:58:05 - Mohammad Nasser AlHayaya (Notes) Approved by DWT PM, 01 ODB not Implemented (D9175475001) as customer refused the service. 19/01/2026 23:14:44 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 12/01/2026 21:59:29 - Mohammad Nasser AlHayaya (Notes) Reject, 2 ODBs Not Yet Implemented
JED-HRR2-SALH-02 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 242464.65 | 242464.65 | 2025-08-10 11:33 | 2025-08-10 11:33 | 2025 | 2025-12-17 |  | 2026-03-01 12:48 | 0 | 0 | 0 | 0 | 171 | 424 |  | 22520 | 22520 | 177 | 177 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 12 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002478 | OSPWO0021579 | RITM0070551 |  | 2376401 | 17/02/2026 13:47:16 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-02 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 932260.7 | 932260.7 | 2025-08-12 13:20 | 2025-08-12 13:20 | 2025 | 2025-11-27 | 2025-12-14 | 2026-03-01 12:48 | 6557 | 6557 | 14 | 14 | 171 | 424 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002454 | OSPWO0021612 | RITM0070519 |  | 2376401 | 25/01/2026 13:38:44 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:31:21 - Mufleh Alsulami (Notes) Revise the target with project manger
MOY-MOYH-KHAL-01 | 100 | MAKKAH | FEP-Phase1 | Fiber | 5 - Conducting PAT | 186673.2 | 171378 | 2025-08-16 18:30 | 2025-08-16 18:30 | 2025 | 2025-09-05 |  | 2026-01-01 14:09 | 0 | 0 | 0 | 0 | 2 | 2 |  | 288 | 288 | 2 | 2 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | OSPWO0021711 | RITM0070780 |  | 2759401 | 01/01/2026 14:08:36 - Mohammad Nasser AlHayaya (Notes) Reject, PAT Documents missing DCR Pending with no report submitted 13/11/2025 11:14:19 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-66 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 166999.9 | 168000 | 2025-08-15 13:54 | 2025-08-15 13:54 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:46 | 0 | 0 | 0 | 0 | 100 | 309 |  | 13986 | 13986 | 100 | 100 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001538 | OSPWO0021682 | RITM0070692 |  | 2383801 | 12/01/2026 22:05:02 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-64 | 100 | MAKKAH | FTTH | Civil | 6 - PAT Approval | 613447 | 612787 | 2025-08-12 22:59 | 2025-08-12 22:59 | 2025 | 2025-09-29 | 2025-09-29 | 2026-03-26 15:03 | 3918 | 3918 | 11 | 11 | 281 | 107 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001498 | OSPWO0021638 | RITM0070558 |  | 2383801 | 13/11/2025 11:15:25 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-67 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 847493.4 | 846393 | 2025-08-15 14:03 | 2025-08-15 14:03 | 2025 | 2025-10-31 |  | 2026-03-02 14:46 | 6642 | 6642 | 12 | 12 | 110 | 314 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 2402OSPCD0001501 | OSPWO0021692 | RITM0070699 |  | 2383801 | 12/01/2026 22:06:08 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 21:10:37 - Mufleh Alsulami (Notes) Revise the target with project manager 30/09/2025 09:29:56 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-10 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 904296.7 | 904297 | 2025-10-06 09:57 | 2025-10-06 09:57 | 2025 | 2026-01-28 |  | 2026-03-09 16:06 | 6633 | 6633 | 14 | 14 | 179 | 137 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000017 | OSPWO0023535 | RITM0074722 |  | 2376401 | 25/01/2026 13:39:10 - Mohammad Nasser AlHayaya (Notes) Approved
SHU-AZRQ-SHUQ-01 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 1574004 | 1574004 | 2025-10-27 08:50 | 2025-10-27 08:50 | 2025 | 2026-09-30 |  | 2026-02-18 11:38 | 11603 | 11603 | 56 | 56 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 5 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023910 | RITM0076020 |  | 8485401
JED-HRR2-RIYA-68 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 774818.4 | 773798 | 2025-08-15 13:56 | 2025-08-15 13:56 | 2025 | 2025-10-31 | 2025-11-30 | 2026-03-02 14:48 | 6041 | 6041 | 13 | 13 | 102 | 304 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 2402OSPCD0001502 | OSPWO0021684 | RITM0070694 |  | 2383801 | 18/01/2026 14:26:20 - Mohammad Nasser AlHayaya (Notes) Approved 01/12/2025 20:19:27 - Mohammad Nasser AlHayaya (Notes) Reject, The remaining 5 HH to be installed, with 100 m to be excavated 30/09/2025 09:30:10 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-35 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 666148 | 666148 | 2025-11-05 10:37 |  | 2025 | 2026-02-25 |  | 2026-03-10 22:47 | 5300 | 5300 | 14 | 14 | 48 | 302 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000799 | OSPWO0024384 | RITM0076809 |  | 2387401
JED-HRR2-RIYA-47 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 753767 | 753767 | 2025-11-05 10:45 |  | 2025 | 2026-01-25 |  | 2026-03-01 14:13 | 5105 | 5105 | 14 | 14 | 79 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000650 | OSPWO0024428 | RITM0076831 |  | 2387401 | 21/01/2026 16:59:07 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-26 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 726486 | 726486 | 2025-11-05 10:34 |  | 2025 | 2026-01-25 |  | 2026-03-10 22:44 | 6300 | 6300 | 14 | 14 | 56 | 276 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000748 | OSPWO0024368 | RITM0076801 |  | 2387401
JED-HRR2-SALH-09 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 217615.85 | 217616 | 2025-11-03 19:06 | 2025-11-03 19:06 | 2025 | 2026-03-25 |  | 2026-03-11 14:54 | 0 | 0 | 0 | 0 | 146 | 139 |  | 22960 | 22960 | 169 | 169 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 20 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000016 | OSPWO0024204 | RITM0076643 |  | 2376401 | 11/03/2026 14:53:35 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-12 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 278039.9 | 278040 | 2025-10-06 11:52 | 2025-10-06 11:52 | 2025 | 2026-03-25 |  | 2026-03-11 14:54 | 0 | 0 | 0 | 0 | 204 | 135 |  | 28803 | 28803 | 230 | 230 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 15 | 15 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000019 | OSPWO0023600 | RITM0074761 |  | 2376401 | 11/03/2026 14:54:00 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-08 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 195167.95 | 195168 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025 | 2026-02-27 |  | 2026-03-11 14:54 | 0 | 0 | 0 | 0 | 131 | 134 |  | 22650 | 22650 | 138 | 138 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000015 | OSPWO0023529 | RITM0074719 |  | 2376401 | 11/03/2026 14:54:29 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-66 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 808777.9 | 807778 | 2025-08-15 13:53 | 2025-08-15 13:53 | 2025 | 2025-10-31 |  | 2026-03-02 14:46 | 6162 | 6162 | 15 | 15 | 100 | 309 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0001500 | OSPWO0021680 | RITM0070693 |  | 2383801 | 12/01/2026 22:06:51 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:29:29 - Mufleh Alsulami (Notes) Revise the target with project manger
SAM-SMTH-KHAD-01 | 100 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 670187 | 670187 | 2025-11-16 10:38 |  | 2025 | 2026-09-30 |  | 2026-02-05 09:06 | 5015 | 5015 | 24 | 24 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 10 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024843 | RITM0077589 |  | 8673901
JED-HRR2-SALH-08 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 875273.2 | 875273 | 2025-10-06 09:52 | 2025-10-06 09:52 | 2025 | 2026-01-26 |  | 2026-03-02 12:13 | 6263 | 6263 | 13 | 13 | 171 | 131 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000015 | OSPWO0023527 | RITM0074718 |  | 2376401 | 25/01/2026 13:39:35 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-25 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 714254 | 714254 | 2025-11-05 10:34 |  | 2025 | 2026-01-26 |  | 2026-03-01 14:13 | 5121 | 5121 | 11 | 11 | 84 | 257 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2302OSPCD0000739 | OSPWO0024364 | RITM0076799 |  | 2387401 | 12/02/2026 14:54:03 - Mohammad Nasser AlHayaya (Notes) Approved 25/01/2026 13:36:16 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress
SHU-AZRQ-SHUQ-01 | 100 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 281335.4 | 281335.4 | 2025-10-27 08:51 | 2025-10-27 08:51 | 2025 | 2026-09-30 |  | 2026-02-18 11:39 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12443 | 12443 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023912 | RITM0076021 |  | 8485401
JED-HRR2-RIYA-24 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 760211 | 760211 | 2025-11-05 10:33 |  | 2025 | 2026-01-24 |  | 2026-03-01 14:13 | 5455 | 5455 | 11 | 11 | 79 | 264 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 2302OSPCD0000763 | OSPWO0024360 | RITM0076797 |  | 2387401 | 17/02/2026 13:58:16 - Mohammad Nasser AlHayaya (Notes) Approved 12/02/2026 14:54:46 - Mohammad Nasser AlHayaya (Notes) Reject, 3 Span Not Yet IMPL 25/01/2026 13:37:08 - Mohammad Nasser AlHayaya (Notes) Reject, Civil Work Still In progress
TAI-AYKB-QAMA-01 | 100 | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 345947.4 | 288628 | 2025-09-28 08:36 | 2025-09-28 08:36 | 2025 | 2026-04-30 |  | 2026-02-24 15:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16159 | 16159 | 0 | 0 | 1 | 1 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | OSPWO0023235 | RITM0073986 |  | 2634901 | 24/02/2026 15:36:12 - Mohammad Nasser AlHayaya (Notes) Not Yet Started
JED-HRR2-RIYA-23 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 870181 | 870181 | 2025-12-22 22:51 | 2025-12-22 22:51 | 2025 | 2026-02-07 |  | 2026-02-25 00:57 | 8470 | 8470 | 18 | 18 | 65 | 286 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000762 | OSPWO0026339 | RITM0080199 |  | 2387401
JED-HRR2-RIYA-69 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 816783 | 815973 | 2025-08-15 13:59 | 2025-08-15 13:59 | 2025 | 2025-10-31 | 2025-11-30 | 2026-03-02 14:48 | 6380 | 6380 | 14 | 14 | 81 | 242 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0001503 | OSPWO0021688 | RITM0070697 |  | 2383801 | 25/01/2026 13:41:11 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:30:25 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-09 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 931223.5 | 931224 | 2025-11-03 19:06 | 2025-11-03 19:06 | 2025 | 2026-02-28 |  | 2026-03-09 15:57 | 6685 | 6685 | 13 | 13 | 146 | 139 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000016 | OSPWO0024202 | RITM0076644 |  | 2376401 | 25/01/2026 13:41:46 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-37 | 100 | MAKKAH | FTTH | Civil | 3 - Implementation | 1003675 | 1003675 | 2025-11-05 10:39 |  | 2025 | 2026-03-31 |  | 2026-03-10 22:53 | 8250 | 8250 | 18 | 18 | 45 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000640 | OSPWO0024392 | RITM0076813 |  | 2387401
JED-HRR2-SALH-04 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 838015.3 | 838015.3 | 2025-08-12 13:26 | 2025-08-12 13:26 | 2025 | 2025-12-05 |  | 2026-03-01 12:48 | 5703 | 5703 | 15 | 15 | 151 | 300 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002456 | OSPWO0021618 | RITM0070521 |  | 2376401 | 25/01/2026 13:42:25 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:32:13 - Mufleh Alsulami (Notes) Revise the target with project manger
MOY-MOYH-KHAL-01 | 100 | MAKKAH | FEP-Phase1 | Civil | 5 - Conducting PAT | 936270.4 | 936270.4 | 2025-08-16 18:29 | 2025-08-16 18:29 | 2025 | 2025-09-05 |  | 2026-01-01 11:46 | 6740 | 6740 | 26 | 26 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Requested | 100 | 9 | 9 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0021709 | RITM0070781 |  | 2759401 | 13/11/2025 11:16:29 - Muhammad Nabeel Shahid (Notes) Approved
JED-HRR2-RIYA-68 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 170711.45 | 171731 | 2025-08-15 13:57 | 2025-08-15 13:57 | 2025 | 2025-11-05 | 2025-12-31 | 2026-03-02 14:48 | 0 | 0 | 0 | 0 | 102 | 304 |  | 14133 | 14133 | 102 | 102 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001540 | OSPWO0021686 | RITM0070695 |  | 2383801 | 18/01/2026 14:26:51 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-65 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 1216284.2 | 1165710.2 | 2025-09-16 11:47 |  | 2025 | 2025-10-09 | 2025-10-25 | 2026-03-02 14:45 | 7560 | 7560 | 20 | 20 | 309 | 283 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022886 | RITM0073181 |  | 2383801 | 12/01/2026 22:11:29 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-12 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 1048065.3 | 1048065 | 2025-10-06 11:51 | 2025-10-06 11:51 | 2025 | 2026-02-26 |  | 2026-03-02 12:14 | 7576 | 7576 | 13 | 13 | 204 | 135 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000019 | OSPWO0023598 | RITM0074760 |  | 2376401 | 25/01/2026 13:42:55 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-70 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 771781.3 | 706747 | 2025-08-12 23:05 | 2025-08-12 23:05 | 2025 | 2025-09-28 | 2025-10-18 | 2026-01-21 17:02 | 5525 | 5525 | 12 | 12 | 243 | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2402OSPCD0001495 | OSPWO0021642 | RITM0070560 |  | 2383801 | 21/01/2026 17:02:04 - Mohammad Nasser AlHayaya (Notes) Approved 19/01/2026 23:16:12 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented
JED-HRR2-RIYA-71 | 100 | MAKKAH | FTTH | Civil | 5 - Conducting PAT | 649016.5 | 636503 | 2025-08-12 23:07 | 2025-08-12 23:07 | 2025 | 2025-09-27 | 2025-09-30 | 2026-01-18 14:28 | 4614 | 4614 | 11 | 11 | 258 | 117 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001496 | OSPWO0021646 | RITM0070562 |  | 2383801 | 18/01/2026 14:27:41 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-RIYA-65 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 169864.45 | 170334.45 | 2025-09-16 11:47 |  | 2025 | 2025-10-31 | 2025-12-31 | 2026-03-02 14:45 | 0 | 0 | 0 | 0 | 75 | 284 |  | 13593 | 13593 | 105 | 105 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0022888 | RITM0073182 |  | 2383801 | 06/01/2026 12:34:34 - Mohammad Nasser AlHayaya (Notes) Approved 30/09/2025 09:26:56 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-70 | 100 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 271582.95 | 273553 | 2025-08-12 23:05 | 2025-08-12 23:05 | 2025 | 2025-10-31 | 2025-11-25 | 2026-01-25 13:44 | 0 | 0 | 0 | 0 | 225 | 234 |  | 27813 | 27813 | 225 | 225 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 21 | 21 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2402OSPFD0001533 | OSPWO0021644 | RITM0070561 |  | 2383801 | 25/01/2026 13:43:58 - Mohammad Nasser AlHayaya (Notes) Approved 19/01/2026 23:16:56 - Mohammad Nasser AlHayaya (Notes) 1 ODB Not Yet implemented 25/11/2025 15:47:11 - Muhammad Nabeel Shahid (Notes) Reject, 3 ODB not implemented 30/09/2025 09:25:59 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-SALH-10 | 99.93 | MAKKAH | FTTH | Fiber | 3 - Implementation | 225566.85 | 225567 | 2025-10-06 09:58 | 2025-10-06 09:58 | 2025 | 2026-02-28 |  | 2026-03-09 16:06 | 0 | 0 | 0 | 0 | 171 | 137 |  | 21657 | 21657 | 177 | 171 | 0 | 0 | 0 | 0 | 2 | 12 | 0 | 0 | 2 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000017 | OSPWO0023537 | RITM0074723 |  | 2376401
JED-HRR2-SALH-05 | 99.32 | MAKKAH | FTTH | Fiber | 3 - Implementation | 227271.35 | 227271.35 | 2025-08-12 13:29 | 2025-08-12 13:29 | 2025 | 2025-12-23 |  | 2026-03-03 22:08 | 0 | 0 | 0 | 0 | 169 | 368 |  | 22530 | 22503 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002481 | OSPWO0021624 | RITM0070554 |  | 2376401
TAB-TBK5-MASY-02 | 98.91 | TABUK | FTTH | Fiber | 3 - Implementation | 310878 | 310878 | 2026-01-07 12:24 |  | 2026 | 2026-03-15 |  | 2026-03-03 22:05 | 0 | 0 | 0 | 0 | 200 | 200 |  | 20962 | 20962 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002384 | OSPWO0027073 | RITM0086548 |  | 4732401
TAB-TBK5-MASY-04 | 98.75 | TABUK | FTTH | Fiber | 3 - Implementation | 273659 | 273659 | 2026-01-07 12:24 |  | 2026 | 2026-03-17 |  | 2026-03-03 22:06 | 0 | 0 | 0 | 0 | 171 | 171 |  | 15881 | 15881 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002386 | OSPWO0027077 | RITM0086552 |  | 4732401
TAB-TBK5-MASY-03 | 91.35 | TABUK | FTTH | Fiber | 3 - Implementation | 313953 | 313953 | 2026-01-07 12:24 |  | 2026 | 2026-03-28 |  | 2026-03-25 11:27 | 0 | 0 | 0 | 0 | 205 | 205 |  | 18000 | 19466 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 22 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002385 | OSPWO0027075 | RITM0086550 |  | 4732401 |  | 2,026
JED-HRR2-SALH-03 | 89.28 | MAKKAH | FTTH | Fiber | 5 - Conducting PAT | 212835 | 212835 | 2025-08-12 13:25 | 2025-08-12 13:25 | 2025 | 2025-12-21 |  | 2026-03-01 12:48 | 0 | 0 | 0 | 0 | 155 | 342 |  | 20832 | 23200 | 156 | 155 | 0 | 155 | 0 | 0 | 12 | 12 | 0 | 0 | 13 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002479 | OSPWO0021616 | RITM0070552 |  | 2376401 | 17/02/2026 13:59:11 - Mohammad Nasser AlHayaya (Notes) Approved
JED-HRR2-SALH-16 | 83.57 | MAKKAH | FTTH | Civil | 3 - Implementation | 937327.4 | 937327 | 2025-10-06 10:30 | 2025-10-06 10:30 | 2025 | 2026-02-26 |  | 2026-03-25 11:24 | 5800 | 6938 | 10 | 14 | 137 | 159 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002460 | OSPWO0023579 | RITM0074746 |  | 2376401
JED-HRR2-SALH-17 | 79.34 | MAKKAH | FTTH | Civil | 3 - Implementation | 904261.8 | 904262 | 2025-10-06 10:24 | 2025-10-06 10:24 | 2025 | 2026-02-27 |  | 2026-03-25 11:25 | 5200 | 6552 | 10 | 15 | 161 | 142 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002461 | OSPWO0023571 | RITM0074742 |  | 2376401
JED-HRR2-SALH-14 | 73.63 | MAKKAH | FTTH | Civil | 3 - Implementation | 938610 | 938610 | 2025-12-31 16:10 | 2025-12-31 16:10 | 2025 | 2026-06-30 |  | 2026-03-25 11:25 | 4950 | 6724 | 12 | 15 | 164 | 357 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 50 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002458 | OSPWO0026485 | RITM0082468 |  | 2376401
JED-HRR2-SALH-11 | 66.95 | MAKKAH | FTTH | Fiber | 3 - Implementation | 230941.2 | 230941 | 2025-11-04 22:07 | 2025-11-04 22:07 | 2025 | 2026-02-28 |  | 2026-03-25 11:26 | 0 | 0 | 0 | 0 | 170 | 139 |  | 14000 | 20909 | 120 | 170 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000018 | OSPWO0024251 | RITM0076722 |  | 2376401
JED-HRR2-SALH-F2 | 57.09 | MAKKAH | FTTH | Fiber | 3 - Implementation | 1185423 | 1185423 | 2025-08-12 13:31 | 2025-08-12 13:31 | 2025 | 2025-12-15 |  | 2026-03-09 17:16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20500 | 35906 | 0 | 0 | 2 | 4 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000021 | OSPWO0021626 | RITM0070555 |  | 2376401
EDA-AYBN-EDAB-01 | 8.93 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 4861289.9 | 4985409.8 | 2025-10-27 08:38 | 2025-10-27 08:38 | 2025 | 2026-10-31 |  | 2026-03-03 23:40 | 3350 | 37467 | 10 | 170 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 40 | 4 | 10 | 2 | 0 | 0 | 0 | 0 |  | OSPWO0023902 | RITM0076015 |  | 8574601 | 27/01/2026 14:22:25 - Husam Jari (Notes) Proposed Target is Rejected. Revise the Date with PM 01/12/2025 10:04:35 - Husam Jari (Notes) completion Target Date is rejected
DAI-ADAR-DAIR-01 | 5.29 | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 6679307 | 6679307 | 2025-11-16 10:38 |  | 2025 | 2026-09-30 |  | 2026-03-03 23:41 | 2640 | 49908 | 9 | 202 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 60 | 3 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024839 | RITM0077587 |  | 8386301
DAI-ADAR-DAIR-01 | 4.13 | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 1126800 | 1126800 | 2025-11-16 10:38 |  | 2025 | 2026-09-30 |  | 2026-03-03 23:42 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2200 | 53278 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 161 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024841 | RITM0077588 |  | 8386301
JED-HRR2-RIYA-53 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:47 |  | 2025 |  |  | 2025-11-05 10:49 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002997 | OSPWO0024441
TAI-MELI-FIYS-02 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:43 |  | 2026 |  |  | 2026-01-06 14:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000105 | OSPWO0026976
SAM-SMTH-MASO-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:40 |  | 2025 |  |  | 2025-11-16 10:41 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003075 | OSPWO0024852
JED-HRR2-WAFA-05 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:00 | 2026-03-26 11:00 | 2026 |  |  | 2026-03-26 11:01 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000678 | OSPWO0034791 | RITM0095072 |  | 2378601
JED-HRR2-RIYA-35 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:38 |  | 2025 |  |  | 2025-11-05 10:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002997 | OSPWO0024387
JED-HRR2-RIYA-24 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:33 |  | 2025 |  |  | 2025-11-05 10:34 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002977 | OSPWO0024361
TAI-QRAU-SABA-05 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 193465 | 193465 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026 |  |  | 2026-03-16 01:35 | 0 | 0 | 0 | 0 | 119 | 551 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002391 | OSPWO0034519 | RITM0094609 |  | 2651701
TAI-MELI-FIYS-01 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028764 | RITM0088963 |  | 2652602 |  | To close the pending held orders in the mentioned cluster
TAI-QRAU-MUAS-01 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:52 |  | 2026 |  |  | 2026-01-06 14:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000112 | OSPWO0027018
JED-FRDS-MANA-17 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:56 |  | 2026 |  |  | 2026-01-06 14:57 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000117 | OSPWO0027038
SAM-SMTH-AMUD-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:41 |  | 2025 |  |  | 2025-11-16 10:42 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003096 | OSPWO0024858
JED-HRR2-WAFA-87 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:12 |  | 2026 |  |  | 2026-02-16 12:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000466 | OSPWO0032377
BAH-BCPS-RADW-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:26 |  | 2026 |  |  | 2026-01-14 14:27 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000220 | OSPWO0027726
SAM-SMTH-AMUD-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:40 |  | 2025 |  |  | 2025-11-16 10:42 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003076 | OSPWO0024856
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:21 |  | 2026 |  |  | 2026-01-28 14:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028526 | RITM0088840 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-11 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:06 |  | 2026 |  |  | 2026-03-07 23:38 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000441 | OSPWO0028755
TAI-QRAU-MUAS-01 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:52 |  | 2026 |  |  | 2026-01-06 14:52 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027017 | RITM0086064 |  | 2652202
SAM-SMTH-TURS-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:39 |  | 2025 |  |  | 2025-11-16 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003074 | OSPWO0024848
BAH-BCPS-ADEL-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 202846 | 202846 | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027715 | RITM0087560 |  | 6558501
JED-HRR2-RIYA-29 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:36 |  | 2025 |  |  | 2025-11-05 10:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002981 | OSPWO0024377
JED-HRR2-RIYA-55 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:48 |  | 2025 |  |  | 2025-11-05 10:50 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002999 | OSPWO0024449
JED-HRR2-WAFA-06 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:30 | 2026-03-17 11:30 | 2026 |  |  | 2026-03-17 11:31 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000679 | OSPWO0034626 | RITM0094721 |  | 2378601
JED-FRDS-BUHA-26 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:11 |  | 2025 |  |  | 2025-12-16 13:12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003236 | OSPWO0025998
JED-HRR2-WAFA-14 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:33 | 2026-03-17 11:33 | 2026 |  |  | 2026-03-17 11:34 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000687 | OSPWO0034630 | RITM0094722 |  | 2378601
JED-HRR2-RIYA-44 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:43 |  | 2025 |  |  | 2025-11-05 10:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003005 | OSPWO0024419
TAI-QRAU-SABA-02 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 262287 | 262287 | 2026-03-16 01:29 | 2026-03-16 01:29 | 2026 |  |  | 2026-03-16 01:29 | 0 | 0 | 0 | 0 | 171 | 614 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002388 | OSPWO0034507 | RITM0094603 |  | 2651701
JED-HRR2-WAFA-85 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:10 |  | 2026 |  |  | 2026-03-01 15:39 | 0 | 0 | 0 | 0 | 32 | 59 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000619 | OSPWO0032370 | RITM0091401 |  | 2378501
JED-HRR2-WAFA-19 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:27 | 2026-03-26 11:27 | 2026 |  |  | 2026-03-26 11:28 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000667 | OSPWO0034825 | RITM0095089 |  | 2378601
JED-HRR2-WAFA-27 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026 |  |  | 2026-03-26 11:44 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000675 | OSPWO0034845 | RITM0095100 |  | 2378601
BAH-BCPS-NAIM-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:29 |  | 2026 |  |  | 2026-01-14 14:30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000250 | OSPWO0027738
JED-HRR2-WAFA-07 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:04 | 2026-03-26 11:04 | 2026 |  |  | 2026-03-26 11:04 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000680 | OSPWO0034795 | RITM0095074 |  | 2378601
JED-FRDS-BUHA-25 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:10 |  | 2025 |  |  | 2025-12-16 13:11 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003235 | OSPWO0025994
JED-FRDS-MANA-09 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:14 |  | 2025 |  |  | 2025-11-05 10:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002968 | OSPWO0024325
JED-FRDS-MANA-09 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:14 |  | 2025 |  |  | 2025-11-05 10:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002982 | OSPWO0024327
JED-HRR2-RIYA-24 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:33 |  | 2025 |  |  | 2025-11-05 10:35 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002991 | OSPWO0024363
JED-HRR2-WAFA-98 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:20 |  | 2026 |  |  | 2026-02-16 12:20 | 0 | 0 | 0 | 0 |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000608 | OSPWO0032400 | RITM0091416 |  | 2378501
JED-HRR2-WAFA-24 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:35 | 2026-03-26 11:35 | 2026 |  |  | 2026-03-26 11:36 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000672 | OSPWO0034837 | RITM0095095 |  | 2378601
SAM-SMTH-MAJA-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:41 |  | 2025 |  |  | 2025-11-16 10:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003097 | OSPWO0024862
JED-HRR2-RIYA-55 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:49 |  | 2025 |  |  | 2025-11-05 10:50 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003013 | OSPWO0024451
JED-HRR2-WAFA-28 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:49 | 2026-03-26 11:49 | 2026 |  |  | 2026-03-26 11:50 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000676 | OSPWO0034849 | RITM0095102 |  | 2378601
JED-HRR2-WAFA-101 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:14 | 2026-02-15 22:14 | 2026 |  |  | 2026-03-01 15:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000635 | OSPWO0032350 | RITM0091370 |  | 2378501
TAI-QAIM-HASH-F4 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:46 |  | 2026 |  |  | 2026-01-06 14:46 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000108 | OSPWO0026988
TAI-MELI-JUBR-10 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:03 |  | 2026 |  |  | 2026-01-28 14:03 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028432 | RITM0088789 |  | 2652504 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-99 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:22 |  | 2026 |  |  | 2026-02-16 12:22 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000522 | OSPWO0032407
JED-HRR2-WAFA-57 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026 |  |  | 2026-03-26 12:33 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000705 | OSPWO0034869 | RITM0095113 |  | 2378601
JED-HRR2-WAFA-89 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:16 |  | 2026 |  |  | 2026-02-16 12:16 | 0 | 0 | 0 | 0 | 23 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000623 | OSPWO0032386 | RITM0091409 |  | 2378501
JED-HRR2-WAFA-91 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:18 |  | 2026 |  |  | 2026-02-16 12:18 | 0 | 0 | 0 | 0 | 21 | 65 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000625 | OSPWO0032394 | RITM0091413 |  | 2378501
JED-HRR2-RIYA-47 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:45 |  | 2025 |  |  | 2025-11-05 10:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003008 | OSPWO0024431
JED-HRR2-WAFA-79 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:18 | 2026-02-15 22:18 | 2026 |  |  | 2026-03-01 15:42 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000613 | OSPWO0032358 | RITM0091374 |  | 2378501
JED-HRR2-RIYA-64 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 13:54 |  | 2026 |  |  | 2026-01-28 13:55 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000332 | OSPWO0028393
BAH-BCPS-SARA-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 470440 | 470440 | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027713 | RITM0087559 |  | 6558101
BAH-BCPS-ADEL-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000218 | OSPWO0027718
| 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-03-08 10:30 | 2026-03-08 10:30 | 2026 |  |  | 2026-03-08 10:30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034192 | RITM0094080 |  | 2241601
JED-HRR2-RIYA-37 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:39 |  | 2025 |  |  | 2025-11-05 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002999 | OSPWO0024395
JED-HRR2-RIYA-64 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:43 |  | 2026 |  |  | 2026-01-28 14:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000382 | OSPWO0028637
JED-HRR2-RIYA-70 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:17 |  | 2026 |  |  | 2026-01-28 14:17 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028508 | RITM0088831 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-GHAD-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:26 |  | 2026 |  |  | 2026-01-14 14:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000247 | OSPWO0027724
BAH-BCPS-AREE-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 531632 | 531632 | 2026-01-14 14:27 |  | 2026 |  |  | 2026-01-14 14:27 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027727 | RITM0087567 |  | 6574301
BAH-BCPS-BADR-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1295656 | 1295656 | 2026-01-14 14:30 |  | 2026 |  |  | 2026-01-14 14:30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027741 | RITM0087574 |  | 6574901
JED-HRR2-RIYA-70 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:17 |  | 2026 |  |  | 2026-01-28 14:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000390 | OSPWO0028509
JED-HRR2-WAFA-90 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:16 |  | 2026 |  |  | 2026-02-16 12:16 | 0 | 0 | 0 | 0 |  |  | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000600 | OSPWO0032388 | RITM0091410 |  | 2378501
TAI-QRAU-SABA-02 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1280045 | 1280045 | 2026-03-16 01:28 | 2026-03-16 01:28 | 2026 |  |  | 2026-03-16 01:29 | 0 | 0 | 0 | 0 |  |  | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002374 | OSPWO0034505 | RITM0094604 |  | 2651701
JED-HRR2-WAFA-84 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:08 |  | 2026 |  |  | 2026-03-01 15:40 | 0 | 0 | 0 | 0 |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000594 | OSPWO0032364 | RITM0091398 |  | 2378501
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:10 |  | 2026 |  |  | 2026-01-28 15:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028770 | RITM0088966 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
| 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-03-08 10:35 | 2026-03-08 10:35 | 2026 |  |  | 2026-03-08 10:36 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034193 | RITM0094081 |  | 2374501
JED-HRR2-WAFA-10 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:09 | 2026-03-26 11:09 | 2026 |  |  | 2026-03-26 11:09 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000683 | OSPWO0034803 | RITM0095077 |  | 2378601
TAI-MELI-JUBR-10 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:51 |  | 2026 |  |  | 2026-01-28 14:51 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028676 | RITM0088916 |  | 2652504 |  | To close the pending held orders in the mentioned cluster
TAB-TBK5-MASY-F1 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  | 2026 |  |  | 2026-01-07 12:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000138 | OSPWO0027080
JED-HRR2-WAFA-85 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:10 |  | 2026 |  |  | 2026-03-01 15:39 | 0 | 0 | 0 | 0 |  |  | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000595 | OSPWO0032368 | RITM0091400 |  | 2378501
JED-HRR2-WAFA-85 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:10 |  | 2026 |  |  | 2026-02-16 12:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000464 | OSPWO0032369
JED-HRR2-RIYA-38 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 932366 | 932366 | 2025-11-05 10:39 |  | 2025 |  |  | 2025-11-10 17:50 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000693 | OSPWO0024396 | RITM0076815 |  | 2387401
JED-HRR2-WAFA-16 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:19 | 2026-03-26 11:19 | 2026 |  |  | 2026-03-26 11:20 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000664 | OSPWO0034813 | RITM0095083 |  | 2378601
JED-HRR2-WAFA-173 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:11 | 2026-03-17 11:11 | 2026 |  |  | 2026-03-17 11:12 | 0 | 0 | 0 | 0 | 125 | 125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0001013 | OSPWO0034608 | RITM0094713 |  | 2378501
JED-HRR2-RIYA-64 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:43 |  | 2026 |  |  | 2026-01-28 14:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028636 | RITM0088896 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-145 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:09 | 2026-03-17 11:09 | 2026 |  |  | 2026-03-17 11:09 | 0 | 0 | 0 | 0 | 4 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000985 | OSPWO0034604 | RITM0094711 |  | 2378501
JED-HRR2-WAFA-160 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:04 | 2026-03-17 11:04 | 2026 |  |  | 2026-03-17 11:04 | 0 | 0 | 0 | 0 | 9 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034596 | RITM0094707 |  | 2378501
JED-HRR2-WAFA-22 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:35 | 2026-03-17 11:35 | 2026 |  |  | 2026-03-17 11:36 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000670 | OSPWO0034632 | RITM0094725 |  | 2378601
JED-FRDS-BUHA-24 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:09 |  | 2025 |  |  | 2025-12-16 13:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003234 | OSPWO0025990
JED-HRR2-WAFA-57 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:33 | 2026-03-26 12:33 | 2026 |  |  | 2026-03-26 12:33 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000730 | OSPWO0034871 | RITM0095114 |  | 2378601
JED-HRR2-WAFA-15 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:16 | 2026-03-26 11:16 | 2026 |  |  | 2026-03-26 11:17 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000663 | OSPWO0034809 | RITM0095081 |  | 2378601
BAH-BCPS-RADW-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:25 |  | 2026 |  |  | 2026-01-14 14:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000246 | OSPWO0027720
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:20 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000395 | OSPWO0028519
JED-FRDS-MANA-07 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:13 |  | 2025 |  |  | 2025-11-05 10:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002980 | OSPWO0024319
JED-HRR2-WAFA-16 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:19 | 2026-03-26 11:19 | 2026 |  |  | 2026-03-26 11:20 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000689 | OSPWO0034815 | RITM0095084 |  | 2378601
JED-HRR2-WAFA-84 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:09 |  | 2026 |  |  | 2026-03-01 15:40 | 0 | 0 | 0 | 0 | 14 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000618 | OSPWO0032366 | RITM0091399 |  | 2378501
TAB-TBK5-MASY-03 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  | 2026 |  |  | 2026-01-07 12:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000136 | OSPWO0027076
JED-HRR2-RIYA-57 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:57 |  | 2026 |  |  | 2026-01-06 14:58 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000118 | OSPWO0027042
JUB-DHAH-AZIZ-16 | 0 | EASTERN REGION | FTTH | Fiber | 1 - PIP Submission | 66919 | 66919 | 2026-01-04 09:15 | 2026-01-04 09:15 | 2026 |  |  | 2026-01-04 09:16 | 0 | 0 | 0 | 0 | 18 | 57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-04 09:16 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026613 | RITM0084725 |  | 3541601
JED-FRDS-MANA-21 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:18 |  | 2025 |  |  | 2025-11-05 10:20 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002974 | OSPWO0024349
BAH-BCPS-MASA-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2295598 | 2295598 | 2026-01-14 14:22 |  | 2026 |  |  | 2026-01-14 14:22 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027707 | RITM0087556 |  | 6557601
JED-HRR2-RIYA-47 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:45 |  | 2025 |  |  | 2025-11-05 10:46 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002994 | OSPWO0024429
| 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2025-12-16 19:31 | 2025-12-16 19:31 | 2025 |  |  | 2025-12-16 19:31 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026041 | RITM0079749 |  | 2241301
TAI-MELI-FIYS-01 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:42 |  | 2026 |  |  | 2026-01-06 14:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000106 | OSPWO0026974
JED-HRR2-RIYA-42 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:42 |  | 2025 |  |  | 2025-11-05 10:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003003 | OSPWO0024411
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 870180 | 870180 | 2026-01-15 16:24 |  | 2026 |  |  | 2026-01-26 08:53 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-26 08:53 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000762 | OSPWO0027799 | RITM0087655 |  | 2387401
TAI-QAIM-HASH-08 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:44 |  | 2026 |  |  | 2026-01-06 14:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000108 | OSPWO0026982
BAH-BCPS-BADR-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:30 |  | 2026 |  |  | 2026-01-14 14:30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000224 | OSPWO0027742
JED-HRR2-WAFA-17 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:21 | 2026-03-26 11:21 | 2026 |  |  | 2026-03-26 11:22 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000665 | OSPWO0034817 | RITM0095085 |  | 2378601
BAH-BCPS-NAIM-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:29 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000223 | OSPWO0027736
JED-HRR2-FURO-29 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:10 | 2026-02-15 22:10 | 2026 |  |  | 2026-03-01 15:46 | 0 | 0 | 0 | 0 |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000585 | OSPWO0032344 | RITM0091368 |  | 2378501
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:07 |  | 2026 |  |  | 2026-01-28 15:07 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028756 | RITM0088959 |  | 2656301 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-RADW-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1483547 | 1483547 | 2026-01-14 14:26 |  | 2026 |  |  | 2026-01-14 14:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027725 | RITM0087566 |  | 6574301
JED-FRDS-BUHA-23 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:09 |  | 2025 |  |  | 2025-12-16 13:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003264 | OSPWO0025988
JED-HRR2-WAFA-51 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:28 | 2026-03-26 12:28 | 2026 |  |  | 2026-03-26 12:28 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000699 | OSPWO0034861 | RITM0095109 |  | 2378601
JED-HRR2-WAFA-19 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:28 | 2026-03-26 11:28 | 2026 |  |  | 2026-03-26 11:28 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000692 | OSPWO0034827 | RITM0095090 |  | 2378601
JED-HRR2-SALH-08 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:09 |  | 2026 |  |  | 2026-01-28 15:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028766 | RITM0088964 |  | 2376401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-80 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:07 |  | 2026 |  |  | 2026-02-16 12:07 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000614 | OSPWO0032360 | RITM0091396 |  | 2378501
JED-HRR2-WAFA-80 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:07 |  | 2026 |  |  | 2026-02-16 12:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000462 | OSPWO0032361
JED-FRDS-MANA-08 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:13 |  | 2025 |  |  | 2025-11-05 10:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002967 | OSPWO0024321
JED-FRDS-MANA-16 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:16 |  | 2025 |  |  | 2025-11-05 10:17 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002984 | OSPWO0024335
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:21 |  | 2026 |  |  | 2026-01-28 14:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028524 | RITM0088839 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-42 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:25 | 2026-03-26 12:25 | 2026 |  |  | 2026-03-26 12:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000690 | OSPWO0034857 | RITM0095107 |  | 2378601
JED-HRR2-WAFA-18 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:25 | 2026-03-26 11:25 | 2026 |  |  | 2026-03-26 11:25 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000691 | OSPWO0034823 | RITM0095087 |  | 2378601
JED-FRDS-MANA-18 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:17 |  | 2025 |  |  | 2025-11-05 10:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002985 | OSPWO0024339
BAH-BCPS-AREE-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:28 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000249 | OSPWO0027732
JED-FRDS-AMWA-11 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 79735 | 79735 | 2026-03-28 21:53 | 2026-03-28 21:53 | 2026 |  |  | 2026-03-28 21:54 | 0 | 0 | 0 | 0 | 33 | 104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001046 | OSPWO0034884 | RITM0095199 |  | 2381401
TAI-QAIM-QIAA-F2 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:49 |  | 2026 |  |  | 2026-01-06 14:49 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000113 | OSPWO0027002
TAI-MELI-JALL-01 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:44 | 2026-03-17 11:44 | 2026 |  |  | 2026-03-17 11:45 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034648 | RITM0094733 |  | 2652306
JED-HRR2-WAFA-87 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:12 |  | 2026 |  |  | 2026-03-01 15:47 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000597 | OSPWO0032376 | RITM0091404 |  | 2378501
TAB-TBK5-MASY-04 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  | 2026 |  |  | 2026-01-07 12:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000137 | OSPWO0027078
JED-FRDS-MANA-21 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:19 |  | 2025 |  |  | 2025-11-05 10:20 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002988 | OSPWO0024351
JED-FRDS-MANA-22 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:19 |  | 2025 |  |  | 2025-11-05 10:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002975 | OSPWO0024353
JED-FRDS-BUHA-23 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 98385 | 98385 | 2025-12-16 13:09 |  | 2025 |  |  | 2025-12-16 13:09 | 0 | 0 | 0 | 0 | 48 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002800 | OSPWO0025987 | RITM0079691 |  | 2382301
JED-HRR2-WAFA-170 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:27 | 2026-03-17 11:27 | 2026 |  |  | 2026-03-17 11:27 | 0 | 0 | 0 | 0 | 21 | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0001010 | OSPWO0034622 | RITM0094719 |  | 2378501
SAM-SMTH-TURS-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:39 |  | 2025 |  |  | 2025-11-16 10:41 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003094 | OSPWO0024850
JED-HRR2-RIYA-27 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:35 |  | 2025 |  |  | 2025-11-05 10:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002980 | OSPWO0024373
JED-HRR2-RIYA-43 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:42 |  | 2025 |  |  | 2025-11-05 10:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003004 | OSPWO0024415
JED-HRR2-WAFA-11 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:39 | 2026-03-17 11:39 | 2026 |  |  | 2026-03-17 11:40 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000659 | OSPWO0034640 | RITM0094729 |  | 2378601
JED-HRR2-WAFA-137 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:16 | 2026-02-15 22:16 | 2026 |  |  | 2026-03-01 15:43 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000647 | OSPWO0032354 | RITM0091372 |  | 2378501
JED-HRR2-WAFA-05 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:00 | 2026-03-26 11:00 | 2026 |  |  | 2026-03-26 11:00 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000653 | OSPWO0034789 | RITM0095071 |  | 2378601
JED-HRR2-RIYA-36 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:38 |  | 2025 |  |  | 2025-11-05 10:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002984 | OSPWO0024389
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028762 | RITM0088962 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-78 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026 |  |  | 2026-03-26 12:35 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000751 | OSPWO0034875 | RITM0095116 |  | 2378601
JED-FRDS-BUHA-29 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:14 |  | 2025 |  |  | 2025-12-16 13:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003270 | OSPWO0026012
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:18 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000392 | OSPWO0028513
JED-HRR2-WAFA-86 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:11 |  | 2026 |  |  | 2026-02-16 12:12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000465 | OSPWO0032373
JED-FRDS-BUHA-23 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:08 |  | 2025 |  |  | 2025-12-16 13:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003233 | OSPWO0025986
TAI-QRAU-MUAS-01 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:52 |  | 2026 |  |  | 2026-01-06 14:52 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027019 | RITM0086065 |  | 2652202
JED-FRDS-BUHA-30 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:14 |  | 2025 |  |  | 2025-12-16 13:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003240 | OSPWO0026014
JED-HRR2-WAFA-92 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:19 |  | 2026 |  |  | 2026-02-16 12:19 | 0 | 0 | 0 | 0 | 11 | 82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000626 | OSPWO0032398 | RITM0091415 |  | 2378501
JED-HRR2-WAFA-91 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:17 |  | 2026 |  |  | 2026-02-16 12:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000470 | OSPWO0032393
JED-HRR2-WAFA-07 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:03 | 2026-03-26 11:03 | 2026 |  |  | 2026-03-26 11:04 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000655 | OSPWO0034793 | RITM0095073 |  | 2378601
JED-HRR2-WAFA-137 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:15 | 2026-02-15 22:15 | 2026 |  |  | 2026-03-01 15:43 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000671 | OSPWO0032352 | RITM0091373 |  | 2378501
JED-HRR2-WAFA-92 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:19 |  | 2026 |  |  | 2026-02-16 12:19 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000602 | OSPWO0032396 | RITM0091414 |  | 2378501
TAI-QAIM-QIAA-10 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028514 | RITM0088834 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-78 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:35 | 2026-03-26 12:35 | 2026 |  |  | 2026-03-26 12:35 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000726 | OSPWO0034873 | RITM0095117 |  | 2378601
TAI-MELI-FIYS-01 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000446 | OSPWO0028765
SAM-SMTH-KHAD-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:39 |  | 2025 |  |  | 2025-11-16 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003093 | OSPWO0024846
JED-FRDS-BUHA-29 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 102929 | 102929 | 2025-12-16 13:14 |  | 2025 |  |  | 2025-12-16 13:14 | 0 | 0 | 0 | 0 | 49 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002806 | OSPWO0026011 | RITM0079703 |  | 2382301
JED-HRR2-RIYA-70 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:06 |  | 2026 |  |  | 2026-01-28 15:07 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000440 | OSPWO0028753
BAH-BCPS-BADR-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:29 |  | 2026 |  |  | 2026-01-14 14:30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000251 | OSPWO0027740
TAI-QRAU-MUAS-01 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:52 |  | 2026 |  |  | 2026-01-06 14:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000121 | OSPWO0027020
JED-HRR2-WAFA-89 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:15 |  | 2026 |  |  | 2026-02-16 12:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000468 | OSPWO0032385
BAH-BCPS-NAIM-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 450271 | 450271 | 2026-01-14 14:29 |  | 2026 |  |  | 2026-01-14 14:29 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027737 | RITM0087572 |  | 6574501
JED-FRDS-BUHA-27 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:12 |  | 2025 |  |  | 2025-12-16 13:12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003237 | OSPWO0026002
JED-HRR2-WAFA-90 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:17 |  | 2026 |  |  | 2026-02-16 12:17 | 0 | 0 | 0 | 0 | 23 | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000624 | OSPWO0032390 | RITM0091411 |  | 2378501
JED-FRDS-MANA-22 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:19 |  | 2025 |  |  | 2025-11-05 10:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002989 | OSPWO0024355
TAI-QAIM-QIAA-F2 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:48 |  | 2026 |  |  | 2026-01-06 14:49 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000111 | OSPWO0027000
JED-HRR2-RIYA-50 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:46 |  | 2025 |  |  | 2025-11-05 10:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003009 | OSPWO0024435
JED-HRR2-RIYA-F3 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:50 |  | 2025 |  |  | 2025-11-05 10:52 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003015 | OSPWO0024459
JED-HRR2-WAFA-15 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:17 | 2026-03-26 11:17 | 2026 |  |  | 2026-03-26 11:17 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000688 | OSPWO0034811 | RITM0095082 |  | 2378601
JED-HRR2-WAFA-99 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:21 |  | 2026 |  |  | 2026-02-16 12:22 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000473 | OSPWO0032405
JED-HRR2-WAFA-54 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 14:04 | 2026-03-17 14:04 | 2026 |  |  | 2026-03-17 14:05 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000727 | OSPWO0034670 | RITM0094747 |  | 2378601
JED-HRR2-WAFA-23 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026 |  |  | 2026-03-26 11:32 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000671 | OSPWO0034833 | RITM0095093 |  | 2378601
JED-HRR2-RIYA-65 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-09-16 11:47 |  | 2025 |  |  | 2025-09-16 11:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002695 | OSPWO0022887
JED-FRDS-MANA-20 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:18 |  | 2025 |  |  | 2025-11-05 10:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002973 | OSPWO0024345
JED-HRR2-WAFA-88 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:14 |  | 2026 |  |  | 2026-02-16 12:14 | 0 | 0 | 0 | 0 | 27 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000622 | OSPWO0032382 | RITM0091407 |  | 2378501
JED-HRR2-WAFA-88 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:14 |  | 2026 |  |  | 2026-02-16 12:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000516 | OSPWO0032383
JED-FRDS-MANA-10 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:15 |  | 2025 |  |  | 2025-11-05 10:17 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002983 | OSPWO0024331
JED-HRR2-WAFA-84 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:08 |  | 2026 |  |  | 2026-02-16 12:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000463 | OSPWO0032365
BAH-BCPS-ADEL-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 1241863 | 1241863 | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027717 | RITM0087562 |  | 6558501
JED-FRDS-MANA-F1 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:20 |  | 2025 |  |  | 2025-11-05 10:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002976 | OSPWO0024357
JED-HRR2-WAFA-141 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:07 | 2026-03-17 11:07 | 2026 |  |  | 2026-03-17 11:07 | 0 | 0 | 0 | 0 | 16 | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000981 | OSPWO0034600 | RITM0094709 |  | 2378501
JED-FRDS-MANA-20 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:18 |  | 2025 |  |  | 2025-11-05 10:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002987 | OSPWO0024347
BAH-BCPS-GHAD-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 62008 | 62008 | 2026-01-14 14:26 |  | 2026 |  |  | 2026-01-14 14:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027723 | RITM0087565 |  | 6574301
JED-HRR2-RIYA-50 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:46 |  | 2025 |  |  | 2025-11-05 10:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002995 | OSPWO0024433
JED-HRR2-RIYA-F6 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 0 | 0 | 2025-08-23 21:28 | 2025-08-23 21:28 | 2025 |  |  | 2026-03-01 12:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001504 | OSPWO0021885 | RITM0072340 |  | 2383801
JED-HRR2-WAFA-80 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:08 |  | 2026 |  |  | 2026-02-16 12:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000511 | OSPWO0032363
JED-FRDS-BUHA-25 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:10 |  | 2025 |  |  | 2025-12-16 13:11 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003266 | OSPWO0025996
JED-HRR2-WAFA-141 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:06 | 2026-03-17 11:06 | 2026 |  |  | 2026-03-17 11:07 | 0 | 0 | 0 | 0 |  |  | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000948 | OSPWO0034598 | RITM0094708 |  | 2378501
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:46 |  | 2026 |  |  | 2026-01-06 14:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000109 | OSPWO0026992
JED-HRR2-RIYA-65 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-09-16 11:47 |  | 2025 |  |  | 2025-09-16 11:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002703 | OSPWO0022889
JED-FRDS-MANA-05 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:11 |  | 2025 |  |  | 2025-11-05 10:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002964 | OSPWO0024309
JED-HRR2-WAFA-84 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:09 |  | 2026 |  |  | 2026-02-16 12:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000512 | OSPWO0032367
JED-HRR2-RIYA-35 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:37 |  | 2025 |  |  | 2025-11-05 10:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002983 | OSPWO0024385
TAI-MELI-JALL-01 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:45 | 2026-03-17 11:45 | 2026 |  |  | 2026-03-17 11:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034650 | RITM0094734 |  | 2652306
JED-HRR2-RIYA-26 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:34 |  | 2025 |  |  | 2025-11-05 10:36 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002979 | OSPWO0024369
JED-HRR2-SALH-18 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-07 15:45 |  | 2026 |  |  | 2026-01-07 15:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000143 | OSPWO0027100
JED-HRR2-WAFA-145 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:08 | 2026-03-17 11:08 | 2026 |  |  | 2026-03-17 11:09 | 0 | 0 | 0 | 0 |  |  | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000952 | OSPWO0034602 | RITM0094710 |  | 2378501
TAI-MELI-FIYS-02 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:43 |  | 2026 |  |  | 2026-01-06 14:43 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026977 | RITM0086037 |  | 2652602
JED-FRDS-BUHA-25 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 138009 | 138009 | 2025-12-16 13:10 |  | 2025 |  |  | 2025-12-16 13:10 | 0 | 0 | 0 | 0 | 71 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002802 | OSPWO0025995 | RITM0079695 |  | 2382301
TAB-TBHH-MASY-01 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  | 2026 |  |  | 2026-02-10 15:33 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000134 | OSPWO0027072
JED-HRR2-WAFA-53 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:22 | 2026-03-17 11:22 | 2026 |  |  | 2026-03-26 10:56 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000726 | OSPWO0034616 | RITM0095070 |  | 2378601
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:09 |  | 2026 |  |  | 2026-01-28 15:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028768 | RITM0088965 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-SARA-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:23 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000217 | OSPWO0027712
| 0 | MAKKAH | FTTH | Others | 1 - PIP Submission |  |  | 2026-02-11 08:54 | 2026-02-11 08:54 | 2026 |  |  | 2026-02-11 08:54 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0030093 | RITM0090257 |  | 2427301
JED-HRR2-WAFA-98 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:20 |  | 2026 |  |  | 2026-02-16 12:21 | 0 | 0 | 0 | 0 | 11 | 87 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000632 | OSPWO0032402 | RITM0091417 |  | 2378501
JED-HRR2-WAFA-18 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:25 | 2026-03-26 11:25 | 2026 |  |  | 2026-03-26 11:26 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000666 | OSPWO0034821 | RITM0095088 |  | 2378601
JED-HRR2-RIYA-52 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:46 |  | 2025 |  |  | 2025-11-05 10:48 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002996 | OSPWO0024437
BAH-BCPS-RADW-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 227778 | 227778 | 2026-01-14 14:25 |  | 2026 |  |  | 2026-01-14 14:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027719 | RITM0087563 |  | 6574301
JED-HRR2-RIYA-52 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:47 |  | 2025 |  |  | 2025-11-05 10:48 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003010 | OSPWO0024439
JED-HRR2-RIYA-26 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:35 |  | 2025 |  |  | 2025-11-05 10:36 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002993 | OSPWO0024371
JED-HRR2-WAFA-88 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:14 |  | 2026 |  |  | 2026-02-16 12:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000467 | OSPWO0032381
JED-HRR2-WAFA-53 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:21 | 2026-03-17 11:21 | 2026 |  |  | 2026-03-26 10:57 | 0 | 0 | 0 | 0 |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-26 10:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000726 | OSPWO0034614 | RITM0094716 |  | 2378601
JED-HRR2-WAFA-170 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:26 | 2026-03-17 11:26 | 2026 |  |  | 2026-03-17 11:27 | 0 | 0 | 0 | 0 |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000977 | OSPWO0034620 | RITM0094718 |  | 2378501
JED-HRR2-RIYA-42 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:41 |  | 2025 |  |  | 2025-11-05 10:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002989 | OSPWO0024409
TAI-MELI-FIYS-02 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:43 |  | 2026 |  |  | 2026-01-06 14:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000107 | OSPWO0026978
JED-HRR2-SALH-08 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:20 |  | 2026 |  |  | 2026-01-28 14:20 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028522 | RITM0088838 |  | 2376401 |  | To close the pending held orders in the mentioned cluster
TAI-MELI-FIYS-02 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:43 |  | 2026 |  |  | 2026-01-06 14:43 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026975 | RITM0086036 |  | 2652602
JED-HRR2-RIYA-53 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:47 |  | 2025 |  |  | 2025-11-05 10:49 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003011 | OSPWO0024443
JED-HRR2-WAFA-160 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:03 | 2026-03-17 11:03 | 2026 |  |  | 2026-03-17 11:04 | 0 | 0 | 0 | 0 |  |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0034594 | RITM0094706 |  | 2378501
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:07 |  | 2026 |  |  | 2026-01-28 15:07 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000442 | OSPWO0028757
JED-FRDS-BUHA-22 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:07 |  | 2025 |  |  | 2025-12-16 13:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003232 | OSPWO0025982
JED-HRR2-SALH-08 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:09 |  | 2026 |  |  | 2026-01-28 15:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000447 | OSPWO0028767
BAH-BCPS-ARIF-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:27 |  | 2026 |  |  | 2026-01-14 14:28 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000248 | OSPWO0027730
JED-HRR2-WAFA-79 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:18 | 2026-02-15 22:18 | 2026 |  |  | 2026-03-01 15:42 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000589 | OSPWO0032356 | RITM0091375 |  | 2378501
JED-HRR2-WAFA-14 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:33 | 2026-03-17 11:33 | 2026 |  |  | 2026-03-17 11:34 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000662 | OSPWO0034628 | RITM0094723 |  | 2378601
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:21 |  | 2026 |  |  | 2026-01-28 14:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000398 | OSPWO0028525
JED-HRR2-WAFA-20 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:29 | 2026-03-26 11:29 | 2026 |  |  | 2026-03-26 11:30 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000668 | OSPWO0034829 | RITM0095091 |  | 2378601
SAM-SMTH-MASO-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:40 |  | 2025 |  |  | 2025-11-16 10:41 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003095 | OSPWO0024854
JED-FRDS-MANA-18 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:16 |  | 2025 |  |  | 2025-11-05 10:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002971 | OSPWO0024337
JED-HRR2-WAFA-53 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:24 | 2026-03-17 11:24 | 2026 |  |  | 2026-03-17 11:24 | 0 | 0 | 0 | 0 |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000701 | OSPWO0034618 | RITM0094717 |  | 2378601
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:47 |  | 2026 |  |  | 2026-01-06 14:48 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000111 | OSPWO0026994
BAH-BCPS-MASA-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:23 |  | 2026 |  |  | 2026-01-14 14:23 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000243 | OSPWO0027710
BAH-BCPS-NAIM-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2899644 | 2899644 | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:28 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027735 | RITM0087571 |  | 6574501
JED-HRR2-WAFA-02 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:38 | 2026-03-17 11:38 | 2026 |  |  | 2026-03-17 11:38 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000675 | OSPWO0034638 | RITM0094727 |  | 2378601
JED-HRR2-RIYA-57 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:58 |  | 2026 |  |  | 2026-01-06 14:58 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000127 | OSPWO0027044
TAI-QAIM-QIAA-09 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000394 | OSPWO0028517
JED-HRR2-RIYA-54 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:48 |  | 2025 |  |  | 2025-11-05 10:49 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002998 | OSPWO0024445
BAH-BCPS-AREE-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 79479 | 79479 | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:28 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027731 | RITM0087569 |  | 6574301
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:09 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000445 | OSPWO0028763
JED-HRR2-WAFA-54 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 14:03 | 2026-03-17 14:03 | 2026 |  |  | 2026-03-17 14:05 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000702 | OSPWO0034668 | RITM0094746 |  | 2378601
SHA-ADAR-DAIR-01 | 0 | JIZAN | FEP-Phase1 | Fiber |  |  |  | 2025-11-16 10:38 |  | 2025 |  |  | 2025-11-16 10:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPFI0003092 | OSPWO0024842
JED-FRDS-MANA-17 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:57 |  | 2026 |  |  | 2026-01-06 14:57 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000126 | OSPWO0027040
MAK-WHD2-QASA-15 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-07 15:46 |  | 2026 |  |  | 2026-01-07 17:57 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000131 | OSPWO0027106
TAI-QAIM-HASH-09 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:45 |  | 2026 |  |  | 2026-01-06 14:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000107 | OSPWO0026984
JED-FRDS-MANA-06 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:12 |  | 2025 |  |  | 2025-11-05 10:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002965 | OSPWO0024313
JED-FRDS-MANA-19 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:17 |  | 2025 |  |  | 2025-11-05 10:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002972 | OSPWO0024341
BAH-BCPS-BADR-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 198041 | 198041 | 2026-01-14 14:29 |  | 2026 |  |  | 2026-01-14 14:29 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027739 | RITM0087573 |  | 6574901
TAI-QRAU-SABA-03 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 805902 | 805902 | 2026-03-16 01:30 | 2026-03-16 01:30 | 2026 |  |  | 2026-03-16 01:31 | 0 | 0 | 0 | 0 |  |  | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002375 | OSPWO0034509 | RITM0094605 |  | 2651701
JED-HRR2-WAFA-98 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:20 |  | 2026 |  |  | 2026-02-16 12:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000472 | OSPWO0032401
SAM-SMTH-MAJA-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:41 |  | 2025 |  |  | 2025-11-16 10:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003077 | OSPWO0024860
SAM-SMTH-KHAD-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:38 |  | 2025 |  |  | 2025-11-16 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003073 | OSPWO0024844
JED-FRDS-MANA-10 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:15 |  | 2025 |  |  | 2025-11-05 10:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002969 | OSPWO0024329
JED-HRR2-WAFA-22 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:36 | 2026-03-17 11:36 | 2026 |  |  | 2026-03-17 11:36 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000695 | OSPWO0034634 | RITM0094726 |  | 2378601
BAH-BCPS-GHAD-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:25 |  | 2026 |  |  | 2026-01-14 14:26 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000219 | OSPWO0027722
JED-HRR2-RIYA-27 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:35 |  | 2025 |  |  | 2025-11-05 10:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002994 | OSPWO0024375
TAI-QAIM-QIAA-10 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000393 | OSPWO0028515
JED-HRR2-WAFA-89 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:16 |  | 2026 |  |  | 2026-02-16 12:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000517 | OSPWO0032387
| 0 | MAKKAH | FTTH | Others | 2 - PIP Approval |  |  | 2025-11-16 22:33 | 2025-11-16 22:33 | 2025 |  | 2026-01-01 | 2026-03-16 13:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Survey | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0024971 | RITM0077704 |  | 2254201
JED-HRR2-WAFA-87 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:13 |  | 2026 |  |  | 2026-02-16 12:13 | 0 | 0 | 0 | 0 | 37 | 58 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000621 | OSPWO0032378 | RITM0091405 |  | 2378501
MAK-WHD2-QASA-15 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 490966 | 490966 | 2026-01-07 15:46 |  | 2026 |  |  | 2026-01-07 17:57 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-07 17:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001763 | OSPWO0027105 | RITM0086640 |  | 2457701
TAI-MELI-JUBR-10 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:03 |  | 2026 |  |  | 2026-01-28 14:03 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000352 | OSPWO0028433
JED-HRR2-WAFA-99 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:22 |  | 2026 |  |  | 2026-02-16 12:22 | 0 | 0 | 0 | 0 | 9 | 90 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000633 | OSPWO0032406 | RITM0091419 |  | 2378501
JED-FRDS-BUHA-24 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 139770 | 139770 | 2025-12-16 13:10 |  | 2025 |  |  | 2025-12-16 13:10 | 0 | 0 | 0 | 0 | 71 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002801 | OSPWO0025991 | RITM0079693 |  | 2382301
TAI-QAIM-QIAA-11 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:18 |  | 2026 |  |  | 2026-03-07 23:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000391 | OSPWO0028511
TAI-MELI-JUFE-04 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:10 |  | 2026 |  |  | 2026-01-28 15:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028772 | RITM0088967 |  | 2652502 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-08 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:18 |  | 2026 |  |  | 2026-01-28 14:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028512 | RITM0088833 |  | 2656301 |  | To close the pending held orders in the mentioned cluster
SHA-ADAR-DAIR-01 | 0 | JIZAN | FEP-Phase1 | Civil |  |  |  | 2025-11-16 10:38 |  | 2025 |  |  | 2025-11-16 10:39 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510OSPCI0003072 | OSPWO0024840
TAI-MELI-FIYS-01 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 600000 | 600000 | 2026-01-06 14:42 |  | 2026 |  |  | 2026-01-06 14:42 | 0 | 0 | 0 | 0 |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026971 | RITM0086034 |  | 2652602
JED-HRR2-WAFA-10 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:08 | 2026-03-26 11:08 | 2026 |  |  | 2026-03-26 11:09 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000658 | OSPWO0034801 | RITM0095078 |  | 2378601
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-15 16:24 |  | 2026 |  |  | 2026-01-26 08:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000271 | OSPWO0027802
JED-HRR2-RIYA-34 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:36 |  | 2025 |  |  | 2025-11-05 10:38 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002982 | OSPWO0024381
JED-HRR2-TEEB-11 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 14:52 |  | 2026 |  |  | 2026-01-28 14:52 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028682 | RITM0088919 |  | 2383501 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-52 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:30 | 2026-03-26 12:30 | 2026 |  |  | 2026-03-26 12:31 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000725 | OSPWO0034867 | RITM0095111 |  | 2378601
JED-FRDS-BUHA-30 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 115971 | 115971 | 2025-12-16 13:15 |  | 2025 |  |  | 2025-12-16 13:15 | 0 | 0 | 0 | 0 | 36 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002807 | OSPWO0026015 | RITM0079705 |  | 2382301
JED-HRR2-WAFA-90 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:16 |  | 2026 |  |  | 2026-02-16 12:17 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000469 | OSPWO0032389
JED-HRR2-RIYA-38 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:39 |  | 2025 |  |  | 2025-11-10 17:52 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002986 | OSPWO0024397
JED-FRDS-AMWA-11 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 472544 | 472544 | 2026-03-28 21:52 | 2026-03-28 21:52 | 2026 |  |  | 2026-03-28 21:53 | 0 | 0 | 0 | 0 |  |  | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001018 | OSPWO0034882 | RITM0095198 |  | 2381401
JED-FRDS-BUHA-24 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:10 |  | 2025 |  |  | 2025-12-16 13:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003265 | OSPWO0025992
JED-HRR2-WAFA-20 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:30 | 2026-03-26 11:30 | 2026 |  |  | 2026-03-26 11:30 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000693 | OSPWO0034831 | RITM0095092 |  | 2378601
JED-HRR2-WAFA-101 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-15 22:13 | 2026-02-15 22:13 | 2026 |  |  | 2026-03-01 15:45 | 0 | 0 | 0 | 0 |  |  | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000611 | OSPWO0032348 | RITM0091371 |  | 2378501
JED-HRR2-RIYA-45 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:43 |  | 2025 |  |  | 2025-11-05 10:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002992 | OSPWO0024421
JED-HRR2-RIYA-25 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:34 |  | 2025 |  |  | 2025-11-05 10:35 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002978 | OSPWO0024365
TAI-QAIM-QIAA-09 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000444 | OSPWO0028761
JED-FRDS-BUHA-F2 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 693462 | 693462 | 2025-12-16 13:15 |  | 2025 |  |  | 2025-12-16 13:16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002809 | OSPWO0026019 | RITM0079707 |  | 2382301
TAI-MELI-FIYS-01 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:42 |  | 2026 |  |  | 2026-01-06 14:43 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000104 | OSPWO0026972
JED-HRR2-WAFA-173 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:11 | 2026-03-17 11:11 | 2026 |  |  | 2026-03-17 11:12 | 0 | 0 | 0 | 0 |  |  | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000980 | OSPWO0034606 | RITM0094712 |  | 2378501
TAI-MELI-JUBR-10 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:51 |  | 2026 |  |  | 2026-01-28 14:51 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000402 | OSPWO0028677
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:41 |  | 2025 |  |  | 2025-11-10 17:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003002 | OSPWO0024407
JED-HRR2-WAFA-80 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:08 |  | 2026 |  |  | 2026-03-01 15:41 | 0 | 0 | 0 | 0 | 11 | 86 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000590 | OSPWO0032362 | RITM0091397 |  | 2378501
JED-HRR2-WAFA-87 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:13 |  | 2026 |  |  | 2026-02-16 12:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000515 | OSPWO0032379
JED-HRR2-WAFA-91 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:18 |  | 2026 |  |  | 2026-02-16 12:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000519 | OSPWO0032395
JED-FRDS-BUHA-30 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:15 |  | 2025 |  |  | 2025-12-16 13:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003271 | OSPWO0026016
JED-FRDS-BUHA-28 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:12 |  | 2025 |  |  | 2025-12-16 13:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003238 | OSPWO0026006
JED-HRR2-RIYA-64 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 13:54 |  | 2026 |  |  | 2026-01-28 13:54 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028392 | RITM0088769 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-ARIF-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:29 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000222 | OSPWO0027734
TAI-QRAU-SABA-03 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 144855 | 144855 | 2026-03-16 01:31 | 2026-03-16 01:31 | 2026 |  |  | 2026-03-16 01:31 | 0 | 0 | 0 | 0 | 88 | 185 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002389 | OSPWO0034511 | RITM0094606 |  | 2651701
JED-FRDS-BUHA-F2 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:15 |  | 2025 |  |  | 2025-12-16 13:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003272 | OSPWO0026020
BAH-BCPS-MASA-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:22 |  | 2026 |  |  | 2026-01-14 14:23 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000216 | OSPWO0027708
TAI-QAIM-HASH-09 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:45 |  | 2026 |  |  | 2026-01-06 14:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000109 | OSPWO0026986
BAH-BCPS-SARA-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 2999446 | 2999446 | 2026-01-14 14:23 |  | 2026 |  |  | 2026-01-14 14:23 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027711 | RITM0087558 |  | 6558101
TAI-QAIM-QIAA-10 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:07 |  | 2026 |  |  | 2026-01-28 15:07 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028758 | RITM0088960 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
TAI-QRAU-SABA-05 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 891498 | 891498 | 2026-03-16 01:35 | 2026-03-16 01:35 | 2026 |  |  | 2026-03-16 01:35 | 0 | 0 | 0 | 0 |  |  | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002377 | OSPWO0034517 | RITM0094610 |  | 2651701
JED-HRR2-WAFA-09 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026 |  |  | 2026-03-26 11:06 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000682 | OSPWO0034799 | RITM0095076 |  | 2378601
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:09 |  | 2026 |  |  | 2026-01-28 15:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000448 | OSPWO0028769
JED-HRR2-RIYA-34 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:37 |  | 2025 |  |  | 2025-11-05 10:38 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002996 | OSPWO0024383
JED-HRR2-RIYA-46 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:45 |  | 2025 |  |  | 2025-11-05 10:46 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003007 | OSPWO0024427
JED-HRR2-WAFA-32 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:24 | 2026-03-26 12:24 | 2026 |  |  | 2026-03-26 12:24 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000705 | OSPWO0034855 | RITM0095105 |  | 2378601
JED-HRR2-WAFA-06 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:29 | 2026-03-17 11:29 | 2026 |  |  | 2026-03-17 11:30 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000654 | OSPWO0034624 | RITM0094720 |  | 2378601
JED-HRR2-RIYA-39 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:40 |  | 2025 |  |  | 2025-11-05 10:41 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002987 | OSPWO0024401
JED-HRR2-WAFA-23 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:32 | 2026-03-26 11:32 | 2026 |  |  | 2026-03-26 11:32 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000696 | OSPWO0034835 | RITM0095094 |  | 2378601
JED-FRDS-MANA-16 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:16 |  | 2025 |  |  | 2025-11-05 10:17 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002970 | OSPWO0024333
JED-HRR2-RIYA-54 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:48 |  | 2025 |  |  | 2025-11-05 10:50 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003012 | OSPWO0024447
JED-HRR2-SALH-08 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:20 |  | 2026 |  |  | 2026-01-28 14:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000397 | OSPWO0028523
JED-HRR2-WAFA-13 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026 |  |  | 2026-03-26 11:12 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000686 | OSPWO0034807 | RITM0095079 |  | 2378601
JED-HRR2-WAFA-27 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:44 | 2026-03-26 11:44 | 2026 |  |  | 2026-03-26 11:45 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000700 | OSPWO0034847 | RITM0095101 |  | 2378601
JED-HRR2-RIYA-39 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:40 |  | 2025 |  |  | 2025-11-05 10:42 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003001 | OSPWO0024403
BAH-BCPS-ADEL-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000245 | OSPWO0027716
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1020256 | 1020256 | 2025-11-05 10:41 |  | 2025 |  |  | 2025-11-10 17:52 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000786 | OSPWO0024404 | RITM0076819 |  | 2387401
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH-Expansion | Civil |  |  |  | 2026-01-28 14:21 |  | 2026 |  |  | 2026-01-28 14:22 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000399 | OSPWO0028527
JED-FRDS-BUHA-29 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:13 |  | 2025 |  |  | 2025-12-16 13:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003239 | OSPWO0026010
TAI-QAIM-QIAA-11 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:06 |  | 2026 |  |  | 2026-03-07 23:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-07 23:37 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028754 | RITM0088958 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-32 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:23 | 2026-03-26 12:23 | 2026 |  |  | 2026-03-26 12:24 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000680 | OSPWO0034853 | RITM0095106 |  | 2378601
JED-HRR2-RIYA-44 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:43 |  | 2025 |  |  | 2025-11-05 10:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002991 | OSPWO0024417
JED-FRDS-MANA-05 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:12 |  | 2025 |  |  | 2025-11-05 10:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002978 | OSPWO0024311
JED-HRR2-RIYA-41 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:41 |  | 2025 |  |  | 2025-11-10 17:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002988 | OSPWO0024405
BAH-BCPS-ARIF-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 67224 | 67224 | 2026-01-14 14:27 |  | 2026 |  |  | 2026-01-14 14:27 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027729 | RITM0087568 |  | 6574301
JED-HRR2-WAFA-09 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:06 | 2026-03-26 11:06 | 2026 |  |  | 2026-03-26 11:06 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000657 | OSPWO0034797 | RITM0095075 |  | 2378601
TAI-QAIM-QIAA-09 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028516 | RITM0088835 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
BAH-BCPS-MASA-01 | 0 | BAHA | FEP-Phase1 | Fiber | 1 - PIP Submission | 369663 | 369663 | 2026-01-14 14:23 |  | 2026 |  |  | 2026-01-14 14:23 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027709 | RITM0087557 |  | 6557601
JED-HRR2-RIYA-36 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:38 |  | 2025 |  |  | 2025-11-05 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002998 | OSPWO0024391
JED-HRR2-WAFA-17 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:22 | 2026-03-26 11:22 | 2026 |  |  | 2026-03-26 11:22 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000690 | OSPWO0034819 | RITM0095086 |  | 2378601
JED-HRR2-WAFA-85 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:10 |  | 2026 |  |  | 2026-02-16 12:11 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000513 | OSPWO0032371
JED-HRR2-WAFA-92 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:19 |  | 2026 |  |  | 2026-02-16 12:20 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000520 | OSPWO0032399
TAI-QRAU-SABA-04 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 1343637 | 1343637 | 2026-03-16 01:32 | 2026-03-16 01:32 | 2026 |  |  | 2026-03-16 01:33 | 0 | 0 | 0 | 0 |  |  | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002376 | OSPWO0034513 | RITM0094607 |  | 2651701
JED-FRDS-MANA-19 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:17 |  | 2025 |  |  | 2025-11-05 10:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002986 | OSPWO0024343
JED-FRDS-MANA-08 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:14 |  | 2025 |  |  | 2025-11-05 10:15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002981 | OSPWO0024323
JED-HRR2-WAFA-92 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-02-16 12:19 |  | 2026 |  |  | 2026-02-16 12:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000471 | OSPWO0032397
JED-FRDS-MANA-06 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:12 |  | 2025 |  |  | 2025-11-05 10:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002979 | OSPWO0024315
JED-FRDS-BUHA-26 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 139597 | 139597 | 2025-12-16 13:11 |  | 2025 |  |  | 2025-12-16 13:11 | 0 | 0 | 0 | 0 | 46 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002803 | OSPWO0025999 | RITM0079697 |  | 2382301
JED-FRDS-BUHA-27 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 122675 | 122675 | 2025-12-16 13:12 |  | 2025 |  |  | 2025-12-16 13:12 | 0 | 0 | 0 | 0 | 56 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002804 | OSPWO0026003 | RITM0079699 |  | 2382301
JED-HRR2-WAFA-91 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:17 |  | 2026 |  |  | 2026-02-16 12:17 | 0 | 0 | 0 | 0 |  |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000601 | OSPWO0032392 | RITM0091412 |  | 2378501
TAB-TBK5-MASY-02 | 0 | TABUK | FTTH | Fiber |  |  |  | 2026-01-07 12:24 |  | 2026 |  |  | 2026-01-07 12:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607OSPFI0000135 | OSPWO0027074
JED-HRR2-WAFA-25 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:41 | 2026-03-26 11:41 | 2026 |  |  | 2026-03-26 11:42 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000698 | OSPWO0034843 | RITM0095097 |  | 2378601
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:49 |  | 2025 |  |  | 2025-11-10 17:54 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003000 | OSPWO0024453
JED-HRR2-RIYA-70 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:06 |  | 2026 |  |  | 2026-01-28 15:06 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028752 | RITM0088957 |  | 2383801 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-QIAA-11 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:18 |  | 2026 |  |  | 2026-03-07 23:37 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-03-07 23:37 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028510 | RITM0088832 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-WAFA-89 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:15 |  | 2026 |  |  | 2026-02-16 12:15 | 0 | 0 | 0 | 0 |  |  | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000599 | OSPWO0032384 | RITM0091408 |  | 2378501
JED-HRR2-RIYA-37 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:39 |  | 2025 |  |  | 2025-11-05 10:40 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002985 | OSPWO0024393
JED-FRDS-BUHA-26 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:11 |  | 2025 |  |  | 2025-12-16 13:12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003267 | OSPWO0026000
JED-FRDS-BUHA-27 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:12 |  | 2025 |  |  | 2025-12-16 13:13 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003268 | OSPWO0026004
TAI-MELI-JUFE-04 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:10 |  | 2026 |  |  | 2026-01-28 15:11 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000450 | OSPWO0028773
BAH-BCPS-GHAD-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 383374 | 383374 | 2026-01-14 14:25 |  | 2026 |  |  | 2026-01-14 14:25 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027721 | RITM0087564 |  | 6574301
JED-HRR2-WAFA-25 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:41 | 2026-03-26 11:41 | 2026 |  |  | 2026-03-26 11:42 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000673 | OSPWO0034841 | RITM0095098 |  | 2378601
JED-HRR2-WAFA-86 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:11 |  | 2026 |  |  | 2026-03-01 15:37 | 0 | 0 | 0 | 0 |  |  | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000620 | OSPWO0032372 | RITM0091402 |  | 2378501
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 710415 | 710415 | 2025-11-05 10:49 |  | 2025 |  |  | 2025-11-10 17:52 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000798 | OSPWO0024452 | RITM0076843 |  | 2387401
JED-HRR2-RIYA-29 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:36 |  | 2025 |  |  | 2025-11-05 10:38 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002995 | OSPWO0024379
JED-HRR2-TEEB-11 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 14:52 |  | 2026 |  |  | 2026-01-28 14:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000405 | OSPWO0028683
JED-HRR2-WAFA-99 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:21 |  | 2026 |  |  | 2026-02-16 12:21 | 0 | 0 | 0 | 0 |  |  | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000609 | OSPWO0032404 | RITM0091418 |  | 2378501
JED-HRR2-RIYA-46 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:44 |  | 2025 |  |  | 2025-11-05 10:46 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002993 | OSPWO0024425
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:10 |  | 2026 |  |  | 2026-01-28 15:10 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000449 | OSPWO0028771
JED-HRR2-FURO-29 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-15 22:11 | 2026-02-15 22:11 | 2026 |  |  | 2026-03-01 15:46 | 0 | 0 | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000609 | OSPWO0032346 | RITM0091369 |  | 2378501
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:49 |  | 2025 |  |  | 2025-11-10 17:54 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003014 | OSPWO0024455
BAH-BCPS-SARA-01 | 0 | BAHA | FEP-Phase1 | Fiber |  |  |  | 2026-01-14 14:24 |  | 2026 |  |  | 2026-01-14 14:24 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPFI0000244 | OSPWO0027714
JED-HRR2-RIYA-F3 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:50 |  | 2025 |  |  | 2025-11-10 17:51 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003001 | OSPWO0024457
BAH-BCPS-ARIF-01 | 0 | BAHA | FEP-Phase1 | Civil | 1 - PIP Submission | 438579 | 438579 | 2026-01-14 14:28 |  | 2026 |  |  | 2026-01-14 14:28 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0027733 | RITM0087570 |  | 6574301
JED-HRR2-RIYA-25 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:34 |  | 2025 |  |  | 2025-11-05 10:36 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002992 | OSPWO0024367
JED-FRDS-MANA-07 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:13 |  | 2025 |  |  | 2025-11-05 10:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002966 | OSPWO0024317
TAI-QAIM-QIAA-09 | 0 | MAKKAH | FTTH-Expansion | Fiber | 1 - PIP Submission | 0 | 0 | 2026-01-28 15:08 |  | 2026 |  |  | 2026-01-28 15:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028760 | RITM0088961 |  | 2656101 |  | To close the pending held orders in the mentioned cluster
TAI-QAIM-HASH-F4 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-06 14:46 |  | 2026 |  |  | 2026-01-06 14:47 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000110 | OSPWO0026990
JED-HRR2-WAFA-28 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:50 | 2026-03-26 11:50 | 2026 |  |  | 2026-03-26 11:50 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000701 | OSPWO0034851 | RITM0095103 |  | 2378601
JED-HRR2-WAFA-86 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 50000 | 50000 | 2026-02-16 12:12 |  | 2026 |  |  | 2026-03-01 15:37 | 0 | 0 | 0 | 0 | 31 | 63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000596 | OSPWO0032374 | RITM0091403 |  | 2378501
JED-HRR2-WAFA-52 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 12:30 | 2026-03-26 12:30 | 2026 |  |  | 2026-03-26 12:31 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000700 | OSPWO0034865 | RITM0095112 |  | 2378601
JED-HRR2-SALH-18 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-07 15:44 |  | 2026 |  |  | 2026-01-07 15:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000129 | OSPWO0027098
BAH-BCPS-AREE-01 | 0 | BAHA | FEP-Phase1 | Civil |  |  |  | 2026-01-14 14:27 |  | 2026 |  |  | 2026-01-14 14:27 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612OSPCI0000221 | OSPWO0027728
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 211409 | 211409 | 2026-01-15 16:24 |  | 2026 |  |  | 2026-01-26 08:52 | 0 | 0 | 0 | 0 | 65 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-26 08:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000732 | OSPWO0027801 | RITM0087656 |  | 2387401
JED-HRR2-RIYA-45 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:44 |  | 2025 |  |  | 2025-11-05 10:45 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003006 | OSPWO0024423
TAI-QAIM-HASH-08 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-06 14:44 |  | 2026 |  |  | 2026-01-06 14:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000106 | OSPWO0026980
JED-HRR2-RIYA-38 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 219834 | 219834 | 2025-10-11 22:39 | 2025-10-11 22:39 | 2025 |  |  | 2025-11-10 17:51 | 0 | 0 | 0 | 0 | 59 | 185 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:51 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000629 | OSPWO0023696 | RITM0075248 |  | 2387401
JED-HRR2-WAFA-86 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:12 |  | 2026 |  |  | 2026-02-16 12:12 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000514 | OSPWO0032375
JED-HRR2-WAFA-90 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:17 |  | 2026 |  |  | 2026-02-16 12:18 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000518 | OSPWO0032391
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 184795 | 184795 | 2025-11-05 10:49 |  | 2025 |  |  | 2025-11-10 17:52 | 0 | 0 | 0 | 0 | 75 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000727 | OSPWO0024454 | RITM0076844 |  | 2387401
JED-HRR2-RIYA-F3 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 214465 | 214465 | 2025-11-05 10:50 |  | 2025 |  |  | 2025-11-10 17:50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000779 | OSPWO0024456 | RITM0076845 |  | 2387401
TAI-AYKB-QAMA-01 | 0 | MAKKAH | FEP-Phase1 | Civil | 1 - PIP Submission | 1818336.8 | 1818336.8 | 2025-09-28 08:35 | 2025-09-28 08:35 | 2025 |  |  | 2025-10-01 08:03 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-10-01 08:03 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023233 | RITM0073988 |  | 2634901
TAI-QRAU-SABA-04 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 329236 | 329236 | 2026-03-16 01:33 | 2026-03-16 01:33 | 2026 |  |  | 2026-03-16 01:33 | 0 | 0 | 0 | 0 | 186 | 813 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002390 | OSPWO0034515 | RITM0094608 |  | 2651701
JED-FRDS-BUHA-F2 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-12-16 13:15 |  | 2025 |  |  | 2025-12-16 13:16 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0003241 | OSPWO0026018
JED-HRR2-WAFA-24 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 11:36 | 2026-03-26 11:36 | 2026 |  |  | 2026-03-26 11:36 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000697 | OSPWO0034839 | RITM0095096 |  | 2378601
JED-HRR2-WAFA-11 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-17 11:40 | 2026-03-17 11:40 | 2026 |  |  | 2026-03-17 11:40 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000684 | OSPWO0034642 | RITM0094730 |  | 2378601
JED-FRDS-BUHA-28 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 130244 | 130244 | 2025-12-16 13:13 |  | 2025 |  |  | 2025-12-16 13:13 | 0 | 0 | 0 | 0 | 62 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002805 | OSPWO0026007 | RITM0079701 |  | 2382301
JED-HRR2-WAFA-42 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:26 | 2026-03-26 12:26 | 2026 |  |  | 2026-03-26 12:26 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000715 | OSPWO0034859 | RITM0095108 |  | 2378601
MAK-WHD2-QASA-15 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-01-07 15:47 |  | 2026 |  |  | 2026-01-07 17:58 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000145 | OSPWO0027108
JED-FRDS-MANA-F1 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:20 |  | 2025 |  |  | 2025-11-05 10:22 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0002990 | OSPWO0024359
JED-HRR2-WAFA-02 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-17 11:37 | 2026-03-17 11:37 | 2026 |  |  | 2026-03-17 11:38 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000650 | OSPWO0034636 | RITM0094728 |  | 2378601
TAI-QAIM-QIAA-10 | 0 | MAKKAH | FTTH-Expansion | Fiber |  |  |  | 2026-01-28 15:07 |  | 2026 |  |  | 2026-01-28 15:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000443 | OSPWO0028759
JED-FRDS-BUHA-22 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 146064 | 146064 | 2025-12-16 13:08 |  | 2025 |  |  | 2025-12-16 13:08 | 0 | 0 | 0 | 0 | 71 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0002799 | OSPWO0025983 | RITM0079689 |  | 2382301
JED-HRR2-WAFA-13 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 300000 | 300000 | 2026-03-26 11:12 | 2026-03-26 11:12 | 2026 |  |  | 2026-03-26 11:12 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000661 | OSPWO0034805 | RITM0095080 |  | 2378601
JED-HRR2-WAFA-98 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2026-02-16 12:20 |  | 2026 |  |  | 2026-02-16 12:21 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFI0000521 | OSPWO0032403
JED-HRR2-RIYA-38 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-11-05 10:40 |  | 2025 |  |  | 2025-11-05 10:41 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003000 | OSPWO0024399
JED-FRDS-BUHA-28 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:13 |  | 2025 |  |  | 2025-12-16 13:14 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003269 | OSPWO0026008
MAK-WHD2-QASA-15 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 103731 | 103731 | 2026-01-07 15:47 |  | 2026 |  |  | 2026-01-07 17:57 | 0 | 0 | 0 | 0 | 64 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2026-01-07 17:57 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001804 | OSPWO0027107 | RITM0086641 |  | 2457701
JED-HRR2-WAFA-88 | 0 | MAKKAH | FTTH | Civil | 1 - PIP Submission | 200000 | 200000 | 2026-02-16 12:14 |  | 2026 |  |  | 2026-02-16 12:14 | 0 | 0 | 0 | 0 |  |  | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCD0000598 | OSPWO0032380 | RITM0091406 |  | 2378501
JED-HRR2-RIYA-43 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2025-11-05 10:42 |  | 2025 |  |  | 2025-11-05 10:44 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPCI0002990 | OSPWO0024413
JED-FRDS-BUHA-22 | 0 | MAKKAH | FTTH | Fiber |  |  |  | 2025-12-16 13:08 |  | 2025 |  |  | 2025-12-16 13:08 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFI0003263 | OSPWO0025984
JED-HRR2-WAFA-51 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 100000 | 100000 | 2026-03-26 12:28 | 2026-03-26 12:28 | 2026 |  |  | 2026-03-26 12:29 | 0 | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPFD0000724 | OSPWO0034863 | RITM0095110 |  | 2378601
JED-HRR2-RIYA-F3 | 0 | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 3859165 | 3859165 | 2025-10-11 22:31 | 2025-10-11 22:31 | 2025 |  |  | 2025-11-10 17:50 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:50 | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000737 | OSPWO0023692 | RITM0075246 |  | 2387401
JED-HRR2-RIYA-56 | 0 | MAKKAH | FTTH-Expansion | Civil | 1 - PIP Submission | 0 |  | 2026-01-28 14:19 |  | 2026 |  |  | 2026-01-28 14:19 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0028518 | RITM0088836 |  | 2387401 |  | To close the pending held orders in the mentioned cluster
JED-HRR2-RIYA-23 | 0 | MAKKAH | FTTH | Civil |  |  |  | 2026-01-15 16:24 |  | 2026 |  |  | 2026-01-26 08:53 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | Inspection | OSP |  | Not Yet Requested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2602OSPCI0000234 | OSPWO0027800
JED-FRDS-MANA-05 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 136321 | 136321 | 2025-11-05 10:12 |  | 2025 | 2026-06-28 |  | 2025-12-17 10:37 | 0 | 0 | 0 | 0 | 82 | 161 | 0 | 0 | 11292 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001885 | OSPWO0024310 | RITM0076771 |  | 2382901
SAM-SMTH-AMUD-01 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 500700 | 500700 | 2025-11-16 10:40 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 0 | 3773 | 0 | 16 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024855 | RITM0077595 |  | 8684101
TAI-MELI-JUFE-02 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 221229 | 221229 | 2025-12-17 10:33 | 2025-12-17 10:33 | 2025 | 2026-05-31 |  | 2026-02-24 11:20 | 0 | 0 | 0 | 0 | 142 | 547 |  | 0 | 21101 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001768 | OSPWO0026129 | RITM0079813 |  | 2652502
TAI-MELI-NASE-03 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1600420 | 1600420 | 2025-12-17 10:47 | 2025-12-17 10:47 | 2025 | 2026-02-28 |  | 2026-02-24 10:52 | 0 | 13276 | 0 | 23 | 219 | 1171 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000019 | OSPWO0026146 | RITM0079821 |  | 2651801
JED-HRR2-RIYA-57 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 169308 | 169308 | 2026-01-06 14:58 |  | 2026 | 2026-06-30 |  | 2026-02-10 14:18 | 0 | 0 | 0 | 0 | 55 | 113 | 0 | 0 | 8383 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 11 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000694 | OSPWO0027043 | RITM0086078 |  | 2387401
TAI-MELI-JUFE-03 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 983261 | 983261 | 2025-12-17 10:34 | 2025-12-17 10:34 | 2025 | 2026-04-30 |  | 2026-02-24 11:21 | 0 | 9579 | 0 | 13 | 163 | 549 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001728 | OSPWO0026131 | RITM0079814 |  | 2652502
JED-HRR2-RIYA-47 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 197261 | 197261 | 2025-11-05 10:45 |  | 2025 | 2026-02-25 |  | 2026-03-01 14:13 | 0 | 0 | 0 | 0 | 79 | 268 | 0 | 0 | 10100 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000760 | OSPWO0024430 | RITM0076832 |  | 2387401
SAM-SMTH-TURS-01 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 380983 | 380983 | 2025-11-16 10:39 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 0 | 2902 | 0 | 12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 5 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024847 | RITM0077591 |  | 8674201
JED-HRR2-RIYA-53 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 709548 | 709548 | 2025-11-05 10:47 |  | 2025 | 2026-04-25 |  | 2025-12-17 10:35 | 0 | 6521 | 0 | 13 | 59 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000766 | OSPWO0024440 | RITM0076837 |  | 2387401
SAM-SMTH-MASO-01 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 180723 | 180723 | 2025-11-16 10:40 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 0 | 1398 | 0 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024851 | RITM0077593 |  | 8679401
JED-HRR2-RIYA-35 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 170387 | 170387 | 2025-11-05 10:38 |  | 2025 | 2026-03-28 |  | 2025-12-17 10:33 | 0 | 0 | 0 | 0 | 48 | 302 | 0 | 0 | 7968 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000779 | OSPWO0024386 | RITM0076810 |  | 2387401
JED-FRDS-BUHA-22 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 894379 | 894379 | 2025-12-16 13:07 |  | 2025 | 2026-07-30 |  | 2026-01-28 14:23 | 0 | 8852 | 0 | 15 | 71 | 146 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002748 | OSPWO0025981 | RITM0079688 |  | 2382301
JED-FRDS-MANA-17 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 659281 | 659281 | 2026-01-06 14:56 |  | 2026 | 2026-07-30 |  | 2026-01-28 14:21 | 0 | 7780 | 0 | 12 | 54 | 170 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001855 | OSPWO0027037 | RITM0086075 |  | 2382901
SAM-SMTH-MASO-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 26756 | 26756 | 2025-11-16 10:40 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1495 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024853 | RITM0077594 |  | 8679401
JED-FRDS-MANA-06 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 754708 | 754708 | 2025-11-05 10:12 |  | 2025 | 2026-05-29 |  | 2025-12-17 10:25 | 0 | 7065 | 0 | 14 | 110 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001844 | OSPWO0024312 | RITM0076772 |  | 2382901
TAI-MELI-JUFE-F1 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 108806 | 108806 | 2025-12-17 10:46 | 2025-12-17 10:46 | 2025 | 2026-02-28 |  | 2026-02-24 10:49 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4794 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001772 | OSPWO0026144 | RITM0079820 |  | 2652502
JED-FRDS-MANA-09 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 108345 | 108345 | 2025-11-05 10:14 |  | 2025 | 2026-07-20 |  | 2025-12-17 10:32 | 0 | 0 | 0 | 0 | 58 | 154 | 0 | 0 | 8283 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001889 | OSPWO0024326 | RITM0076779 |  | 2382901
JED-HRR2-RIYA-24 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 202694 | 202694 | 2025-11-05 10:33 |  | 2025 | 2026-02-22 |  | 2026-03-01 14:13 | 0 | 0 | 0 | 0 | 79 | 264 | 0 | 0 | 10989 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000676 | OSPWO0024362 | RITM0076798 |  | 2387401
TAI-MELI-JUFE-02 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 868963 | 868963 | 2025-12-17 10:32 | 2025-12-17 10:32 | 2025 | 2026-04-30 |  | 2026-02-24 11:19 | 0 | 8990 | 0 | 10 | 142 | 547 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001727 | OSPWO0026127 | RITM0079812 |  | 2652502
SAM-SMTH-MAJA-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 191528 | 191528 | 2025-11-16 10:41 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10190 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024861 | RITM0077598 |  | 8684101
JED-HRR2-RIYA-55 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 204518 | 204518 | 2025-11-05 10:49 |  | 2025 | 2026-05-23 |  | 2025-12-17 10:41 | 0 | 0 | 0 | 0 | 73 | 281 | 0 | 0 | 10934 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000600 | OSPWO0024450 | RITM0076842 |  | 2387401
TAI-QAIM-HASH-F4 |  | MAKKAH | FTTH | Civil | 2 - PIP Approval | 1240 | 1240 | 2026-01-06 14:46 |  | 2026 |  |  | 2026-02-24 12:09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000559 | OSPWO0026987 | RITM0086049 |  | 2656301
JED-HRR2-SALH-19 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 172425.9 | 172426 | 2025-11-04 22:04 | 2025-11-04 22:04 | 2025 | 2026-03-28 |  | 2026-03-09 17:16 | 0 | 0 | 0 | 0 | 131 | 179 |  | 0 | 14673 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002487 | OSPWO0024247 | RITM0076719 |  | 2376401
JED-HRR2-RIYA-40 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1106083 | 1106083 | 2025-10-27 13:48 | 2025-10-27 13:48 | 2025 | 2026-03-30 |  | 2025-12-17 10:21 | 0 | 9612 | 0 | 16 | 50 | 293 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000629 | OSPWO0023942 | RITM0076064 |  | 2387401
JED-HRR2-RIYA-29 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 769265 | 769265 | 2025-11-05 10:36 |  | 2025 | 2026-02-28 |  | 2025-12-17 10:24 | 0 | 6830 | 0 | 13 | 94 | 302 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000751 | OSPWO0024376 | RITM0076805 |  | 2387401
JED-FRDS-MANA-17 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 133041 | 133041 | 2026-01-06 14:57 |  | 2026 | 2026-08-20 |  | 2026-02-22 22:25 | 0 | 0 | 0 | 0 | 54 | 170 | 0 | 0 | 11220 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 14 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001897 | OSPWO0027039 | RITM0086076 |  | 2382901
JED-HRR2-RIYA-55 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 840954 | 840954 | 2025-11-05 10:48 |  | 2025 | 2026-04-25 |  | 2025-12-17 10:28 | 0 | 7186 | 0 | 15 | 73 | 281 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000648 | OSPWO0024448 | RITM0076841 |  | 2387401
JED-FRDS-BUHA-26 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 838712 | 838712 | 2025-12-16 13:11 |  | 2025 | 2026-07-29 |  | 2026-01-28 14:24 | 0 | 9339 | 0 | 18 | 46 | 119 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002752 | OSPWO0025997 | RITM0079696 |  | 2382301
JED-HRR2-RIYA-44 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 167845 | 167845 | 2025-11-05 10:43 |  | 2025 | 2026-05-30 |  | 2025-12-17 10:41 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 9604 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000762 | OSPWO0024418 | RITM0076826 |  | 2387401
TAI-MELI-JUFE-05 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 0 | 0 | 2025-12-17 10:43 | 2025-12-17 10:43 | 2025 | 2026-05-31 |  | 2026-02-24 11:28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001771 | OSPWO0026142 | RITM0079819 |  | 2652502
JED-FRDS-BUHA-25 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 768706 | 768706 | 2025-12-16 13:10 |  | 2025 | 2026-07-29 |  | 2026-01-28 14:24 | 0 | 8718 | 0 | 13 | 71 | 174 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002751 | OSPWO0025993 | RITM0079694 |  | 2382301
JED-FRDS-MANA-09 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 580928 | 580928 | 2025-11-05 10:14 |  | 2025 | 2026-06-25 |  | 2025-12-17 10:26 | 0 | 6761 | 0 | 12 | 58 | 154 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001847 | OSPWO0024324 | RITM0076778 |  | 2382901
JED-FRDS-MANA-21 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 824615 | 824615 | 2025-11-05 10:18 |  | 2025 | 2026-05-30 |  | 2025-12-17 10:27 | 0 | 8246 | 0 | 13 | 61 | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001859 | OSPWO0024348 | RITM0076790 |  | 2382901
JED-HRR2-RIYA-41 |  | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 216927 | 216927 | 2025-11-05 10:41 |  | 2025 |  |  | 2025-12-17 01:55 | 0 | 0 | 0 | 0 | 65 | 170 | 0 | 0 | 14355 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | Cancelled | No Longer Required | Implementation | OSP | 2025-11-10 17:52 | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000772 | OSPWO0024406 | RITM0076820 |  | 2387401
TAB-TBK5-MASY-F1 |  | TABUK | FTTH | Fiber | 3 - Implementation | 60084 | 60084 | 2026-01-07 12:24 |  | 2026 | 2026-03-30 |  | 2026-02-11 14:24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2182 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2409OSPFD0002441 | OSPWO0027079 | RITM0086554 |  | 4732401
TAI-THVT-YASM-02 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 196871 | 196871 | 2025-12-16 10:02 | 2025-12-16 10:02 | 2025 | 2026-03-31 |  | 2026-02-24 12:02 | 0 | 0 | 0 | 0 | 137 | 472 |  | 0 | 16547 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000577 | OSPWO0025907 | RITM0079641 |  | 2656201
TAI-QAIM-QIAA-F2 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 5200 | 5200 | 2026-01-06 14:48 |  | 2026 | 2026-02-28 |  | 2026-02-24 12:03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000473 | OSPWO0026999 | RITM0086055 |  | 2656101
EDA-AYBN-EDAB-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 949010 | 831746.7 | 2025-10-27 08:39 | 2025-10-27 08:39 | 2025 | 2026-10-31 |  | 2026-03-02 14:38 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0023904 | RITM0076014 |  | 8574601
TAI-MELI-FIYS-01 |  | MAKKAH | FTTH | Fiber | 1 - PIP Submission | 200000 | 200000 | 2026-01-06 14:42 |  | 2026 |  |  | 2026-01-22 13:49 | 0 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026973 | RITM0086035 |  | 2652602
TAI-QAIM-HASH-08 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130567 | 130567 | 2026-01-06 14:44 |  | 2026 | 2026-04-30 |  | 2026-02-24 11:52 | 0 | 0 | 0 | 0 | 62 | 310 | 0 | 0 | 9035 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000533 | OSPWO0026981 | RITM0086040 |  | 2656301
JED-FRDS-BUHA-24 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 849302 | 849302 | 2025-12-16 13:09 |  | 2025 | 2026-07-31 |  | 2026-01-28 14:24 | 0 | 8391 | 0 | 15 | 71 | 163 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002750 | OSPWO0025989 | RITM0079692 |  | 2382301
JED-HRR2-RAHA-18 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 257236.75 | 258927 | 2025-11-16 22:39 | 2025-11-16 22:39 | 2025 | 2026-01-29 |  | 2026-03-09 17:22 | 0 | 0 | 0 | 0 | 170 | 220 |  | 0 | 20347 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000008 | OSPWO0024974 | RITM0077706 |  | 2376401
TAB-TBHH-MASY-01 |  | TABUK | FTTH | Fiber | 3 - Implementation | 280379 | 280379 | 2026-01-07 12:24 |  | 2026 | 2026-03-26 |  | 2026-02-11 14:24 | 0 | 0 | 0 | 0 | 186 | 186 |  | 0 | 16903 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407OSPFD0002383 | OSPWO0027071 | RITM0086547 |  | 4732401
JED-HRR2-SALH-07 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 189442.35 | 189442.35 | 2025-08-14 15:51 | 2025-08-14 15:51 | 2025 | 2025-12-19 |  | 2026-03-09 16:02 | 0 | 0 | 0 | 0 | 142 | 291 |  | 0 | 18952 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000014 | OSPWO0021672 | RITM0070644 |  | 2376401
JED-HRR2-RIYA-57 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 751838 | 751838 | 2026-01-06 14:57 |  | 2026 | 2026-06-30 |  | 2026-02-10 08:25 | 0 | 5449 | 0 | 16 | 55 | 113 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000749 | OSPWO0027041 | RITM0086077 |  | 2387401
JED-HRR2-SALH-17 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 239877.7 | 239878 | 2025-10-06 10:25 | 2025-10-06 10:25 | 2025 | 2026-03-28 |  | 2026-03-02 14:32 | 0 | 0 | 0 | 0 | 161 | 142 |  | 0 | 22706 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002485 | OSPWO0023573 | RITM0074743 |  | 2376401
TAI-QAIM-QIAA-F2 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 59839 | 59839 | 2026-01-06 14:49 |  | 2026 | 2026-03-31 |  | 2026-02-24 12:04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000449 | OSPWO0027001 | RITM0086056 |  | 2656101
JED-FRDS-MANA-21 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 128671 | 128671 | 2025-11-05 10:19 |  | 2025 | 2026-06-24 |  | 2025-12-17 10:39 | 0 | 0 | 0 | 0 | 61 | 190 | 0 | 0 | 9506 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001901 | OSPWO0024350 | RITM0076791 |  | 2382901
JED-FRDS-MANA-22 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 804013 | 804013 | 2025-11-05 10:19 |  | 2025 | 2026-05-30 |  | 2025-12-17 10:27 | 0 | 7917 | 0 | 14 | 57 | 171 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001860 | OSPWO0024352 | RITM0076792 |  | 2382901
SAM-SMTH-TURS-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 60718 | 60718 | 2025-11-16 10:39 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024849 | RITM0077592 |  | 8674201
JED-HRR2-RIYA-27 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 808790 | 808790 | 2025-11-05 10:35 |  | 2025 | 2026-02-25 |  | 2025-12-17 10:23 | 0 | 6670 | 0 | 15 | 79 | 281 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000698 | OSPWO0024372 | RITM0076803 |  | 2387401
JED-HRR2-RIYA-36 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1012456 | 1012456 | 2025-11-05 10:38 |  | 2025 | 2026-03-24 |  | 2025-12-17 10:28 | 0 | 6300 | 0 | 17 | 59 | 291 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000760 | OSPWO0024388 | RITM0076811 |  | 2387401
JED-HRR2-RIYA-40 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 183272 | 183272 | 2025-10-27 13:49 | 2025-10-27 13:49 | 2025 | 2026-04-25 |  | 2025-12-17 10:32 | 0 | 0 | 0 | 0 | 50 | 293 |  | 0 | 10102 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000776 | OSPWO0023944 | RITM0076065 |  | 2387401
TAI-THVT-YASM-01 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 615453 | 615453 | 2025-12-16 09:59 | 2025-12-16 09:59 | 2025 | 2026-02-28 |  | 2026-02-24 11:59 | 0 | 7671 | 0 | 13 | 86 | 314 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000557 | OSPWO0025901 | RITM0079639 |  | 2656201
TAI-THVT-YASM-01 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 144002 | 144002 | 2025-12-16 09:59 | 2025-12-16 09:59 | 2025 | 2026-03-31 |  | 2026-02-24 12:00 | 0 | 0 | 0 | 0 | 86 | 314 |  | 0 | 11412 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000576 | OSPWO0025903 | RITM0079640 |  | 2656201
JED-FRDS-MANA-08 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 631849 | 631849 | 2025-11-05 10:13 |  | 2025 | 2026-06-30 |  | 2025-12-17 10:26 | 0 | 4217 | 0 | 12 | 51 | 157 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001846 | OSPWO0024320 | RITM0076776 |  | 2382901
JED-FRDS-MANA-18 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130417 | 130417 | 2025-11-05 10:17 |  | 2025 | 2026-07-25 |  | 2025-12-17 10:34 | 0 | 0 | 0 | 0 | 62 | 178 | 0 | 0 | 10071 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001898 | OSPWO0024338 | RITM0076785 |  | 2382901
SAM-SMTH-KHAD-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 115316 | 115316 | 2025-11-16 10:39 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024845 | RITM0077590 |  | 8673901
TAI-AYKB-QUDS-01 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 2538475.7 | 2664847.4 | 2025-09-28 08:31 | 2025-09-28 08:31 | 2025 | 2026-04-30 |  | 2025-12-01 16:59 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023227 | RITM0073989 |  | 2634701
TAI-MELI-NASE-03 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 515873 | 515873 | 2025-12-17 10:48 | 2025-12-17 10:48 | 2025 | 2026-03-31 |  | 2026-02-24 10:53 | 0 | 0 | 0 | 0 | 219 | 1171 |  | 0 | 37390 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000019 | OSPWO0026148 | RITM0079822 |  | 2651801
JED-FRDS-BUHA-27 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 727041 | 727041 | 2025-12-16 13:12 |  | 2025 | 2026-07-28 |  | 2026-01-28 14:24 | 0 | 8092 | 0 | 14 | 56 | 137 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002753 | OSPWO0026001 | RITM0079698 |  | 2382301
JED-FRDS-BUHA-23 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 586418 | 586418 | 2025-12-16 13:08 |  | 2025 | 2026-07-30 |  | 2026-02-22 22:23 | 0 | 4164 | 0 | 10 | 48 | 93 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002749 | OSPWO0025985 | RITM0079690 |  | 2382301
JED-FRDS-BUHA-30 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 693068 | 693068 | 2025-12-16 13:14 |  | 2025 | 2026-08-31 |  | 2026-02-22 22:23 | 0 | 4779 | 0 | 11 | 36 | 92 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002756 | OSPWO0026013 | RITM0079704 |  | 2382301
JED-FRDS-MANA-06 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 168819 | 168819 | 2025-11-05 10:12 |  | 2025 | 2026-06-24 |  | 2025-12-17 10:38 | 0 | 0 | 0 | 0 | 110 | 163 | 0 | 0 | 13656 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001886 | OSPWO0024314 | RITM0076773 |  | 2382901
JED-HRR2-RIYA-59 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 131792 | 131792 | 2026-01-04 09:02 | 2026-01-04 09:02 | 2026 | 2026-06-30 |  | 2026-02-10 14:19 | 0 | 0 | 0 | 0 | 37 | 94 |  | 0 | 5781 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 10 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000668 | OSPWO0026593 | RITM0084708 |  | 2387401
JED-FRDS-MANA-F1 |  | MAKKAH | FTTH | Civil | 1 - PIP Submission | 0 | 0 | 2025-11-05 10:20 |  | 2025 |  |  | 2026-02-09 23:43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001866 | OSPWO0024356 | RITM0076794 |  | 2382901
JED-FRDS-MANA-20 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 137448 | 137448 | 2025-11-05 10:18 |  | 2025 | 2026-06-25 |  | 2025-12-17 10:38 | 0 | 0 | 0 | 0 | 74 | 174 | 0 | 0 | 10309 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001900 | OSPWO0024346 | RITM0076789 |  | 2382901
JED-HRR2-RIYA-50 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 596304 | 596304 | 2025-11-05 10:46 |  | 2025 | 2026-04-25 |  | 2025-12-17 10:28 | 0 | 4255 | 0 | 11 | 64 | 290 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000653 | OSPWO0024432 | RITM0076833 |  | 2387401
JED-HRR2-RIYA-37 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 180887 | 180887 | 2025-11-05 10:39 |  | 2025 | 2026-04-27 |  | 2025-12-17 10:40 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 11418 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000604 | OSPWO0024394 | RITM0076814 |  | 2387401
JED-FRDS-MANA-22 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 130834 | 130834 | 2025-11-05 10:19 |  | 2025 | 2026-06-25 |  | 2025-12-17 10:34 | 0 | 0 | 0 | 0 | 57 | 171 | 0 | 0 | 9419 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001902 | OSPWO0024354 | RITM0076793 |  | 2382901
JED-HRR2-RIYA-50 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 153573 | 153573 | 2025-11-05 10:46 |  | 2025 | 2026-05-24 |  | 2025-12-17 10:41 | 0 | 0 | 0 | 0 | 64 | 290 | 0 | 0 | 8028 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000599 | OSPWO0024434 | RITM0076834 |  | 2387401
JED-HRR2-RIYA-F3 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 3859165 | 3859165 | 2025-11-05 10:50 |  | 2025 | 2026-02-21 |  | 2025-12-17 10:36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152899 | 0 | 0 | 0 | 15 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000737 | OSPWO0024458 | RITM0076846 |  | 2387401
JED-FRDS-MANA-F1 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 1116248 | 1116248 | 2025-11-05 10:20 |  | 2025 | 2026-06-21 |  | 2025-12-17 10:39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43083 | 0 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001908 | OSPWO0024358 | RITM0076795 |  | 2382901
TAI-MELI-JUFE-01 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 744980 | 744980 | 2025-12-17 10:01 | 2025-12-17 10:01 | 2025 | 2026-04-30 |  | 2026-02-24 11:17 | 0 | 7249 | 0 | 12 | 120 | 471 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001726 | OSPWO0026123 | RITM0079810 |  | 2652502
JED-HRR2-SALH-13 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 896064 | 896064 | 2026-01-04 00:50 | 2026-01-04 00:50 | 2026 | 2026-05-31 |  | 2026-02-10 08:29 | 0 | 6313 | 0 | 15 | 143 | 257 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000020 | OSPWO0026572 | RITM0084629 |  | 2376401
JED-HRR2-SALH-06 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 191872.45 | 191872 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025 | 2026-02-26 |  | 2026-03-09 16:03 | 0 | 0 | 0 | 0 | 135 | 148 |  | 0 | 19132 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000013 | OSPWO0023545 | RITM0074728 |  | 2376401
JED-FRDS-MANA-20 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 747315 | 747315 | 2025-11-05 10:18 |  | 2025 | 2026-05-30 |  | 2025-12-17 10:26 | 0 | 5404 | 0 | 13 | 74 | 174 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001858 | OSPWO0024344 | RITM0076788 |  | 2382901
JED-FRDS-MANA-10 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 125939 | 125939 | 2025-11-05 10:15 |  | 2025 | 2026-07-20 |  | 2025-12-17 10:34 | 0 | 0 | 0 | 0 | 65 | 163 | 0 | 0 | 9110 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001890 | OSPWO0024330 | RITM0076781 |  | 2382901
TAI-QAIM-QIAA-10 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 885820 | 885820 | 2026-01-03 00:57 | 2026-01-03 00:57 | 2026 | 2026-03-31 |  | 2026-02-24 11:57 | 0 | 6383 | 0 | 18 | 55 | 135 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000470 | OSPWO0026558 | RITM0084115 |  | 2656101
JED-HRR2-RIYA-38 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 219834 | 219834 | 2025-11-05 10:40 |  | 2025 | 2026-04-27 |  | 2025-12-17 10:40 | 0 | 0 | 0 | 0 | 59 | 290 | 0 | 0 | 13795 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000629 | OSPWO0024398 | RITM0076816 |  | 2387401
JED-HRR2-RIYA-52 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 814566 | 814566 | 2025-11-05 10:46 |  | 2025 | 2026-04-28 |  | 2025-12-17 10:23 | 0 | 5560 | 0 | 14 | 83 | 299 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000778 | OSPWO0024436 | RITM0076835 |  | 2387401
TAI-MELI-JUFE-04 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 582247 | 582247 | 2025-12-17 10:39 | 2025-12-17 10:39 | 2025 | 2026-04-30 |  | 2026-02-24 11:24 | 0 | 7390 | 0 | 12 | 120 | 420 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001729 | OSPWO0026135 | RITM0079816 |  | 2652502
JED-HRR2-RIYA-52 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 208651 | 208651 | 2025-11-05 10:47 |  | 2025 | 2026-05-24 |  | 2025-12-17 10:41 | 0 | 0 | 0 | 0 | 83 | 299 | 0 | 0 | 11988 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000698 | OSPWO0024438 | RITM0076836 |  | 2387401
JED-HRR2-RIYA-26 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 186530 | 186530 | 2025-11-05 10:35 |  | 2025 | 2026-02-25 |  | 2025-12-17 10:40 | 0 | 0 | 0 | 0 | 56 | 276 | 0 | 0 | 10462 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000658 | OSPWO0024370 | RITM0076802 |  | 2387401
JED-HRR2-RIYA-42 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 902935 | 902935 | 2025-11-05 10:41 |  | 2025 | 2026-03-31 |  | 2025-12-17 10:27 | 0 | 6164 | 0 | 18 | 46 | 294 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000743 | OSPWO0024408 | RITM0076821 |  | 2387401
TAI-QAIM-QIAA-08 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1055534 | 1055534 | 2026-01-06 14:46 |  | 2026 | 2026-03-31 |  | 2026-02-24 11:54 | 0 | 7411 | 0 | 19 | 72 | 140 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000468 | OSPWO0026991 | RITM0086051 |  | 2656101
JED-FRDS-MANA-16 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 71468 | 71468 | 2025-11-05 10:16 |  | 2025 | 2026-07-25 |  | 2025-12-17 10:33 | 0 | 0 | 0 | 0 | 31 | 154 | 0 | 0 | 5163 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001896 | OSPWO0024334 | RITM0076783 |  | 2382901
JED-HRR2-SALH-18 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 223528 | 223528 | 2026-01-07 15:45 |  | 2026 | 2026-07-30 |  | 2026-02-22 22:24 | 0 | 0 | 0 | 0 | 161 | 285 | 0 | 0 | 20347 | 0 | 161 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 17 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002486 | OSPWO0027099 | RITM0086637 |  | 2376401
JED-HRR2-RIYA-54 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 800512 | 800512 | 2025-11-05 10:48 |  | 2025 | 2026-04-28 |  | 2025-12-17 10:30 | 0 | 5740 | 0 | 14 | 78 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000703 | OSPWO0024444 | RITM0076839 |  | 2387401
JED-HRR2-RIYA-53 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 160895 | 160895 | 2025-11-05 10:47 |  | 2025 | 2026-05-23 |  | 2025-12-17 10:34 | 0 | 0 | 0 | 0 | 59 | 293 | 0 | 0 | 7998 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000659 | OSPWO0024442 | RITM0076838 |  | 2387401
SAM-SMTH-AMUD-01 |  | JIZAN | FEP-Phase1 | Fiber | 3 - Implementation | 80211 | 80211 | 2025-11-16 10:41 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024857 | RITM0077596 |  | 8684101
JED-HRR2-RIYA-56 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 184795 | 184795 | 2025-10-27 13:28 | 2025-10-27 13:28 | 2025 | 2026-05-15 |  | 2025-12-18 13:35 | 0 | 0 | 0 | 0 | 75 | 274 |  | 0 | 9799 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000727 | OSPWO0023940 | RITM0076060 |  | 2387401
TAI-QAIM-QIAA-09 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 323132 | 323132 | 2026-01-20 09:18 | 2026-01-20 09:18 | 2026 | 2026-04-30 |  | 2026-02-24 11:56 | 0 | 0 | 0 | 0 | 111 | 503 |  | 0 | 21973 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000445 | OSPWO0028044 | RITM0088067 |  | 2656101
JED-FRDS-MANA-18 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 755028 | 755028 | 2025-11-05 10:16 |  | 2025 | 2026-06-28 |  | 2025-12-18 13:33 | 0 | 5453 | 0 | 13 | 62 | 178 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001856 | OSPWO0024336 | RITM0076784 |  | 2382901
TAI-QAIM-QIAA-08 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 223585 | 223585 | 2026-01-06 14:47 |  | 2026 | 2026-04-30 |  | 2026-02-24 11:55 | 0 | 0 | 0 | 0 | 72 | 140 | 0 | 0 | 16571 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000444 | OSPWO0026993 | RITM0086052 |  | 2656101
JED-HRR2-RIYA-28 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 209040 | 209040 | 2026-01-20 09:35 | 2026-01-20 09:35 | 2026 | 2026-06-30 |  | 2026-02-10 14:17 | 0 | 0 | 0 | 0 | 72 | 231 |  | 0 | 11877 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 13 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000660 | OSPWO0028063 | RITM0088077 |  | 2387401
TAI-MELI-JUBR-10 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 600000 | 600000 | 2025-12-17 09:57 | 2025-12-17 09:57 | 2025 | 2026-04-30 |  | 2026-02-24 10:56 | 0 | 10034 | 0 | 16 | 294 | 294 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026119 | RITM0079808 |  | 2652504
JED-HRR2-RIYA-49 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 174131 | 174131 | 2026-01-01 11:53 | 2026-01-01 11:53 | 2026 | 2026-03-28 |  | 2026-01-25 13:32 | 0 | 0 | 0 | 0 | 63 | 262 |  | 0 | 9920 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000638 | OSPWO0026527 | RITM0083099 |  | 2387401
JED-HRR2-SALH-13 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 220776 | 220776 | 2026-01-04 00:51 | 2026-01-04 00:51 | 2026 | 2026-07-29 |  | 2026-02-22 22:22 | 0 | 0 | 0 | 0 | 143 | 257 |  | 0 | 21707 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502OSPFD0000020 | OSPWO0026574 | RITM0084628 |  | 2376401
TAI-QAIM-HASH-09 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 105221 | 105221 | 2026-01-06 14:45 |  | 2026 | 2026-03-31 |  | 2026-02-24 11:53 | 0 | 3947 | 0 | 7 | 20 | 83 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000558 | OSPWO0026983 | RITM0086047 |  | 2656301
JED-FRDS-MANA-19 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 784999 | 784999 | 2025-11-05 10:17 |  | 2025 | 2026-06-29 |  | 2025-12-18 13:33 | 0 | 5663 | 0 | 14 | 47 | 164 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001857 | OSPWO0024340 | RITM0076786 |  | 2382901
SAM-SMTH-MAJA-01 |  | JIZAN | FEP-Phase1 | Civil | 3 - Implementation | 1245407 | 1245407 | 2025-11-16 10:41 |  | 2025 | 2026-09-30 |  | 2026-02-03 20:35 | 0 | 9520 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 1 | 0 | 0 | 0 | 0 |  | OSPWO0024859 | RITM0077597 |  | 8684101
JED-FRDS-MANA-10 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 594385 | 594385 | 2025-11-05 10:15 |  | 2025 | 2026-06-29 |  | 2025-12-18 13:32 | 0 | 4318 | 0 | 13 | 65 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001848 | OSPWO0024328 | RITM0076780 |  | 2382901
JED-HRR2-RIYA-27 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 203152 | 203152 | 2025-11-05 10:35 |  | 2025 | 2026-03-25 |  | 2025-12-18 13:35 | 0 | 0 | 0 | 0 | 79 | 281 | 0 | 0 | 10597 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000667 | OSPWO0024374 | RITM0076804 |  | 2387401
TAI-THVT-YASM-F1 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 38564 | 38564 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025 | 2026-03-31 |  | 2026-02-24 12:06 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0000579 | OSPWO0026117 | RITM0079807 |  | 2656201
TUR-TRBH::TUR-SECO:01 |  | MAKKAH | CBU | Civil | 3 - Implementation | 0 |  | 2025-09-01 12:00 |  | 2025 | 2026-04-30 |  | 2026-02-24 10:48 | 0 | 4453 | 0 | 14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022345 | RITM0072157 |  | 0 |  | Torbah PP 21.287766076248896, 41.70283329787832
JED-HRR2-RIYA-59 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 550728 | 550728 | 2026-01-04 09:01 | 2026-01-04 09:01 | 2026 | 2026-06-30 |  | 2026-02-10 08:29 | 0 | 3783 | 0 | 12 | 37 | 94 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000702 | OSPWO0026591 | RITM0084709 |  | 2387401
JED-HRR2-RIYA-F3 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 214465 | 214465 | 2025-10-11 22:30 | 2025-10-11 22:30 | 2025 | 2026-01-31 |  | 2025-12-21 20:59 | 0 | 862 | 0 | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000779 | OSPWO0023690 | RITM0075245 |  | 2387401
JED-FRDS-BUHA-28 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 795100 | 795100 | 2025-12-16 13:12 |  | 2025 | 2026-08-30 |  | 2026-02-22 22:23 | 0 | 5705 | 0 | 13 | 62 | 112 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002754 | OSPWO0026005 | RITM0079700 |  | 2382301
TAI-THVT-YASM-F1 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 100436 | 100436 | 2025-12-17 09:55 | 2025-12-17 09:55 | 2025 | 2026-02-28 |  | 2026-02-24 12:05 | 0 | 875 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000560 | OSPWO0026115 | RITM0079806 |  | 2656201
JED-HRR2-RIYA-34 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 810212 | 810212 | 2025-11-05 10:36 |  | 2025 | 2026-02-26 |  | 2025-12-18 13:34 | 0 | 5970 | 0 | 12 | 88 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000718 | OSPWO0024380 | RITM0076807 |  | 2387401
JED-HRR2-RIYA-45 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 758652 | 758652 | 2025-11-05 10:43 |  | 2025 | 2026-04-30 |  | 2025-12-18 13:34 | 0 | 5369 | 0 | 14 | 54 | 297 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000642 | OSPWO0024420 | RITM0076827 |  | 2387401
JED-HRR2-SALH-18 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 860735 | 860735 | 2026-01-07 15:44 |  | 2026 | 2026-06-30 |  | 2026-03-10 23:02 | 0 | 5988 | 0 | 17 | 161 | 285 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002462 | OSPWO0027097 | RITM0086636 |  | 2376401 | 10/02/2026 08:25:39 - Mufleh Alsulami (Notes) update target date as agreed with project manger
JED-FRDS-MANA-07 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 729065 | 729065 | 2025-11-05 10:13 |  | 2025 | 2026-05-30 |  | 2025-12-18 13:28 | 0 | 5222 | 0 | 13 | 96 | 164 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001845 | OSPWO0024316 | RITM0076774 |  | 2382901
TAI-AYKB-QUDS-01 |  | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 592193 | 448619.5 | 2025-09-28 08:32 | 2025-09-28 08:32 | 2025 | 2026-04-30 |  | 2025-12-01 16:59 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023229 | RITM0073990 |  | 2634701
TAI-MELI-JUBR-10 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 200000 | 200000 | 2025-12-17 09:58 | 2025-12-17 09:58 | 2025 | 2026-05-31 |  | 2026-02-24 11:16 | 0 | 0 | 0 | 0 | 294 | 294 |  | 0 | 21064 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0026121 | RITM0079809 |  | 2652504
TAI-AYKB-SAKA-01 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 3606464.6 | 3782217.2 | 2025-09-28 08:29 | 2025-09-28 08:29 | 2025 | 2026-04-30 |  | 2025-12-01 16:58 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023223 | RITM0073991 |  | 2634701
JED-HRR2-SALH-15 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 759659 | 759659 | 2026-01-04 09:04 | 2026-01-04 09:04 | 2026 | 2026-06-30 |  | 2026-03-01 13:47 | 0 | 5283 | 0 | 14 | 133 | 258 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2402OSPCD0002459 | OSPWO0026595 | RITM0084715 |  | 2376401 | 10/02/2026 08:28:45 - Mufleh Alsulami (Notes) update target date as agreed with the project manger
JED-HRR2-RIYA-34 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 213942 | 213942 | 2025-11-05 10:37 |  | 2025 | 2026-03-26 |  | 2025-12-18 13:35 | 0 | 0 | 0 | 0 | 88 | 298 | 0 | 0 | 11746 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000652 | OSPWO0024382 | RITM0076808 |  | 2387401
TAI-MELI-JUFE-03 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 232355 | 232355 | 2025-12-17 10:35 | 2025-12-17 10:35 | 2025 | 2026-05-31 |  | 2026-02-24 11:22 | 0 | 0 | 0 | 0 | 163 | 549 |  | 0 | 24233 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001769 | OSPWO0026133 | RITM0079815 |  | 2652502
JED-HRR2-RIYA-46 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 172543 | 172543 | 2025-11-05 10:45 |  | 2025 | 2026-05-26 |  | 2025-12-18 13:36 | 0 | 0 | 0 | 0 | 48 | 301 | 0 | 0 | 8212 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000646 | OSPWO0024426 | RITM0076830 |  | 2387401
TAI-MELI-JUFE-05 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 2830 | 2830 | 2025-12-17 10:43 | 2025-12-17 10:43 | 2025 | 2026-05-31 |  | 2026-02-24 11:26 | 0 | 6058 | 0 | 12 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001730 | OSPWO0026140 | RITM0079818 |  | 2652502
JED-HRR2-RIYA-39 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 772418 | 772418 | 2025-11-05 10:40 |  | 2025 | 2026-03-28 |  | 2025-12-18 13:34 | 0 | 5595 | 0 | 12 | 47 | 289 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000731 | OSPWO0024400 | RITM0076817 |  | 2387401
JED-FRDS-MANA-07 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 152230 | 152230 | 2025-11-05 10:13 |  | 2025 | 2026-06-24 |  | 2025-12-18 13:35 | 0 | 0 | 0 | 0 | 96 | 164 | 0 | 0 | 12550 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001887 | OSPWO0024318 | RITM0076775 |  | 2382901
JED-FRDS-MANA-16 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 471431 | 471431 | 2025-11-05 10:16 |  | 2025 | 2026-06-30 |  | 2025-12-18 13:32 | 0 | 3423 | 0 | 8 | 31 | 154 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001854 | OSPWO0024332 | RITM0076782 |  | 2382901
TAI-QAIM-HASH-09 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 50062 | 50062 | 2026-01-06 14:45 |  | 2026 | 2026-04-30 |  | 2026-02-24 11:53 | 0 | 0 | 0 | 0 | 20 | 83 | 0 | 0 | 3161 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000534 | OSPWO0026985 | RITM0086048 |  | 2656301
TAI-QAIM-QIAA-09 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1091571 | 1091571 | 2026-01-20 09:17 | 2026-01-20 09:17 | 2026 | 2026-03-31 |  | 2026-02-24 11:56 | 0 | 8104 | 0 | 18 | 111 | 503 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000469 | OSPWO0028042 | RITM0088066 |  | 2656101
JED-HRR2-SALH-07 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 744983 | 744983 | 2025-08-14 15:49 | 2025-08-14 15:49 | 2025 | 2025-11-29 | 2025-12-31 | 2026-03-09 16:02 | 0 | 5361 | 0 | 11 | 142 | 291 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 2502OSPCD0000014 | OSPWO0021670 | RITM0070645 |  | 2376401 | 30/09/2025 09:32:51 - Mufleh Alsulami (Notes) Revise the target with project manger
JED-HRR2-RIYA-42 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 194356 | 194356 | 2025-11-05 10:42 |  | 2025 | 2026-04-30 |  | 2025-12-18 13:35 | 0 | 0 | 0 | 0 | 46 | 294 | 0 | 0 | 10357 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000682 | OSPWO0024410 | RITM0076822 |  | 2387401
JED-HRR2-SALH-19 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 801709.7 | 801710 | 2025-11-04 22:04 | 2025-11-04 22:04 | 2025 | 2026-02-28 |  | 2026-03-09 17:15 | 0 | 5721 | 0 | 15 | 107 | 147 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0002463 | OSPWO0024245 | RITM0076720 |  | 2376401
JED-FRDS-BUHA-29 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 605352 | 605352 | 2025-12-16 13:13 |  | 2025 | 2026-08-30 |  | 2026-02-22 22:23 | 0 | 4228 | 0 | 11 | 49 | 84 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002755 | OSPWO0026009 | RITM0079702 |  | 2382301
JED-HRR2-RIYA-43 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 173770 | 173770 | 2025-11-05 10:42 |  | 2025 | 2026-04-30 |  | 2025-12-18 13:36 | 0 | 0 | 0 | 0 | 56 | 279 | 0 | 0 | 10286 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000710 | OSPWO0024414 | RITM0076824 |  | 2387401
JED-HRR2-RIYA-44 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 902831 | 902831 | 2025-11-05 10:43 |  | 2025 | 2026-04-30 |  | 2025-12-18 13:34 | 0 | 6511 | 0 | 15 | 45 | 298 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000746 | OSPWO0024416 | RITM0076825 |  | 2387401
TAI-MELI-JUFE-04 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 177103 | 177103 | 2025-12-17 10:40 | 2025-12-17 10:40 | 2025 | 2026-05-31 |  | 2026-02-24 11:25 | 0 | 0 | 0 | 0 | 120 | 420 |  | 0 | 19390 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001770 | OSPWO0026137 | RITM0079817 |  | 2652502
JED-HRR2-RIYA-54 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 207626 | 207626 | 2025-11-05 10:48 |  | 2025 | 2026-05-26 |  | 2025-12-18 13:36 | 0 | 0 | 0 | 0 | 78 | 300 | 0 | 0 | 11086 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000689 | OSPWO0024446 | RITM0076840 |  | 2387401
TAI-AYKB-QAMA-01 |  | MAKKAH | FEP-Phase1 | Civil | 3 - Implementation | 1531196.4 | 1818336.8 | 2025-09-28 08:34 | 2025-09-28 08:34 | 2025 | 2026-04-30 |  | 2026-02-18 11:55 | 0 | 13824 | 0 | 57 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested | 100 | 3 | 3 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023231 | RITM0073987 |  | 2634901
JED-HRR2-RIYA-39 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 171209 | 171209 | 2025-11-05 10:40 |  | 2025 | 2026-04-27 |  | 2025-12-20 17:36 | 0 | 0 | 0 | 0 | 47 | 289 | 0 | 0 | 9658 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000637 | OSPWO0024402 | RITM0076818 |  | 2387401
JED-HRR2-RIYA-23 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 211409 | 211409 | 2025-12-22 22:52 | 2025-12-22 22:52 | 2025 | 2026-04-30 |  | 2026-02-10 14:19 | 0 | 0 | 0 | 0 | 65 | 204 |  | 0 | 13511 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 11 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000732 | OSPWO0026341 | RITM0080200 |  | 2387401
JED-HRR2-RIYA-56 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 710415 | 710415 | 2025-10-27 13:27 | 2025-10-27 13:27 | 2025 | 2026-04-30 |  | 2025-12-20 17:37 | 0 | 5138 | 0 | 13 | 75 | 274 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000798 | OSPWO0023938 | RITM0076061 |  | 2387401
TAI-THVT-YASM-02 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 683267 | 683267 | 2025-12-16 10:01 | 2025-12-16 10:01 | 2025 | 2026-02-28 |  | 2026-02-24 12:01 | 0 | 7691 | 0 | 12 | 137 | 472 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0000558 | OSPWO0025905 | RITM0079642 |  | 2656201
JED-HRR2-SALH-06 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 731160.5 | 731161 | 2025-10-06 10:04 | 2025-10-06 10:04 | 2025 | 2026-01-31 |  | 2026-03-09 16:03 | 0 | 5240 | 0 | 11 | 135 | 148 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0000013 | OSPWO0023543 | RITM0074727 |  | 2376401
JED-HRR2-RIYA-36 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 193593 | 193593 | 2025-11-05 10:38 |  | 2025 | 2026-04-26 |  | 2025-12-20 17:37 | 0 | 0 | 0 | 0 | 45 | 298 | 0 | 0 | 10735 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000756 | OSPWO0024390 | RITM0076812 |  | 2387401
JED-FRDS-MANA-19 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 112532 | 112532 | 2025-11-05 10:17 |  | 2025 | 2026-07-23 |  | 2025-12-20 17:37 | 0 | 0 | 0 | 0 | 47 | 164 | 0 | 0 | 8129 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001899 | OSPWO0024342 | RITM0076787 |  | 2382901
JED-FRDS-MANA-08 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 106866 | 106866 | 2025-11-05 10:14 |  | 2025 | 2026-07-23 |  | 2025-12-20 17:38 | 0 | 0 | 0 | 0 | 51 | 157 | 0 | 0 | 7523 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001888 | OSPWO0024322 | RITM0076777 |  | 2382901
JED-HRR2-SALH-16 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 215774.45 | 215774 | 2025-10-06 10:30 | 2025-10-06 10:30 | 2025 | 2026-03-29 |  | 2026-03-02 14:32 | 0 | 0 | 0 | 0 | 137 | 159 |  | 0 | 21047 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002484 | OSPWO0023581 | RITM0074747 |  | 2376401
JED-HRR2-RIYA-45 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 176603 | 176603 | 2025-11-05 10:44 |  | 2025 | 2026-05-28 |  | 2025-12-20 17:36 | 0 | 0 | 0 | 0 | 54 | 297 | 0 | 0 | 9125 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000624 | OSPWO0024422 | RITM0076828 |  | 2387401
TAI-QAIM-HASH-08 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 400457 | 400457 | 2026-01-06 14:44 |  | 2026 | 2026-03-31 |  | 2026-02-24 11:51 | 0 | 3155 | 0 | 6 | 62 | 310 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000557 | OSPWO0026979 | RITM0086038 |  | 2656301
JED-HRR2-SALH-14 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 234669 | 234669 | 2025-12-31 16:11 | 2025-12-31 16:11 | 2025 | 2026-07-29 |  | 2026-02-22 22:24 | 0 | 0 | 0 | 0 | 164 | 257 |  | 0 | 23093 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 19 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002482 | OSPWO0026487 | RITM0082469 |  | 2376401
TAI-AYKB-SAKA-01 |  | MAKKAH | FEP-Phase1 | Fiber | 3 - Implementation | 712019.4 | 648267.2 | 2025-09-28 08:30 | 2025-09-28 08:30 | 2025 | 2026-04-30 |  | 2025-12-01 16:58 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0023225 | RITM0073992 |  | 2634701
TAI-MELI-JUFE-01 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 187701 | 187701 | 2025-12-17 10:02 | 2025-12-17 10:02 | 2025 | 2026-05-31 |  | 2026-02-24 11:18 | 0 | 0 | 0 | 0 | 120 | 471 |  | 0 | 19345 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0001767 | OSPWO0026125 | RITM0079811 |  | 2652502
JED-HRR2-RIYA-28 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 786977 | 786977 | 2026-01-20 09:34 | 2026-01-20 09:34 | 2026 | 2026-05-31 |  | 2026-02-10 08:24 | 0 | 5890 | 0 | 12 | 72 | 231 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000707 | OSPWO0028061 | RITM0088076 |  | 2387401
JED-HRR2-RIYA-41 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 1020256 | 1020256 | 2025-10-27 13:19 | 2025-10-27 13:19 | 2025 | 2026-03-29 |  | 2025-12-21 20:59 | 0 | 7394 | 0 | 16 | 65 | 284 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000786 | OSPWO0023926 | RITM0076051 |  | 2387401
JED-HRR2-RIYA-29 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 209866 | 209866 | 2025-11-05 10:36 |  | 2025 | 2026-03-29 |  | 2025-12-21 21:01 | 0 | 0 | 0 | 0 | 94 | 302 | 0 | 0 | 11396 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000653 | OSPWO0024378 | RITM0076806 |  | 2387401
JED-HRR2-RIYA-46 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 798422 | 798422 | 2025-11-05 10:44 |  | 2025 | 2026-04-30 |  | 2025-12-21 21:00 | 0 | 5824 | 0 | 16 | 48 | 301 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000664 | OSPWO0024424 | RITM0076829 |  | 2387401
JED-HRR2-RIYA-25 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 190265 | 190265 | 2025-11-05 10:34 |  | 2025 | 2026-02-25 |  | 2026-03-01 14:13 | 0 | 0 | 0 | 0 | 84 | 257 | 0 | 0 | 10462 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000627 | OSPWO0024366 | RITM0076800 |  | 2387401
TAI-QAIM-HASH-F4 |  | MAKKAH | FTTH | Fiber | 2 - PIP Approval | 24533 | 24533 | 2026-01-06 14:46 |  | 2026 |  |  | 2026-02-24 12:11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000535 | OSPWO0026989 | RITM0086050 |  | 2656301
JED-HRR2-RIYA-41 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 216927 | 216927 | 2025-10-27 13:19 | 2025-10-27 13:19 | 2025 | 2026-04-30 |  | 2025-12-24 17:08 | 0 | 0 | 0 | 0 | 65 | 284 |  | 0 | 14591 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000772 | OSPWO0023928 | RITM0076052 |  | 2387401
JED-HRR2-SALH-15 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 197912 | 197912 | 2026-01-04 09:05 | 2026-01-04 09:05 | 2026 | 2026-07-30 |  | 2026-03-01 13:47 | 0 | 0 | 0 | 0 | 133 | 258 |  | 0 | 18633 | 0 | 133 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 16 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402OSPFD0002483 | OSPWO0026597 | RITM0084714 |  | 2376401
TAI-QAIM-QIAA-10 |  | MAKKAH | FTTH | Fiber | 3 - Implementation | 229673 | 229673 | 2026-01-03 00:58 | 2026-01-03 00:58 | 2026 | 2026-04-30 |  | 2026-02-24 11:58 | 0 | 0 | 0 | 0 | 55 | 135 |  | 0 | 16159 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2302OSPFD0000446 | OSPWO0026560 | RITM0084116 |  | 2656101
JED-HRR2-RIYA-43 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 778031 | 778031 | 2025-11-05 10:42 |  | 2025 | 2026-03-31 |  | 2025-12-21 21:00 | 0 | 5766 | 0 | 12 | 56 | 279 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2302OSPCD0000753 | OSPWO0024412 | RITM0076823 |  | 2387401
JED-FRDS-MANA-05 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 729090 | 729090 | 2025-11-05 10:11 |  | 2025 | 2026-05-30 |  | 2025-12-21 21:00 | 0 | 4679 | 0 | 14 | 82 | 161 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2402OSPCD0001843 | OSPWO0024308 | RITM0076770 |  | 2382901
JED-FRDS-BUHA-F2 |  | MAKKAH | FTTH | Civil | 3 - Implementation | 254819 | 254819 | 2025-12-16 13:15 |  | 2025 | 2026-07-30 |  | 2026-02-22 22:25 | 0 | 1176 | 0 | 5 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2502OSPCD0002758 | OSPWO0026017 | RITM0079706 |  | 2382301
TUR-TRBH::TUR-SECO:01 |  | MAKKAH | CBU | Fiber | 3 - Implementation | 0 |  | 2025-09-01 12:00 |  | 2025 | 2026-04-30 |  | 2026-02-24 10:48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4455 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress |  | Implementation | OSP |  | Not Yet Requested |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OSPWO0022347 | RITM0072158 |  | 0 |  | Torbah PP 21.287766076248896, 41.70283329787832